## Slide 1: Change Delivery Pipeline July 22 – December 23
CSSC Go-Live
February 23 – Major Release
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992, XRN5298
July 22
February 23
June 23 – Major Release
XRN5091, XRN5186, XRN5482
November 22
June 23
November 23
XRN5515
XRN5316
XRN5231
XRN5469
November 23 – Major Release
XRN5472
XRN5143
No Major Release
XRN5379
XRN5236 – CMS Release1
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and Implementation Date not yet approved by ChMC
Delivery Key

## Slide 2: Change Pipeline - Delivery Plan July 2022 – February 2023
Slide produced 22nd July 2022
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5515 | HyDeploy Close Down | NGN | Shipper DN | DN DeCarb | N/A | July 2022 | Standalone | Firm
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | August 22 | Standalone | Indicative
5469 | Increase Frequency of FSG Payments | Cadent | DN | DN | £60K | September 22 | Standalone | Firm
5231 | FWACV Service | SGN | DN NG | DN NG | *£936K | 1st September 22 | Standalone | Firm
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | October 2022 | Standalone | Indicative
5236 | Reporting Valid Confirmed Theft of Gas in central systems (Modification 0734) | Gazprom | Shipper | Shipper | N/A | Oct / Nov 22 | CMS Rebuild Release 1 | Firm
4900 | Biomethane/Propane Reduction | SGN | Shipper DNO | DN Decarb | N/A | February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £150k | February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | SSE | Shipper | Shipper | £150k | February 23 | Major | Firm
4989 | Residual AMT activities | CDSP | Shipper | Shipper | £10k | February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DNO | Shipper DNO | £150k | February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | February 23 | Major | Firm

## Slide 3: Change Pipeline – Delivery Plan April 2023 – June 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | Tbc | 1st April 23 | Standalone | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | DN WWU, Cadent, NGN only | Tbc | 1st April 23 | Standalone | Firm
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | Shipper DN | Shipper DN | Tbc | 1st April 23 | Standalone | Firm
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | 350,000 | June 23 | Major | Indicative
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | 200,000 | June 23 | Major | Indicative
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper | Tbc | June 23 | Major | Indicative
Slide produced 22nd July 2022

## Slide 4: Change Backlog Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | Mod0651 – Retrospective Data Update Provisions | Cadent | Shipper | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5286 | Clarification Change to the AQ amendment process to be applied retrospectively (MO0746) | CDSP | Shipper DN | Shipper | Tbc | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5517 | Hydrogen Checker Website | Cadent | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
Slide produced 22nd July 2022

## Slide 5
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5529 | UNC Derogation Process – Mod 0800 | NGN | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5531 | Hydrogen Village Trial | SGN | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5532 | Hydrogen Town Trial | WWU | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5535 | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | DN IGT Shipper NGT | Shipper | Tbc | Tbc | Tbc | N/A
5541 | Amendments to the UIG Additional National Data Reporting | Scottish Power | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
Change Backlog Details - Continued
Slide produced 22nd July 2022