## Slide 1: Change Delivery Plan January 23 – April 24
February 23 - Major Release (XRN5533)
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992b, XRN5298
Jan-23
Aug-23
June 23 - Major Release (XRN5562)
XRN5091, XRN5186, XRN5482
Apr-23
Dec-23
Apr-24
November 23 – Major Release
XRN5604, XRN5605, XRN5607
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and/or Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 28 January 2023
March 23 - AdHoc Release (XRN5575)
XRN5379, XRN5143, XRN5472
XRN5595
XRN5555
February 24 – Major Release
XRN5535
XRN5567
XRN5602
XRN5606
XRN5454
XRN5547

## Slide 2: Change Pipeline - Delivery Plan - January 2023 – May 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | N/A | January 2023 | Adhoc | Indicative
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | January 2023 | AdHoc | Indicative
4900 | Biomethane/Propane Reduction | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Firm
4989 | Residual AMT activities | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DN | Shipper DNO | £108.7k | 25th February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm
5595 | Changes to the REC Switching Operator Outage Notification Lead Time (R0055) | Xoserve | Shipper | N/A | N/A | 25th Feb 23 | Major | Firm
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | 1st April 2023 | AdHoc | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | £75k | 1st April 2023 | AdHoc | Firm
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | Shipper DN | Shipper DN | £75k | 1st April 2023 | AdHoc | Firm
5606 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0813) | NGT | NGT Shipper Supplier | NGT | N/A | Following Ofgem Decision | Adhoc | Indicative
5602 | Releasing of unused capacity under a specific set of circumstances (Modification 0818) | NGN | Shipper DN | DN | N/A | Following Ofgem Decision | Adhoc | Indicative

## Slide 3: Change Delivery Plan - June 2023 – December 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | 24th June 23 | Major | Firm
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | 24th June 23 | Major | Firm
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper DN | £300k | June 23 (tbc) | Major | Indicative
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | July 23 | Tbc | Indicative
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | Tbc | July 23 | Tbc | Indicative
5535A | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | All DSC Customers | Shipper | £44k | August 23 | Adhoc | Indicative
5567 | Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067) | Xoserve | All DSC Customers | Shipper | £93k | August 23 | Adhoc | Indicative
5604 | Shipper Agreed Read (SAR) exceptions process (Modification 0811S) | SEFE | Shipper | Shipper | Tbc | November 23 | Tbc | Indicative
5605 | Amendments to the must read process (IGT159V) | Centrica | Shipper IGT | Shipper IGT | Tbc | November 23 | Tbc | Indicative
5607 | Update to the AQ correction processes (Modification 0816S) | EON Next | Shipper DN IGT | Shipper | Tbc | November 23 | Tbc | Indicative

## Slide 4
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | Tbc | Tbc | N/A
5531 | Hydrogen Village Trial | SGN | All DSC Customers | DN Decarb | Tbc | Tbc | Tbc | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Tbc | Tbc | Tbc | N/A
5573 | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) – Urgent | Xoserve | All DSC Customers | Part B - Tbc | Part B - Tbc | Part B - Tbc | Part B - Tbc | Part B - Tbc
5584 | Procurement of Climate Change Methodology for Demand Estimation Purposes | Xoserve | DN Shipper | DN Shipper | Tbc | Mid 2023 | AdHoc | Indicative
5585 | Flow Weighted Average Calorific Value - Phase 2 Service Improvements | Cadent | DN | DN | Tbc | Tbc | Tbc | N/A
5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | BUUK | Shipper IGT | Shipper IGT | Tbc | Tbc | Tbc | N/A
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | Tbc | Tbc | Tbc | N/A
Change Backlog Details
Title | Description | XRN | Proposer | Impact/Funding | Status | Release Type | Priority
R0048 | DCC Service Organisation Control 2 (SOC2) Assessments | N/A | DCC | - | Solution development | TBC | Low
R0073 | Introduction of a Housekeeping Change Proposal Process | N/A | Gemserv | - | Preliminary Assessment | TBC | Low
R0088 | Make Shipper NExA values available on the GES portal | N/A | Xoserve | - | New | Major, June 23 | Medium
REC IA Demand – Priority Change

## Slide 5: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | *Mod0651 – Retrospective Data Update Provisions* | Cadent | Shipper DN | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
*Mod0651 : 28.01.23 - Change Status remains on hold and will be reviewed on a monthly basis with ChMC – in line with request from UNCC

## Slide 6: DSC Change Pack Plan
February-23
March-23
April-23
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
Delivery Key
Slide produced 28 January 2023
XRN5535A - Processing of CSS Switch Requests Received in ‘Time Period 5’
XRN5454 – SOLR Reporting Suite
XRN5547 - Updating the Comprehensive Invoice Master List and INV template
XRN5606 - Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0813)
XRN5602 - Releasing of unused capacity under a specific set of circumstances (Modification 0818)
XRN5605 - Amendments to the must read process (IGT159V)
XRN5604 - Shipper Agreed Read (SAR) exceptions process (Modification 0811S)
XRN5379 - Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling)
XRN5556D – CMS Project
Isolation and Dead to Live Contacts