## 19-20 BP change details (hidden)
Title | Description | Amount | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4713: Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Enduring Solution | 165000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 165000
Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 38500
Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 330000
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 55000
Actual read following estimated transfer read calculating AQ of 1 | Interim solution for XRN4713 | 55000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 55000
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137500
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137500
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes | 137500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137500
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes | 110000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 110000
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | This was identified as part of ASP/AML improvement workshop. | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
Smart Metering Report | This is a report regarding Smart meter portfolio, can be generated from ISU as well as BW | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4044: Extension of ‘Must Read’ process to include Annual Read sites | Cadent Gas funded | 57000 | 0% | 100% | 0% |  | 0 | 57000 | 0 | 0
XRN4642: Address Maintenance Solution | CDSP Funded | 165000 | 7.119% | 51.04% | 1.462% | 40.38% | 11746.7058 | 84211.587 | 2412.4667 | 66629.2405
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. | 82500 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 82500
XRN4541: Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | DN Funded | 58000 | 0% | 100% | 0% | 0% | 0 | 58000 | 0 | 0
XRN4717: Use of up to date Forecast weather data in first NDM Nominations Run | New CP that is now witin the Capture phase. Proposed as a Nov 19 release candidate | 165000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 165000
Allowance for unforseen |  | 394000 | 7.119% | 51.04% | 1.462% | 40.38% | 28049.7096 | 201087.0622 | 5760.678 | 159102.5501
Total Change Budget 19-20 | [6 empty] | 39796.4155 | 400298.6491 | 8173.1447 | 2051731.7907

## Sheet2 (hidden)
Spend To date
June 19 Release ( XRN4679) | 51165.89
DDP | 50000
MOD700 | 40448

## Sheet1 (hidden)
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | Approved for Nov 19 | 76367 | 33% | 67% |  |  | 25201.11 | 51165.89 |  | DN
XRN4991: MOD700 |  |  |  | 80896 | 50% | 50% |  |  | 40448 | 40448 | Excluding June 20 | 141613.89
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 2020-06-01 | 247893
DN

## 19-20 - Spend to date (hidden)
| NTS £ | GDN£ | IGT £ | Shipper £ | [8 empty] | Budget £k | F cast £k | Fcast | Budget | Fcast
Change Budget 19/20 Pipeline | 0 | 171053.49 | 10299.9 | 731583.61 | [8 empty] | 2500 | 960.833 |  | 1539.167 | 960.833
19/20 Budget | #REF! | #REF! | #REF! | #REF!
Variance | #REF! | #REF! | #REF! | #REF!
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 2019-11-01 | 85913 | 100% |  |  |  | 85913 | 0 | 0 | 0
XRN4713: Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Enduring Solution | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 2019-06-01 | 24896 |  |  |  |  | 0 | 0 | 0 | 0
XRN4665: Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | EUC | 271954 | 100% |  |  |  | 271954 | 0 | 0 | 0
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 2019-06-01 | 23948 | 100% |  |  |  | 23948 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 2020-06-01 | 5187 |  | 90% |  | 10% | 0 | 4668.3 | 0 | 518.7
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 2020-06-01 | 5434 |  | 90% |  | 10% | 0 | 4890.6 | 0 | 543.4
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes | 137500 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes | 110000 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 2019-06-01 | 23000 |  |  |  |  | 0 | 0 | 0 | 0
XRN4677: Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | This was identified as part of ASP/AML improvement workshop. | 82500 | Cancelled | [5 empty] | 0 | 0 | 0 | 0
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | Approved for Nov 19 | 76367 | 33% | 67% |  |  | 25201.11 | 51165.89 | 0 | 0
Smart Metering Report | This is a report regarding Smart meter portfolio, can be generated from ISU as well as BW | 82500 | ? | [5 empty] | 0 | 0 | 0 | 0
XRN4044: Extension of ‘Must Read’ process to include Annual Read sites | Cadent Gas funded | 57000 | Cancelled | [5 empty] | 0 | 0 | 0 | 0
XRN4642: Address Maintenance Solution | CDSP Funded | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. | 82500 | No release identified | [5 empty] | 0 | 0 | 0 | 0
XRN4541: Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | DN Funded | 58000 | No release identified | [5 empty] | 0 | 0 | 0 | 0
XRN4717: Use of up to date Forecast weather data in first NDM Nominations Run | New CP that is now witin the Capture phase. Proposed as a Nov 19 release candidate | 165000 | No release identified | [5 empty] | 0 | 0 | 0 | 0
XRN4725: New read reason type for LIS estimate readings | Approved for Nov 19 |  | 2019-11-01 | 76367 | 100% |  |  |  | 76367 | 0 | 0 | 0
XRN4866: UIG Recommendation – removal of validation on uncorrected read | Will be a CR to Nov 19 |  | 2019-11-01 | 40000 | 100% |  |  |  | 40000 | 0 | 0 | 0
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | Approved for June 20 |  | 2020-06-01 | 5434 | 100% |  |  |  | 5434 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) Improvements | Approved for June 20 |  | 2020-06-01 | 9139 | 50% | 50% |  |  | 4569.5 | 4569.5 | 0 | 0
XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Descoped from June 20 | [7 empty] | 0 | 0 | 0 | 0
XRN4930 - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | Approved for June 20 |  | 2020-06-01 | 5928 | 100% |  |  |  | 5928 | 0 | 0 | 0
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Approved for June 20 |  | 2020-06-01 | 8151 |  |  |  | 100% | 0 | 0 | 0 | 8151
XRN4941 - Auto updates to meter read frequency (MOD0692) | Approved for June 20 |  | 2020-06-01 | 8892 | 100% |  |  |  | 8892 | 0 | 0 | 0
XRN4871B - Ratchet Regime Changes (Part B) - MOD0665 | Approved for June 20 |  | 2020-06-01 | 9880 |  | 100% |  |  | 0 | 9880 | 0 | 0
XRN4850 - Notification of Customer Contact Details to Transporters | Approved for June 20 |  | 2020-06-01 | 10868 |  | 90% |  | 10% | 0 | 9781.2 | 0 | 1086.8
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Approved for June 20 |  | 2020-06-01 | 5434 | 100% |  |  |  | 5434 | 0 | 0 | 0
XRN4857: Report Review- a formal audit view of all reporting, outputs and extracts |  |  | No release identified | 75845 | 100% |  |  |  | 75845 | 0 | 0 | 0
XRN4991: MOD700 |  |  |  | 72196 | 50% | 50% |  |  | 36098 | 36098 | 0 | 0
XRN5013 - Performance Assurance Framework Administrator Access to Data Discovery Platform |  |  |  | 50000 | 100% |  |  |  | 50000 | 0 | 0 | 0
XRN4980 - Change Supply Point Enquiry API to add in extra field and make certain other fields visible |  |  |  | 16000 | 100% |  |  |  | 16000 | 0 | 0 | 0
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 0 | 0
[9 empty] | 731583.61 | 171053.49 | 0 | 10299.9

## 19-20 Final Cost view (hidden)
| NTS £ | GDN£ | IGT £ | Shipper £ | [9 empty] | Budget £k | Actual |  | Budget | Actual
Change Budget 19/20 Actual cost | 0 | 344531.89 | 72698.6 | 983609.8168 | [9 empty] | 2500 | 1400.8403 |  | 1099.1597 | 1400.8403
19/20 Budget | #REF! | #REF! | #REF! | #REF! | [10 empty] | NTS £ | GDN£ | IGT £ | Shipper £ | Total
Variance | #REF! | #REF! | #REF! | #REF! | [9 empty] | 20/21 June 20 Release |  | 171819.3128 | 43255.2521 | 113689.8466 | 328764.4115
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £ |  | 20/21 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 2019-11-01 | 75174 | 100% |  |  |  | 75174 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 2019-06-01 | 24896 | 100% |  |  |  | 24896 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4665: Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | EUC | 268274 | 100% |  |  |  | 268274 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 2019-06-01 | 23948 | 100% |  |  |  | 23948 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 2020-11-01 | 5187 |  | 90% |  | 10% | 0 | 4668.3 | 0 | 518.7 |  |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 2020-11-01 | 5434 |  | 90% |  | 10% | 0 | 4890.6 | 0 | 543.4 |  |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 2019-06-01 | 23000 | 100% |  |  |  | 23000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | 2019-11-01 | 59097 | 33% | 67% |  |  | 19502.01 | 39594.99 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4725: New read reason type for LIS estimate readings | Approved for Nov 19 |  | 2019-11-01 | 59097 | 100% |  |  |  | 59097 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4866: UIG Recommendation – removal of validation on uncorrected read | Will be a CR to Nov 19 |  | 2019-11-01 | 25510 | 100% |  |  |  | 25510 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | Approved for June 20 |  | 2020-06-01 | 59984 | 100% |  |  |  | 59984 | 0 | 0 | 0 |  | 32131 | 100% |  |  |  | 32131 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) Improvements | Approved for June 20 |  | 2020-06-01 | 97579 | 50% | 50% |  |  | 48789.5 | 48789.5 | 0 | 0 |  | 51831.2915 | 50% | 50% |  |  | 25915.6457 | 25915.6457 | 0 | 0
XRN4930 - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | Approved for June 20 |  | 2020-06-01 | 48679.6684 | 100% |  |  |  | 48679.6684 | 0 | 0 | 0 |  | 24894.0466 | 100% |  |  |  | 24894.0466 | 0 | 0 | 0
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Approved for June 20 |  | 2020-06-01 | 54902 |  |  |  | 100% | 0 | 0 | 0 | 54902 |  | 27043.7336 |  |  |  | 100% | 0 | 0 | 0 | 27043.7336
XRN4941 - Auto updates to meter read frequency (MOD0692) | Approved for June 20 |  | 2020-06-01 | 31990.1193 | 100% |  |  |  | 31990.1193 | 0 | 0 | 0 |  |  | 100% |  |  |  | 0 | 0 | 0 | 0
XRN4871B - Ratchet Regime Changes (Part B) - MOD0665 | Approved for Nov 20 |  | 2020-11-01 | 9880 |  | 100% |  |  | 0 | 9880 | 0 | 0 |  | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
XRN4850 - Notification of Customer Contact Details to Transporters | Approved for June 20 |  | 2020-06-01 | 167345 |  | 90% |  | 10% | 0 | 150610.5 | 0 | 16734.5 |  | 162115.1856 |  | 90% |  | 10% | 0 | 145903.667 | 0 | 16211.5186
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Approved for June 20 |  | 2020-06-01 | 57903.5192 | 100% |  |  |  | 57903.5192 | 0 | 0 | 0 |  | 30749.1543 | 100% |  |  |  | 30749.1543 | 0 | 0 | 0
XRN4857: Report Review- a formal audit view of all reporting, outputs and extracts |  |  | No release identified | 72185 | 100% |  |  |  | 72185 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4991: MOD700 |  |  |  | 72196 | 50% | 50% |  |  | 36098 | 36098 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN5013 - Performance Assurance Framework Administrator Access to Data Discovery Platform |  |  |  | 50000 | 100% |  |  |  | 50000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4980 - Change Supply Point Enquiry API to add in extra field and make certain other fields visible |  |  |  | 15420 | 100% |  |  |  | 15420 | 0 | 0 | 0 | CCR | [5 empty] | 0 | 0 | 0 | 0
XRN4779 - Adding AQ to PARR Report |  |  |  | 31159 | 100% |  |  |  | 31159 | 0 | 0 | 0
XRN5064-Meter Asset enquiry API enhancement |  |  |  | 12000 | 100% |  |  |  | 12000 | 0 | 0 | 0
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
[9 empty] | 983609.8168 | 344531.89 | 0 | 72698.6 | [6 empty] | 113689.8466 | 171819.3128 | 0 | 43255.2521

## 19-20 Year End Forecast (hidden)
| NTS £ | GDN£ | IGT £ | Shipper £ | [9 empty] | Budget £k | F cast £k | Fcast | Budget | Fcast
Change Budget 19/20 Pipeline | 0 | 355523.6799 | 71268.1128 | 1038827.5259 | [9 empty] | 2500 | 1465.6193 |  | 1034.3807 | 1465.6193
19/20 Budget | #REF! | #REF! | #REF! | #REF! | [10 empty] | NTS £ | GDN£ | IGT £ | Shipper £ | Total
Variance | #REF! | #REF! | #REF! | #REF! | [9 empty] | 20/21 June 20 Release |  | 174041.5104 | 41701.2347 | 156977.8676 | 372720.6127
Title | Description | Amount | Status/Release | 19/20 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £ |  | 20/21 | Shipper % | GDN % | NTS % | IGT % | Shippers £ | GDN £ | NTS £ | IGT £
XRN4621: Suspension of the Validation between Meter Index and Uncoverted Converter Index | Reinstate suspended validations as customers are supplier invalid reads | 82500 | 2019-11-01 | 85913 | 100% |  |  |  | 85913 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4713: Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Enduring Solution | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4670: Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | This to increase operation efficiency , as processes done after receiving same read were redundant processes. | 38500 | 2019-06-01 | 24896 | 100% |  |  |  | 24896 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4665: Creation of new End User Categories (R&N portion of Sept 19 release) | Very High Complexity Change | 330000 | EUC | 271954 | 100% |  |  |  | 271954 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4687: PSR updates for large domestic sites | Remove validations from large domestic site for PSR updates | 55000 | 2019-06-01 | 23948 | 100% |  |  |  | 23948 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | SPA process changes | 137500 | 2020-11-01 | 5187 |  | 90% |  | 10% | 0 | 4668.3 | 0 | 518.7 | 2020-06-01 |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | SPA process changes | 137500 | 2020-11-01 | 5434 |  | 90% |  | 10% | 0 | 4890.6 | 0 | 543.4 | 2020-06-01 |  |  | 90% |  | 10% | 0 | 0 | 0 | 0
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | SPA process changes | 137500 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | SPA process changes | 110000 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4676: Reconciliation issues with reads recorded between D-1 to D-5. | This was identified as part of ASP/AML improvement workshop. | 82500 | 2019-06-01 | 23000 | 100% |  |  |  | 23000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4677: Daily report to identify mismatches in Amendment supporting information (ASP & AML files) | This was identified as part of ASP/AML improvement workshop. | 82500 | Cancelled | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4679: Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | New reason code to be created and estimation | 82500 | Approved for Nov 19 | 76367 | 33% | 67% |  |  | 25201.11 | 51165.89 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
Smart Metering Report | This is a report regarding Smart meter portfolio, can be generated from ISU as well as BW | 82500 | ? | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4044: Extension of ‘Must Read’ process to include Annual Read sites | Cadent Gas funded | 57000 | Cancelled | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4642: Address Maintenance Solution | CDSP Funded | 165000 | On hold | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Even though Site was isolated there was difference between last read before isolation and first read after isolation is removed. | 82500 | No release identified | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4541: Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | DN Funded | 58000 | No release identified | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4717: Use of up to date Forecast weather data in first NDM Nominations Run | New CP that is now witin the Capture phase. Proposed as a Nov 19 release candidate | 165000 | No release identified | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4725: New read reason type for LIS estimate readings | Approved for Nov 19 |  | 2019-11-01 | 76367 | 100% |  |  |  | 76367 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4866: UIG Recommendation – removal of validation on uncorrected read | Will be a CR to Nov 19 |  | 2019-11-01 | 40000 | 100% |  |  |  | 40000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads | Approved for June 20 |  | 2020-06-01 | 59100.11 | 100% |  |  |  | 59100.11 | 0 | 0 | 0 |  | 32044 | 100% |  |  |  | 32044 | 0 | 0 | 0
XRN4772 - Composite Weather Variable (CWV) Improvements | Approved for June 20 |  | 2020-06-01 | 95945.3193 | 50% | 50% |  |  | 47972.6596 | 47972.6596 | 0 | 0 |  | 84248 | 50% | 50% |  |  | 42124 | 42124 | 0 | 0
XRN4780 - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Approved for June 20 |  | 2020-06-01 | [5 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4930 - REQUIREMENT TO INFORM SHIPPER OF METER LINK CODE CHANGE | Approved for June 20 |  | 2020-06-01 | 47620.2555 | 100% |  |  |  | 47620.2555 | 0 | 0 | 0 |  | 24894.0466 | 100% |  |  |  | 24894.0466 | 0 | 0 | 0
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Approved for June 20 |  | 2020-06-01 | 53445.0983 |  |  |  | 100% | 0 | 0 | 0 | 53445.0983 |  | 27043.7336 |  |  |  | 100% | 0 | 0 | 0 | 27043.7336
XRN4941 - Auto updates to meter read frequency (MOD0692) | Approved for June 20 |  | 2020-06-01 | 30401 | 100% |  |  |  | 30401 | 0 | 0 | 0 |  |  | 100% |  |  |  | 0 | 0 | 0 | 0
XRN4871B - Ratchet Regime Changes (Part B) - MOD0665 | Approved for Nov 20 |  | 2020-11-01 | 9880 |  | 100% |  |  | 0 | 9880 | 0 | 0 | 2020-06-01 | 0 |  | 100% |  |  | 0 | 0 | 0 | 0
XRN4850 - Notification of Customer Contact Details to Transporters | Approved for June 20 |  | 2020-06-01 | 167609.1448 |  | 90% |  | 10% | 0 | 150848.2303 | 0 | 16760.9145 |  | 146575.0115 |  | 90% |  | 10% | 0 | 131917.5104 | 0 | 14657.5012
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Approved for June 20 |  | 2020-06-01 | 56932.3908 | 100% |  |  |  | 56932.3908 | 0 | 0 | 0 |  | 57915.821 | 100% |  |  |  | 57915.821 | 0 | 0 | 0
XRN4857: Report Review- a formal audit view of all reporting, outputs and extracts |  |  | No release identified | 75845 | 100% |  |  |  | 75845 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4991: MOD700 |  |  |  | 72196 | 50% | 50% |  |  | 36098 | 36098 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN5013 - Performance Assurance Framework Administrator Access to Data Discovery Platform |  |  |  | 50000 | 100% |  |  |  | 50000 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4980 - Change Supply Point Enquiry API to add in extra field and make certain other fields visible |  |  |  | 15420 | 100% |  |  |  | 15420 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
XRN4779 - Adding AQ to PARR Report |  |  |  | 36159 | 100% |  |  |  | 36159 | 0 | 0 | 0
XRN5064-Meter Asset enquiry API enhancement |  |  |  | 12000 | 100% |  |  |  | 12000 | 0 | 0 | 0
XRN5003: Data Access Platform DN Dashboard |  |  |  | 50000 |  | 100% |  |  | 0 | 50000 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
[9 empty] | 1038827.5259 | 355523.6799 | 0 | 71268.1128 | [6 empty] | 156977.8676 | 174041.5104 | 0 | 41701.2347

## 20-21 Year End Forecast
Current Month | [6 empty] | 2021-03-01
| NTS £ | GDN£ | IGT £ | Shipper £ | Total £ |  |  | NTS £ | GDN£ | IGT £ | Shipper £ | Total £
Change Budget 20/21 Pipeline | 1200 | 417912.6567 | 75484.9336 | 1099695.2665 | 1594292.8568 |  | Change Budget 20/21 Pipeline | 13950 | 485162.6567 | 75484.9336 | 1144695.2665 | 1719292.8568
20/21 Budget | 48000 | 600000 | 9000 | 2343000 | 3000000 |  | 20/21 Budget | 48000 | 600000 | 9000 | 2343000 | 3000000
Variance | -46800 | -182087.3433 | 66484.9336 | -1243304.7335 | -1405707.1432 |  | Variance | 12750 | 67250 | 0 | 45000 | 125000
Total
Movement since last report
[8 empty] | NTS £ | GDN£ | IGT £ | Shipper £ | Total £
[7 empty] | Varience in avilable funds since last report | 12750 | 67250 | 0 | 45000 | 125000
[7 empty] | 20/21 Budget | 0 | 0 | 0 | 0 | 0
[7 empty] | Variance | 59550 | 249337.3433 | -66484.9336 | 1288304.7335 | 1530707.1432
Title | Cost Type | Release | 19/20 spend | 20/21 Spend | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £ | last month | Diff? |  | 21/22 Committed Spend | BP21 Forecast | HLSO | BER | CCR | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £ | Comments | Proposed Release | BP21 Amount | Current Stage
4645a- The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CCR |  |  | 20000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 20000 | 20000 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4772 - Composite Weather Variable (CWV) improvements | CCR |  | 97578.5807 | 51831.2915 | 0% | 50% | 0% | 50% | 0 | 25915.6457 | 0 | 25915.6457 | 51831.2915 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4801 - Additional information to made veiwable on DES | BER | 2020-11-01 |  | 88703 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 88703 | 88703 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4850 - Notification of customer contact details to Transporters | CCR |  | 167344.5788 | 222162 | 0% | 90% | 10% | 0% | 0 | 199945.8 | 22216.2 | 0 | 222162 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4865 - Amendment to treatment and reporting of CYCL reads | CCR |  | 59984.478 | 32130.9009 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 32130.9009 | 32130.9009 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4871B Modification 0665 - Changes to ratchet regime | BER | 2020-11-01 | 9880 | 103501.73 | 0% | 70% | 0% | 30% | 0 | 72451.211 | 0 | 31050.519 | 103501.73 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4888 - Removing duplicate address update validation for IGT Supply Meter Points via CMS | CCR |  | 54901.791 | 27043.7336 | 0% | 0% | 100% | 0% | 0 | 0 | 27043.7336 | 0 | 27043.7336 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4897 - Resolution of deleted Contact Details (contained within the S66 records) at a change of Shipper event | BER | 2020-11-01 |  | 134798 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 134798 | 134798 | 0 | -17000 | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4899 - PSR - Change of Supplier event | BER | 2020-11-01 |  | 137162 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 137162 | 137162 | 0 | -17000 | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4930 - Requirements to inform Shipper of Meter Link Code Change | CCR |  | 48679.6684 | 24894.0466 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 24894.0466 | 24894.0466 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4931 - Submission of space in mandatory data on multiple SPA files | BER |  |  | 84034 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 84034 | 84034 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4932 - Improvements to the quality of the conversion factor values held on the supply point register (MOD0681S) | CCR |  | 57903.5192 | 30749.1543 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 30749.1543 | 30749.1543 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN5014 - Facilitating hydeploy live trials | BER | 2020-11-01 |  | 82200 | 0% | 100% | 0% | 0% | 0 | 82200 | 0 | 0 | 82200 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN5036 Updates to must read process | BER |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN5168 – MOD0721 – Shipper submitted AQ Corrections during COVID-19 | CCR |  |  | 32000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 32000 | 32000 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN5172 MOD0725 – Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19 | CCR |  |  | 9652 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 9652 | 9652 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4941 Auto updates to meter read frequency (MOD0692) | EQR | 2021-11-01 |  | 10000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 10000 | 10000 | 0 |  | 44694 | 25000 |  | 54694 |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 44694 | Costs shown here represent costs from original BER minus EQR value which will be drawn down from BP20 | 2021-11-01 | 25000
XRN4992 - MOD0687 creation of new charge to recover Last Resort Supply Payments | BER* |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 61760 | 100000 |  | 61760 |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 61760 | Costs taken from original BER | TBC | 100000
IGT DDP access | HLSO |  |  | 0 | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4780C - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | HLSO |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4876 - Changes to PARR Reporting | BER |  |  | 75000 | 1.6% | 20% | 0.3% | 78.1% | 1200 | 15000 | 225 | 58575 | 75000 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN4923-AQ calculation for RGMA (ONUPD) customer reads | HLSO |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN5120 MAP to UKL Monthly Comparison Service Part A | HLSO |  |  | 75000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 75000 | 75000 | 0 |  | 0 | [8 empty] | 0 | 0 | 0 | 0 |  |  | 0
XRN5135 DNO and NTS Invoices to Shippers and DNs VAT compliance | CCR |  |  | 0 | 17% | 83% | 0% | 0% | 0 | 0 | 0 | 0 | 75000 | 75000 |  | 0 | 600000 | [7 empty] | 0 | 0 | 0 | 0 | Being delivered via BP20/21 | MiR9 | 600000
XRN5146 Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES) | CCR |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 5000 | 5000 |  | 0 | 6000 | 5000 | [6 empty] | 0 | 0 | 0 | 0 | Being delivered via BP20/21 |  | 6000
XRN5183 - Access To Daily Biomethane Injections | HLSO |  |  | 5000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 5000 | 5000 | 0 |  |  | 35000 | [7 empty] | 0 | 0 | 0 | 0 |  | TBC | 35000
XRN5091 - Defferral of creation of class change reads at tranfer of ownership | HLSO * 10% to account for potential EQR (Design) costs required in FY 20/21 | 2021-11-01 |  | 25000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 25000 | 25000 | 0 |  | 175000 | 100000 | 200000 |  |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 175000 | Costs shown here represent HLSO costs minus EQR value to be taken from BP20 | 2021-11-01 | 100000
XRN5093 - Update of AUGE table to reflect new EUC band | BER 50% (+19K AUGE set up costs as per revised BER) | 2021-06-01 |  | 186031 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 186031 | 186031 | 0 |  | 167031 | 170000 |  | 167031 |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 167031 | Costs shown here respresent 50% of BER to cover work happening in BP21 | 2021-06-01 | 170000
XRN5142 New Allowable Values for DCC Service Flag in DXI File From DCC | EQR | 2021-11-01 |  | 10000 | 0% | 90% | 10% | 0% | 0 | 9000 | 1000 | 0 | 10000 | 0 |  | 190000 | 75000 | 200000 |  |  | 0% | 90% | 10% | 0% | 0 | 171000 | 19000 | 0 | Costs shown here represent HLSO costs minus 10k for EQR which is accounted for in BP20 | 2021-11-01 | 75000
XRN5038 - MOD0691 CDSP to convert class 3 or 4 meter points to Class 1 when G1.6.15 criteria is met | CCR | Standalone |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 45000 | 45000 |  | 45000 | 45000 |  |  |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 45000 |  |  | 120000
Market Trial for 2 Major releases |  |  |  | 0 | 1.6% | 20% | 0.3% | 78.1% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN 5072 - Class 4 with AMR/DRE installed-RGMA flow received with no RTC count | EQR | 2021-11-01 |  | 30000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 30000 | 30000 | 0 |  | 170000 | 100000 | 200000 |  |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 170000 | Costs shown here represent HLSO costs minus EQR funds which will be drawn down from BP20 | 2021-11-01 | 100000
XRN4645: The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Withdrawn |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN4691: CSEPs: IGT and GT File Formats (CGI Files) | Withdrawn |  | 5187 | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN4692: CSEPs: IGT and GT File Formats (CIN Files) | Withdrawn |  | 5434 | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN4693: CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | Withdrawn |  |  | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN4694: CSEPs: IGT and GT File Formats (Create new data validations ) | Withdrawn |  |  | 0 | 0% | 90% | 10% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN4780B - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | CCR |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN4990 - MOD0664 - Transfer of sites with low read submission performance | BP21 |  |  |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 |  | 0 |  |  | 250000 |  |  |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Awaiting HLSO | TBC | 250000
XRN5007 Enhancement to reconciliation process where prevailing volume is zero | EQR | 2021-11-01 |  | 20000 | 0% | 67% | 0% | 33% | 0 | 13400 | 0 | 6600 | 20000 | 0 |  | 130000 | 150000 | 150000 |  |  | 0% | 67% | 0% | 33% | 0 | 87100 | 0 | 42900 | Costs shown here represent HLSO costs - EQR value which will be drawn down from BP20 | 2021-11-01 | 150000
XRN5048 - Make an indicator available where a Supply Meter Point forms part of a Network Trial | Withdrawn |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5053 - Single sided nominations improvements | Gemini |  |  | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5054 - Negative implied flow rates | Gemini |  |  | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5070 - amendments to isolation flag | Withdrawn |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5080- Failure to supply gas (FSG/GSOP1)-System changes | MiR |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 50000 |  |  |  | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | Being delivered via MiR 9 | MiR | 50000
XRN5092 - iConversion phase2 | Gemini |  |  | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5116 Domestic Report - Must Read Prenotification | Withdrawn |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5120 MAP to UKL Monthly Comparison Service Part B | BP21 |  |  | 0 | [8 empty] | 0 | 0 |  |  | 150000 | [7 empty] | 0 | 0 | 0 | 0 |  | TBC | 150000
XRN5121 Supplier Portfolio Service | Withdrawn |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5122 Gemini System Enhancements - Delivery | Gemini |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5143 Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | BP21 |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 35000 |  |  |  | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | Awaiting HLSO | TBC | 35000
XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | BP21 |  |  | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5147 Optimising the Must Read process for IGT Customers | Withdrawn |  |  | 0 | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5153 iConversion Phase 2 | CCR |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5164 CSEP Data Assurance – Performance Monitoring Capability | BER |  |  | 25000 | 0% | 0% | 100% | 0% | 0 | 0 | 25000 | 0 | 25000 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5167 Report Product Class 4 Read Performance (MOD 672) | Investment |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5169 – MOD0722 – Allow Users to submit Estimated Meter Readings during COVID-19 |  |  |  | 0 | 0% | 67% | 0% | 33% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5170 – MOD0723 – User of the Isolation Flag to identify site with abnormal load reduction during COVID-19 period |  |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5171 – MOD0724 – Amendment to Ratchet charges during COVID-19 period |  |  |  | 0 | 0% | 67% | 0% | 33% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 25000 | [7 empty] | 0 | 0 | 0 | 0 |  | TBC | 25000
XRN5180 Inner Tolerance Validation for replacement reads and read insertions | EQR | 2021-11-01 |  | 20000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 20000 | 20000 | 0 |  | 130000 | 0 | 150000 |  |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 130000 | Change raised after budget set. Costs here are HLSO minus EQR | 2021-11-01 | 0
XRN5186 - MOD0701. Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | BP21 |  |  | 0 | 0% | 50% | 0% | 50% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 100000 |  |  |  | 0% | 50% | 0% | 50% | 0 | 0 | 0 | 0 |  | 2021-11-01 | 100000
XRN5187 - MOD0696v - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExA | BP21 |  |  | 0 | 0% | 50% | 0% | 50% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 30000 |  |  |  | 0% | 50% | 0% | 50% | 0 | 0 | 0 | 0 |  | 2021-11-01 | 30000
XRN5188 Interim Data Loads of MAP Id into UK Link | BP21 |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 35000 |  |  |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Awaiting HLSO | TBC | 35000
XRN5192 CMS Reference Number in Amendment Invoice Supporting Data | Withdrawn |  |  | 0 | 0% | 50% | 0% | 50% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 75000 |  |  |  | 0% | 50% | 0% | 50% | 0 | 0 | 0 | 0 |  |  | 75000
XRN5193 Stop MUR Generation of GT SMPs | Withdrawn |  |  | 0 | 0% | 50% | 0% | 50% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5195 Ceased Responsibility Date Following Shipper Withdrawal (IDL) | BP21 |  |  | 0 | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 120000 |  |  |  | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | Awaiting HLSO | TBC | 120000
XRN5196 Address Amendments Validation | Withdrawn |  |  | 0 | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5197 QMP File Validation in CMS – Current Address field | Withdrawn |  |  | 0 | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5199 Amendments to V12 of the SDT Service Description Table | N/A |  |  | 0 | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5200 Shipper Pack Transition to Data Discovery Platform | BP21 |  |  | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5206 TPI/PCW Access | CCR |  |  | 2400 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 2400 | 2400 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5210 - Daily CV Determination Service DN Invoicing Options | Withdrawn |  |  | 0 | [8 empty] | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5218 CDSP provision of Class 1 read service | HSLO approved, moved to BP21 to reflect when work will be done for Jun-21 implementation |  |  | 0 | 1% | 98% | 1% | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 50000 |  |  |  | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | Awaiting HLSO | TBC | 50000
XRN5231 - MOD0719R - Flow Weighted Average CV (FWACV) | BP21 |  |  | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 600000 |  |  |  | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | Awaiting HLSO | TBC | 600000
XRN5235 - Include SOQ in the “UIG Additional National Data” report (Originally introduced by XRN 4806) | BP21 | [12 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5236 - Reporting Valid Confirmed Theft of Gas into Central Systems (Modification 0734) | BP21 | [12 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5237 - Maintenance of a User relationship table for the purpose of AQ amendments (Modification 0736/0736A) | BP21 |  |  | 30000 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 30000 | 30000 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5238 - New Distribution Network Report – Forecast Invoice Values | BP21 | [12 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5244 – Shared IGT Deeds of Undertaking and CDSP Administration | BP21 |  |  | 0 | [8 empty] | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5246 - Confirmation File (.CNF) Processing Capacity Improvement | BP21 | [12 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5252 Amending the Formula Year AQ approach for 2021/2 Formula Year (Urgent MOD 0740) | Withdrawn |  |  | 0 | [8 empty] | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0
XRN5285 - Mod730 COVID-19 Capacity Retention Process | Withdrawn |  |  | 0 | 17% | 83% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
Total Change Budget 20-21 |  |  |  | 3000000 |  |  |  |  | 1200 | 417912.6567 | 75484.9336 | 1099695.2665 |  |  |  | 1113485 | 2926000 | [7 empty] | 0 | 258100 | 19000 | 836385
[12 empty] | 48000 | 600000 | 9000 | 2343000

## 20-21 Changes from last month
Title | Reason for change | New Amount | NTS % | GDN % | IGT % | Shippers % | NTS £ | GDN £ | IGT £ | Shippers £ | Costs in March | Total Variance to available funds | Varience NTS | Varience DN | Varience IGT | Varience Shipper
XRN5146 Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES) | Zero CCR costs replaced original HLSO of £5k | 0 | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 5000 | 0 | 0
XRN5135 DNO and NTS Invoices to Shippers and DNs VAT compliance | Zero CCR costs replaced original HLSO of £75k | 0 | 17% | 83% | 0% | 0% | 0 | 0 | 0 | 0 | 75000 | 75000 | 12750 | 62250 | 0 | 0
XRN5038 - MOD0691 CDSP to convert class 3 or 4 meter points to Class 1 when G1.6.15 criteria is met | CCR for approval @ zero cost (HLSO was £45k) | 0 | 0% | 0% | 0% | 100% | 0 | 0 | 0 | 0 | 45000 | 45000 | 0 | 0 | 0 | 45000
Total | [10 empty] | 125000 | 125000 | 12750 | 67250 | 0 | 45000

## BP21-22 Direct
Current Month | Shipper |  | DN |  | IGT |  | NTS |  | Total
Element | Budget | Spend | Budget | Spend | Budget | Spend | Budget | Spend | Budget | Spend
Change Budget | 1495000 | 1100367.75 | 900000 | 396822.45 | 140000 | 22081.8 | 54600 | 450 | 2589600 | 1519722
Split of Contingency | 288654.6185 | 0 | 173772.0111 | 0 | 27031.2017 | 0 | 10542.1687 | 0 | 500000 | 0
PAC Funding | 58434 | 58434 | 35457 | 35457 | 6109 | 6109 | 0 | 0 | 100000 | 100000
Xoserve Change Fund | 115461.8474 | 0 | 69508.8044 | 0 | 10812.4807 | 0 | 4216.8675 | 0 | 200000 | 0
Market Trials | 115461.8474 | 0 | 69508.8044 | 0 | 10812.4807 | 0 | 4216.8675 | 0 | 200000 | 0
Total | 2073012.3133 | 1158801.75 | 1248246.62 | 432279.45 | 194765.1631 | 28190.8 | 73575.9036 | 450 | 3589600 | 1619722
Previous Month | Shipper |  | DN |  | IGT |  | NTS |  | Total
Element | Budget | Spend | Budget | Spend | Budget | Spend | Budget | Spend | Budget | Spend
Change Budget | 1495000 | 871385 | 900000 | 302200 | 140000 | 19450 | 54600 | 450 | 2589600 | 1193485
Split of Contingency | 288654.6185 | 0 | 173772.0111 | 0 | 27031.2017 | 0 | 10542.1687 | 0 | 500000 | 0
PAC Funding | 58434 | 58434 | 35457 | 35457 | 6109 | 6109 | 0 | 0 | 100000 | 100000
Xoserve Change Fund | 115461.8474 | 0 | 69508.8044 | 0 | 10812.4807 | 0 | 4216.8675 | 0 | 200000 | 0
Market Trials | 115461.8474 | 0 | 69508.8044 | 0 | 10812.4807 | 0 | 4216.8675 | 0 | 200000 | 0
Total | 2073012.3133 | 929819 | 1248246.62 | 337657 | 194765.1631 | 25559 | 73575.9036 | 450 | 3589600 | 1293485
Monthly Variance | Shipper |  | DN |  | IGT |  | NTS |  | Total Committed Spend Varience
£ | -228982.75 |  | -94622.45 |  | -2631.8 |  | 0 |  | -326237
XRN | Title | HLSO | EQR | BER | CCR | Release Category | Total Committed Change Budget Spend | Shippers % | DN % | IGT % | NTS % | Shippers £ | DN £ | IGT £ | NTS £ | Value last month | Diff? | Notes
4941 | Auto updates to meter read frequency (MOD0692) | 30000 | 10000 | 221942 |  | 2021-11-01 | 211942 | 100% | 0% | 0% | 0% | 211942 | 0 | 0 | 0 | 44694 | -167248 | Costs show original BER costs minus £10k EQR costs which will be drawn from 20/21 budget
4992 | MOD0687 creation of new charge to recover Last Resort Supply Payments | 90000 |  | 61760 |  | Ready for delivery | 61760 | 100% | 0% | 0% | 0% | 61760 | 0 | 0 | 0 | 61760 | 0 | Costs taken from original BER
5091 | Defferral of creation of class change reads at tranfer of ownership | 200000 | 25000 |  |  | TBC | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 175000 | 175000 | Costs show HLSO minus approved EQR costs (£25k) which will be taken from BP20/21
5093 | Update of AUGE table to reflect new EUC band | 250000 | 30000 | 334062 |  | 2021-06-01 | 167031 | 100% | 0% | 0% | 0% | 167031 | 0 | 0 | 0 | 167031 | 0 | Costs show 50% of BER to cover work happening in BP21 (with eth other 50% taken from BP20)
5142 | New Allowable Values for DCC Service Flag in DXI File From DCC | 200000 | 10000 |  |  | 2021-11-01 | 216318 | 0% | 90% | 10% | 0% | 0 | 194686.2 | 21631.8 | 0 | 190000 | -26318 | Costs show HLSO minus approved EQR costs (£10k) which will be taken from BP20/21
5038 | MOD0691 CDSP to convert class 3 or 4 meter points to Class 1 when G1.6.15 criteria is met | 45000 |  |  | 0 | Standalone | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 45000 | 45000 | Costs are HLSO
5072 | Class 4 with AMR/DRE installed-RGMA flow received with no RTC count | 200000 | 30000 | 384482 |  | 2021-11-01 | 354482 | 100% | 0% | 0% | 0% | 354482 | 0 | 0 | 0 | 170000 | -184482 | Costs show HLSO minus approved EQR costs (£30k) which will be taken from BP20/21
4990 | MOD0664 - Transfer of sites with low read submission performance |  |  |  |  | TBC |  | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5007 | Enhancement to reconciliation process where prevailing volume is zero | 150000 | 20000 | 255875 |  | 2021-11-01 | 235875 | 33% | 67% | 0% | 0% | 77838.75 | 158036.25 | 0 | 0 | 130000 | -105875 | Costs show HLSO minus approved EQR costs (£20k) which will be taken from BP20/21
5120B | MAP to UKL Monthly Comparison Service Part B |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5180 | Inner Tolerance Validation for replacement reads and read insertions | 150000 | 20000 | 192314 |  | 2021-11-01 | 172314 | 100% | 0% | 0% | 0% | 172314 | 0 | 0 | 0 | 130000 | -42314 | Costs show HLSO minus approved EQR costs (£20k) which will be taken from BP20/21
5186 | MOD0701. Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs |  |  |  |  | TBC |  | 50% | 50% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5187 | MOD0696v - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExA |  |  |  |  | TBC |  | 50% | 50% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5188 | Interim Data Loads of MAP Id into UK Link | 20000 |  |  |  | TBC | 20000 | 100% | 0% | 0% | 0% | 20000 | 0 | 0 | 0 | 0 | -20000
5195 | Ceased Responsibility Date Following Shipper Withdrawal (IDL) |  |  |  |  | TBC |  | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5218 | CDSP provision of Class 1 read service | 45000 |  |  |  | Standalone | 45000 | 0% | 98% | 1% | 1% | 0 | 44100 | 450 | 450 | 45000 | 0 | Awaiting HLSO
5231 | MOD0719R - Flow Weighted Average CV (FWACV) |  |  |  |  | TBC |  | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort |  |  |  |  | TBC |  | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5200 | Shipper Pack Transition to Data Discovery Platform |  |  |  |  | TBC |  | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5235 | Include SOQ in the “UIG Additional National Data” report (Originally introduced by XRN 4806) |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5236 | Reporting Valid Confirmed Theft of Gas into Central Systems (Modification 0734) |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5238 | New Distribution Network Report – Forecast Invoice Values |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5244 | Shared IGT Deeds of Undertaking and CDSP Administration |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5246 | Confirmation File (.CNF) Processing Capacity Improvement |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5286 | Clarificatory change to the AQ amendment process to be applied retrospectively (Modification 0746) |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5319 | Assessing MPID Reassignment for All Party Types |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5318 | Assessing Supplier MPID Reassignment |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5298 | H100 Fife Project - Phase 1 (Initial Assessment) |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5299 | H100 Fife Project - Phase 1 (Initial Assessment) |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5309 | FSG: Automating the FSR (Mod0565) process |  |  |  |  | TBC |  | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 |  | 0 | Awaiting HLSO
5237 | XRN5237 - Maintenance of a User relationship table for the purpose of AQ amendments (Modification 0736/0736A) | 30000 |  |  |  | Standalone | 30000 | 100% | 0% | 0% | 0% | 30000 | 0 | 0 | 0 | 30000 | 0
5183 | XRN5183 - Access To Daily Biomethane Injections | 5000 |  |  |  | TBC | 5000 | 100% | 0% | 0% | 0% | 5000 | 0 | 0 | 0 | 5000 | 0
5321 | XRN5321 PAC Ring-fenced budget | 100000 |  |  |  | TBC | 100000 | 58.4% | 35.5% | 6.1% | 0% | 58400 | 35500 | 6100 | 0 | 100000 | 0

## 21-22 Changes from last month
XRN | Title | Reason for change | New Amount | Shippers % | DN % | IGT % | NTS % | Shipper £ | GDN £ | IGT £ | NTS | Costs in March | Total Variance to available funds | Varience Shipper | Varience DN | Varience IGT | Varience NTS
5038 | MOD0691 CDSP to convert class 3 or 4 meter points to Class 1 when G1.6.15 criteria is met | Despite HLSO of £45k the change delivered at zero cost as per CCR "We were able to utilise current resource to manage XRN5038 from 01 April 2021 and the amendment to an existing report to create the required reports under XRN5038 was able to be managed without additional funding" | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0
4941 | Auto updates to meter read frequency (MOD0692) | Approved BER for Nov-21 replaces HLSO. EQR amount (£10k) taken from BP20 budget | 211942 | 100% | 0% | 0% | 0% | 211942 | 0 | 0 | 0 | 44694 | -167248 | -167248 | 0 | 0 | 0
5007 | Enhancement to reconciliation process where prevailing volume is zero | Approved BER for Nov-21 replaces HLSO. EQR amount (£20k) taken from BP20 budget | 235875 | 33% | 67% | 0% | 0% | 77838.75 | 158036.25 | 0 | 0 | 130000 | -105875 | -34938.75 | -70936.25 | 0 | 0
5072 | Class 4 with AMR/DRE installed-RGMA flow received with no RTC count | Approved BER for Nov-21 replaces HLSO. EQR amount (£30k) taken from BP20 budget | 354482 | 100% | 0% | 0% | 0% | 354482 | 0 | 0 | 0 | 170000 | -184482 | -184482 | 0 | 0 | 0
5091 | Defferral of creation of class change reads at tranfer of ownership | Change descoped from Nov-21 | 0 | 100% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 175000 | 175000 | 175000 | 0 | 0 | 0
5142 | New Allowable Values for DCC Service Flag in DXI File From DCC | Approved BER for Nov-21 replaces HLSO. EQR amount (£10k) taken from BP20 budget | 216318 | 0% | 90% | 10% | 0% | 0 | 194686.2 | 21631.8 | 0 | 190000 | -26318 | 0 | -23686.2 | -2631.8 | 0
5180 | Inner Tolerance Validation for replacement reads and read insertions | Approved BER for Nov-21 replaces HLSO. EQR amount (£20k) taken from BP20 budget | 172314 | 100% | 0% | 0% | 0% | 172314 | 0 | 0 | 0 | 130000 | -42314 | -42314 | 0 | 0 | 0
5188 | Interim Data Loads of MAP Id into UK Link | HLSO approved (option 1) | 20000 | 100% | 0% | 0% | 0% | 20000 | 0 | 0 | 0 | 0 | -20000 | -20000 | 0 | 0 | 0
[13 empty] | -326237 | -228982.75 | -94622.45 | -2631.8 | 0

## Service Area Cost Splits
Number | Service Area | Shipper | NTS | DN and IGT | DN | IGT
1 | Manage supply point registration | 100%
2 | Provide query management | 90% |  |  | 10%
3 | Record, submit data in compliance with UNC | 100%
4 | Interruption auction services in accordance with UNC |  |  |  | 100%
5 | Metered volume and quantity | 33% |  |  | 67%
6 | Annual quantity, DM supply point capacity and offtake rate reviews | 100%
7 | NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoices |  | 17% |  | 83%
8 | Credit risk management (including cash collection) and management of neutrality accounting processes |  | 100%
9 | User admission and termination |  | 50% |  | 50%
10 | Connected system exit points |  |  |  | 100%
11 | NExA Supply Meter Points |  |  |  | 100%
12 | Generation of supply meter point reference number |  |  |  | 100%
13 | Emergency contact information |  |  |  | 100%
14 | Shipper agreed reads | 100%
15 | Demand Estimation | 50% |  |  | 50%
16 | Provision of supply point information services and other services required to be provided under condition of the GT Licence |  |  | 100%
17 | UK Link Services | 50% |  | 50%
18 | Provision of user reports and information | 34% | 7% | 59%
19 | Network operator and user relationship management | 50% | 6% | 44%
20 | Gemini system services |  | 100%
21 | Data flows and services to Network Operators |  | 6% | 94%
22 | Specific Services
23 | CSS Bid Services | 100%

## PAC reapportionment
| Shipper |  | DN |  | IGT |  | NTS |  |  |  | Constituency split based on current % weighting (inc NTS 2.1% also weighted appropriately)
Element | £ | % | £ | % | £ | % | £ | % | Total | Total Shortfall (with NTS removed) | Shipper (57.7% split of indirect costs) | DN (34.8% split of indirect costs) | IGT (5.4% split of indirect costs) | Remaining amount
Current PAC Funding | 57730.9237 | 57.73% | 34754.4022 | 34.75% | 5406.2403 | 5.406% | 2108.4337 | 2.108% | 100000 | 2108 | 1216.316 | 733.584 | 113.832 | 44.268
Suggested PAC Funding | 58433.7349 | 58.43% | 35457.2135 | 35.46% | 6109.0516 | 6.109% | 0 | 0% | 100000 |  | 25.5426 | 15.4053 | 2.3905
Delta | 702.8112 | 0.7028% | 702.8112 | 0.7028% | 702.8112 | 0.7028% | -2108.4337 | -2.108% | 2108.4337 | 2108 | 1241.8586 | 748.9893 | 116.2225
[11 empty] | 58.91% | 35.53% | 5.513%
| 702.8112 | [8 empty] | Current PAC Funding 21/22 | 57730.9237 | 34754.4022 | 5406.2403
[10 empty] | New PAC Funding | 58972.7823 | 35503.3915 | 5522.4628
| Shipper |  | DN |  | IGT |  | NTS |  |  | Difference | 1241.8586 | 748.9893 | 116.2225
Element | £ | % | £ | % | £ | % | £ | % | Total
Current PAC Funding | 57730.9237 | 57.73% | 34754.4022 | 34.75% | 5406.2403 | 5.406% | 2108.4337 | 2.108% | 100000
Suggested PAC Funding | 57730.9237 | 57.73% | 34754.4022 | 34.75% | 5406.2403 | 5.406% | 0 | 0% | 100000 |  | Shipper | DN | IGT
Delta | 0 | 0% | 0 | 0% | 0 | 0% | -2108.4337 | -2.108% | 0 | Current PAC Funding 21/22 | 57730.9237 | 34754.4022 | 5406.2403
[10 empty] | New PAC Funding 21/22 | 58972.7823 | 35503.3915 | 5522.4628
[10 empty] | Difference | 1241.8586 | 748.9893 | 116.2225