## Current Period Change
Regs ID (i.e. Mod, SPAA) | XRN | Title | Category | Status (Change Register)
Mod 0674 IGT138 | N/A | Performance Assurance Techniques and Controls | Pre-capture | Current
Mod 0686 (Urgent) | N/A | Removal of the NTS Optional Commodity Rate with adequate notice | Pre-capture | Current | Row Labels | Count of XRN
Mod 0705R | N/A | NTS Capacity Access Review | Pre-capture | Current | Capture | 23
Mod 0729 | N/A | Applying a discount to the Revenue Recovery Charge at Storage Points | Pre-capture | Current | Initial Review | 4
Mod 0737 | N/A | Transfer of NTS Entry Capacity from an abandoned ASEP | Pre-capture | Current | Pre-capture | 19
Mod 0739 | N/A | Aggregate overrun regime for Original Capacity held at the Bacton ASEPs | Pre-capture | Current | Grand Total | 46
Mod 0753 | N/A | Removal of Pricing Disincentives for Secondary Trading of Fixed Price NTS System Entry Capacity | Pre-capture | Current
Mod 0754R | N/A | Investigate Advanced Analytic Options to improve NDM Demand Modelling | Pre-capture | Current
Mod 0755 | N/A | Enhancement of Exit Capacity Assignments | Pre-capture | Current
Mod 0758 | N/A | Temporary extension of AUG Statement creation process | Pre-capture | Current
Mod 0759 | N/A | Enhancements to NTS Within-Day Firm Entry and Exit Capacity Allocations | Pre-capture | Current
Mod 0760 | N/A | Introducing the concept of derogation for Net Zero innovation into Uniform Network Code (UNC) | Pre-capture | Current
Mod 0761 | N/A | Arrangements for Interconnectors with additional Storage capability | Pre-capture | Current
Mod 0762 | N/A | Adding the Retail Energy Code Performance Assurance Code Manager as a new User type to the Data Permissions Matrix | Pre-capture | Current
Mod 0763R | N/A | Review of Gas Meter By-Pass Arrangements | Pre-capture | Current
Mod 0765 | N/A | New retrospective debit and credit charges to reflect changes to the treatment of Entry Capacity Revenue between October and December 2020 | Pre-capture | Current
Mod 0766 | N/A | Align TPD Section Y (Part A-I) to the National Grid Licence in respect of the NTS | Pre-capture | Current
Mod 0767 | N/A | Incorporation of AUGE Framework Document into the UNC main body | Pre-capture | Current
Mod 0786 | N/A | Retail Code Consolidation Significant Code Review | Pre-capture | Current
| XRN 4800 | TSO Visibility of System Balance at Interconnection Points | Initial Review | On Hold
| XRN 4810 | Chat Bot Automated Gemini Assistant | Initial Review | On Hold
| XRN 4978 | Notification of Rolling AQ value (following transfer of ownership between M-5 and M) | Capture | Current
MOD 0664 | XRN 4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | Capture | Current
| XRN 5143 | Discharge of Cadent, WWU and NGN NDM sampling obligations by the CDSP | Capture | Current
| XRN 5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Capture | Current
MOD 0701 | XRN 5186 | Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | Capture | Current
MOD 0696 | XRN 5187 | Modification 0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Capture | Current
| XRN 5218 | CDSP provision of Class 1 read service | Capture | Current
| XRN 5231 | Provision of a FWACV Service | Capture | Current
| XRN 5235 | Include SOQ in the “UIG Additional National Data” report (Originally introduced by XRN 4806) | Capture | Current
MOD 0734 | XRN 5236 | Reporting Valid Confirmed Theft of Gas into Central Systems (Modification 0734) | Capture | Current
| XRN 5238 | New Distribution Network Report – Forecast Invoice Values | Capture | On Hold
| XRN 5244 | Shared IGT Deeds of Undertaking and CDSP Administration | Capture | Current
| XRN 5246 | Confirmation File (.CNF) Processing Capacity Improvement | Capture | Current
MOD 0746 | XRN 5286 | Clarificatory change to the AQ amendment process to be applied retrospectively (Modification 0746) | Capture | Current
| XRN 5290 | CNC Bulk Network Report | Capture | Current
| XRN 5298 | H100 Fife Project - Phase 1 (Initial Assessment) | Capture | Current
| XRN 5299 | Future Billing Methodology (analysis only) | Capture | Current
| XRN 5318 | Assessing Supplier MPID Reassignment | Capture | Current
| XRN 5319 | Assessing MPID Reassignment for All Party Types | Capture | Current
| XRN 5321 | PAC Ring-Fenced DSC Change Budget 21/22 | Capture | Current
| XRN 5327 | Xoserve Change Fund 2021/22 | Initial Review | Current
| XRN 5343 | CMS Rebuild | Capture | Current
| XRN 5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at transfer of ownership | Capture | Current
| XRN 5352 | Development of the REC Performance Assurance reporting structure | Capture | Current
| XRN 5365 | Request impact assessment on aligning Major Releases to the REC Release Schedule (Thursday release and 3 Major Releases per year) | Initial Review | Current

## In Delivery
Regs ID (i.e. Mod, SPAA) | XRN | Title | Category | Status (Change Register) | Release Category
| XRN 4627 | CSS Consequential Central Switching Services | In Delivery | Current | CSSC
| XRN 4713 | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | In Delivery | Current | Standalone
| XRN 4780 | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | In Delivery | Current | Nov 21
| XRN 4869 | DC Exit Programme | In Delivery | Current | Standalone
| XRN 4876 | Changes to PARR reporting – provide further data to PAFA to aid analysis of performance reporting | In Delivery | Current | Standalone | Row Labels | Count of XRN
MOD 0651 | XRN 4914 | MOD 0651- Retrospective Data Update Provisions | Awaiting Delivery | Current | Ready for delivery | Awaiting Delivery | 6
| XRN 4920 | Review of the CSSC (Central Switching Service Consequential Changes) Gemini Business Requirements Document | In Delivery | Current | CSSC | Nov 21 | 1
| XRN 4921 | Review of the CSSC (Central Switching Service Consequential Changes) GT and IGT Business Requirements Document | In Delivery | Current | CSSC | Ready for delivery | 3
| XRN 4922 | Review of the CSSC (Central Switching Service Consequential Changes) Shipper Business Requirements Document | In Delivery | Current | CSSC | Standalone | 2
| XRN 4931 | Submission of a Space in Mandatory Data on Multiple SPA Files | Awaiting Delivery | Current | Ready for delivery | In Delivery | 22
MOD 0692 | XRN 4941 | Auto updates to meter read frequency (MOD0692) | In Delivery | Current | Nov 21 | CSSC | 4
MOD 0687 | XRN 4992 | Modification 0687 - Creation of new charge to recover Last Resort Supply Payments | Awaiting Delivery | Current | Ready for delivery | Jun 21 | 1
| XRN 4995 | Procurement of a Laboratory Study of within-pipe gas temperatures | Awaiting Delivery | On Hold | Standalone | Nov 21 | 6
| XRN 5004 | Golden Bullet Report | In Delivery | Current | Standalone | Standalone | 9
| XRN 5007 | Correction in the reconciliation process when volume is zero | In Delivery | Current | Nov 21 | MiR10 | 2
| XRN 5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes | In Delivery | Current | Nov 21 | Grand Total | 28
| XRN 5091 | Deferral of creation of Class change reads at transfer of ownership | Awaiting Delivery | Current | Nov 21
| XRN 5093 | Update of AUG Table to reflect new EUC bands | In Delivery | Current | Jun 21
| XRN 5120 | MAP to UKL Monthly Comparison Service | In Delivery | Current | Standalone
| XRN 5122 | Gemini System Enhancements - Delivery | In Delivery | Current | Standalone
| XRN 5142 | New Allowable Values for DCC Service Flag in DXI File From DCC | In Delivery | Current | Nov 21
| XRN 5180 | Inner Tolerance Validation for replacement reads and read insertions | In Delivery | Current | Nov 21
| XRN 5183 | Access to Daily Biomethane Injections | In Delivery | Current | Standalone
| XRN 5200 | Shipper Pack Transition to Data Discovery Platform | Awaiting Delivery | Current | Standalone
| XRN 5251 | Gemini Exit Zone Change | In Delivery | Current | Standalone
MOD 0745 | XRN 5341 | UNC745 - Mandatory Setting of Auction Bid Parameters | In Delivery | Current | Standalone
| XRN 5188 | Interim Data Loads of MAP Id into UK Link | In Delivery | Current | MiR10
| XRN 5309 | FSG - Automating the FSR ‘Standard Liability’ process | In Delivery | Current | MiR10

## Period updates
Regs ID (i.e. Mod, SPAA) | XRN | Title | Category | Update
Mod 0756S | N/A | Changes to Offtake Profile Notice Submission Requirements | Pre-capture | MOD to be implemented | Key - Updates
Mod 0752 | N/A | Introduction of Weekly Entry Capacity Auction | Pre-capture | MOD to be implemented | To be implemented
Mod 0741 | N/A | Updating specific gender references to neutral terms | Pre-capture | MOD to be implemented | Implemented
Mod 0767 | N/A | Incorporation of AUGE Framework Document into the UNC main body | New | New -Pre-capture | New
Mod 0786 | N/A | Retail Code Consolidation Significant Code Review | New | New -Pre-capture | Rejected by Ofgem
| XRN 5365 | Request impact assessment on aligning Major Releases to the REC Release Schedule | New | New - Initial Review | Awaiting/In Delivery
| XRN 5352 | Development of the REC Performance Assurance reporting structure | New | New - Capture | Withdrawn
| XRN 5251 | Gemini Exit Zone Change | New | In Delivery
MOD 0745 | XRN 5341 | UNC745 - Mandatory Setting of Auction Bid Parameters | New | In Delivery
MOD 0722 | XRN 5169 | UNMOD0722 (Urgent): Allow Users to submit Estimated Meter Reading during COVID-19 | Capture | Implemented
MOD 0723 | XRN 5170 | MOD0723 (Urgent): Use of the Isolation Flag to identify sites with abnormal load reduction during COVID-19 period | Capture | Implemented
MOD 0724 | XRN 5171 | MOD0724 (Urgent): Amendment to Ratchet charges during COVID-19 period | Capture | Implemented
| XRN 5038 | Convert Class 2, 3 or 4 meter points to Class 1 when G1.6.15 criteria are met (MOD 0691) | In Delivery | Implemented
| XRN 5200 | Shipper Pack Transition to Data Discovery Platform | Capture | Awaiting Delivery
| XRN 5091 | Deferral of creation of Class change reads at transfer of ownership | In Delivery | Awaiting Delivery
| XRN 5188 | Interim Data Loads of MAP Id into UK Link | Capture | In Delivery
| XRN 5309 | FSG - Automating the FSR ‘Standard Liability’ process | Capture | In Delivery
Row Labels | Count of XRN
MOD to be implemented | 3
In Delivery | 4
Awaiting Delivery | 2
Implemented | 4
New -Pre-capture | 2
New - Initial Review | 1
New - Capture | 1
Grand Total | 17

## Change Register Extract 260521
Last Updated | Reference Number | Change Title | Status | Origination Date | Proposer | Customer Change Team Lead | Release Type | Implementation Date | DSC Service Area | Shipper Impact | DNO Impact | IGT Impact | NGT Impact | Supplier Impact | GT Impact | Comsumer Impact | DCC Impact | DMSP Impact | MAP Impact | Timeline Status | Platform | Release Category
2019-01-10 | XRN 3667a | Provision of Formula Year AQ/SOQ to Proposing Users | Implemented | 2019-01-10 | Npower | uklink@xoserve.com | Other | 28/02/2019 | Service Area 22: Specific Services | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Release 3
2019-01-10 | XRN 4044 | Extension of ‘Must Read’ process to include Annual Read sites | Withdrawn | 2019-01-10 | National Grid | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | No | Yes | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-01-27 | XRN 4273 | Introducing IHD (In-Home Display) Installed Status of Failed MOD reference 614 | Implemented | 2019-01-15 | EDF Energy | uklink@xoserve.com | Major | 01/02/2019 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Implemented
2020-10-07 | XRN 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | Implemented | 2019-01-10 | National Grid | uklink@xoserve.com | Other | TBC | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | Implemented | Gemini | Standalone
2019-01-17 | XRN 4453 | Amendment to JOB / UPD Hierarchies to show ‘Irrelevant Datasets’ - Confirmation of File Format Changes and clarification on Version Control | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Minor | 01/03/2019 | N/A: Not applicable | Yes | No | No | No | No | No | No | No | No | No | Implemented
2020-01-27 | XRN 4454 | National Grid and Cadent Enduring Invoicing Arrangements | Implemented | 2019-01-23 | National Grid | uklink@xoserve.com | Major | 02/02/2019 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | No | No | No | Yes | No | No | No | No | No | No | Implemented
2019-01-15 | XRN 4534 | Amendment to RGMA Validation Rules for Meter Asset Installation Date | Implemented | 2019-01-15 | Centrica | uklink@xoserve.com | Major | 01/02/2019 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Implemented
2019-01-01 | XRN 4542 | Changes to the Shipper Portfolio Summary Report (new fields and removal of fields no longer applicable) | Implemented | 2019-03-21 | Gazprom | uklink@xoserve.com | Other | 16/11/2018 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2020-01-27 | XRN 4550 | Gemini Re-platform | Implemented | 2019-01-10 | National Grid | uklink@xoserve.com | Other | 05/07/2020 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | Implemented | Gemini | Standalone
2019-01-15 | XRN 4572 | Release 3 Detailed Design Delivery | Implemented | 2019-01-15 | Xoserve | uklink@xoserve.com | Major | 01/02/2019 | N/A: Not applicable | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | UK Link | Release 3
2019-11-08 | XRN 4621 | Suspension of the Validation between Meter Index and Uncoverted Converter Index | Implemented | 2019-01-11 | Orsted | uklink@xoserve.com | Major | 08/11/2019 | Service Area 22: Specific Services | Yes | No | No | No | No | No | Yes | No | No | No | Implemented | UK Link | Nov 19
2019-01-17 | XRN 4626 | Provision of an alternative Consumer Enquiry Service (Mnumber) - PHASE TWO Non-Web Portal Implementation | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Other | 01/07/2019 | N/A: Not applicable | No | No | No | No | No | No | Yes | No | No | No | Implemented | Data | Standalone
2019-09-18 | XRN 4627 | CSS Consequential Central Switching Services | Current | 2019-09-18 | Ofgem | uklink@xoserve.com | Minor | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | In Delivery
2019-01-11 | XRN 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service (Number) | Implemented | 2019-01-11 | Xoserve | uklink@xoserve.com | Other | 16/11/2018 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | N/A | N/A
2020-12-14 | XRN 4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Other | 29/10/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | Implemented |  | Standalone
2019-01-11 | XRN 4653 | National Grid Transmission iConversion Project | Implemented | 2019-01-11 | Xoserve | uklink@xoserve.com | Other | 31/03/2020 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | Implemented | Gemini | Standalone
2019-10-01 | XRN 4665 | Creation of new End User Categories | Implemented | 2019-01-11 | E.ON | uklink@xoserve.com | Major | 31/08/2019 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | UK Link | Standalone
2019-01-17 | XRN 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Major | 28/06/2019 |  | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Jun 19
2020-02-12 | XRN 4676 | Reconciliation issues with reads recorded between D-1 to D-5 | Implemented | 2019-01-17 | Xoserve | uklink@xoserve.com | Major | 28/06/2019 |  | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Jun 19
2019-12-08 | XRN 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | Implemented | 2019-01-11 | Xoserve | uklink@xoserve.com | Major | 08/11/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | No | No | No | No | No | No | No | No | Implemented | UK Link | Nov 19
2019-02-05 | XRN 4686 | Smart Metering Report | Withdrawn | 2019-02-05 | CNG | uklink@xoserve.com | Other | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2019-08-14 | XRN 4687 | PSR updates for large domestic sites | Implemented | 2019-01-11 | E.ON | uklink@xoserve.com | Major | 28/06/2019 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | Jun 19
2019-02-18 | XRN 4690 | Actual read following estimated transfer read calculating AQ of 1 | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Minor | 16/02/2019 | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | MiR3
2020-06-03 | XRN 4691 | CSEPs: IGT and GT File Formats (CGI Files) | Withdrawn | 2019-01-11 | Wales & West Utilities | uklink@xoserve.com | Major | TBC | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-06-03 | XRN 4692 | CSEPs: IGT and GT File Formats (CIN Files) | Withdrawn | 2019-01-11 | Wales & West Utilities | uklink@xoserve.com | Major | TBC | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2019-01-11 | XRN 4693 | CSEPs: IGT and GT File Formats. Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | Withdrawn | 2019-01-11 | Wales & West Utilities | uklink@xoserve.com | Major | TBC | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2019-01-11 | XRN 4694 | CSEPs: IGT and GT File Formats (Create new data validations ) | Withdrawn | 2019-01-11 | Wales & West Utilities | uklink@xoserve.com | Major | TBC | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2019-03-30 | XRN 4695 | Investigating causes and contributors to levels and volatility of Unidentified Gas | Implemented | 2019-01-11 | Xoserve | uklink@xoserve.com | Other | 30/03/2019 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | Implemented
2019-01-14 | XRN 4706 | National Grid Gas – Test Support & Consultancy on Connectivity between Xoserve & Gemini | Implemented | 2019-01-14 | National Grid | uklink@xoserve.com | Other | 31/10/2019 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | Implemented | Gemini | Standalone
2021-02-02 | XRN 4713 | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Current | 2019-01-14 | Npower | uklink@xoserve.com | Other | TBC | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | No | No | No | No | No | No | No | No | No | In Delivery | Data | Standalone
2020-05-18 | XRN 4716 | Increased Field Length – ‘Updated by’ data item | Withdrawn | 2019-02-15 | SGN | uklink@xoserve.com | Minor | TBC | N/A: Not applicable | Yes | Yes | Yes | Yes | No | No | No | No | No | No | N/A | N/A | N/A
2019-02-18 | XRN 4717 | Use of up to date Forecast weather data in first NDM Nominations | Implemented | 2019-01-14 | Total Gas and Power | uklink@xoserve.com | Minor | 16/02/2019 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | Yes | No | No | No | No | No | No | No | No | Implemented | UK Link | MiR3
2019-11-08 | XRN 4725 | New Read Reason Type for LIS Estimate Readings | Implemented | 2019-01-14 | Xoserve | uklink@xoserve.com | Major | 08/11/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Nov 19
2019-07-04 | XRN 4732 | June -19 Release Delivery | Implemented | 2019-04-24 | Xoserve | uklink@xoserve.com | Major | 28/06/2019 | N/A: Not applicable | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Jun 19
2019-01-14 | XRN 4738 | Shipper Portfolio Update of Proposed Formula Year AQ/SOQ | Implemented | 2019-01-14 | Npower | uklink@xoserve.com | Other | 31/03/2020 | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | Data | Standalone
2019-01-14 | XRN 4747 | Smart Meter Upgrade Notification Report | Implemented | 2019-01-14 | Npower | uklink@xoserve.com | Other | 18/01/2019 | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No | No | No | No | No | No | Implemented
2019-01-14 | XRN 4752 | Meter Read Performance | Implemented | 2019-01-14 | Xoserve | uklink@xoserve.com | Other | 15/03/2019 | Service Area 18: Provision of User Reports and Information | Yes | No | No | Yes | No | No | No | No | No | Yes | Implemented | Data | Standalone
2019-01-14 | XRN 4753 | CMS - Increase Information Provided in QCL Response File | Withdrawn | 2019-01-14 | BU-UK | uklink@xoserve.com | Major | 08/11/2019 | Service Area 2 (Previous Dec 18 – Mar 21): Provide Query Management | Yes | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2019-01-14 | XRN 4770 | NDM Sample Data – Mod 0654 Delivery | Implemented | 2019-01-14 | E.ON | uklink@xoserve.com | Minor | 22/02/2019 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | No | No | No | No | No | No | No | No | No | Implemented
2019-12-23 | XRN 4772 | Composite Weather Variable (CWV) Improvements | Implemented | 2019-01-14 | E.ON | uklink@xoserve.com | Major | 27/06/2020 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | Yes | No | No | No | No | No | No | No | No | Implemented | UK Link | Jun 20
2019-01-11 | XRN 4777 | Acceptance of Contact Details Updates | Implemented | 2019-01-11 | EDF Energy | uklink@xoserve.com | Minor | 27/07/2019 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | MiR4
2020-01-27 | XRN 4779 | UNC Modification 0657S - Adding AQ reporting to the PARR Schedule reporting suite | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Other | 11/03/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Standalone
2021-05-14 | XRN 4780 | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Current | 2019-01-11 | SSE | uklink@xoserve.com | Major | 05/11/2021 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | In Delivery | UK Link | MiR4
2020-05-13 | XRN 4785 | SSN Error proofing | Withdrawn | 2019-01-11 | National Grid | uklink@xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | N/A | N/A | N/A
2019-08-01 | XRN 4786 | Provision of Gemini data to Ofgem | Withdrawn | 2019-01-11 | National Grid | uklink@xoserve.com | Unallocated | TBC | Service Area 18: Provision of User Reports and Information | No | No | No | Yes | No | No | No | No | No | No | N/A | N/A | N/A
2020-05-13 | XRN 4787 | Rescheduling of failed SSN | Withdrawn | 2019-01-11 | National Grid | uklink@xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | N/A | N/A | N/A
2019-12-18 | XRN 4789 | Updating Shipper Reporting Packs and glossary | Implemented | 2019-01-11 | E.ON | uklink@xoserve.com | Other | 31/07/2019 | Service Area 18: Provision of User Reports and Information | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | Data | Standalone
2019-01-11 | XRN 4790 | Introduction of winter read/consumption reports and associated obligation (MOD0652) | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Other | 12/07/2019 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Standalone
2020-01-20 | XRN 4795 | Amendments to the PARR (520a) reporting | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Other | 15/11/2019 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | Yes | No | No | No | No | No | No | No | No | Implemented |  | Standalone
2019-11-11 | XRN 4800 | TSO Visibility of System Balance at Interconnection Points | On Hold | 2019-01-11 | National Grid | uklink@xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | Initial Review | Gemini | Standalone
2020-10-08 | XRN 4801 | Additional information to be made viewable on DES | Implemented | 2019-01-11 | Npower | uklink@xoserve.com | Major | 07/11/2020 | Service Area 22: Specific Services | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Nov 20
2019-01-14 | XRN 4803 | Amend AQI validation/processing | Implemented | 2019-01-14 | Npower | uklink@xoserve.com | Minor | 27/07/2019 | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | MiR4
2019-01-14 | XRN 4806 | Additional data at National Level to support UIG Allocation validation | Implemented | 2019-01-14 | Scottish Power | uklink@xoserve.com | Other | 29/03/2019 | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | No | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2019-11-11 | XRN 4810 | Chat Bot Automated Gemini Assistant | On Hold | 2019-01-14 11:01 | National Grid | uklink@xoserve.com | Unallocated | TBC |  | No | No | No | Yes | No | No | No | No | No | No | Initial Review | Gemini | Standalone
2019-01-14 | XRN 4813 | Migration of Xoserve Interfaces | Implemented | 2019-01-14 | National Grid | uklink@xoserve.com | Other | 29/04/2019 |  | No | No | No | Yes | No | No | No | No | No | No | Implemented | Gemini | Standalone
2020-01-27 | XRN 4824 | National Grid Transmission Daily Gemini Report | Withdrawn | 2019-01-17 | National Grid Transmission | uklink@Xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | N/A | N/A | N/A
2019-11-08 | XRN 4828 | Nov-19 Release Delivery | Implemented | 2019-01-16 | Xoserve | uklink@xoserve.com | Major | 08/11/2019 | N/A: Not applicable | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link
2019-01-16 | XRN 4833 | Roll Out of Business Intelligence and Data Discovery Capability | Implemented | 2019-01-16 | Xoserve | uklink@xoserve.com | Other | 07/05/2019 |  | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | Data | Standalone
2020-05-15 | XRN 4850 | Notification of Customer Contact Details to Transporters | Implemented | 2019-02-18 | Wales & West Utilities | uklink@xoserve.com | Major | 27/06/2020 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | Jun 21
2020-03-12 | XRN 4851 | Moving Market Participant Ownership from SPAA to UNC/DSC | Implemented | 2019-02-14 | E.ON | uklink@xoserve.com | Other | 28/02/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented |  | Standalone
2019-02-18 | XRN 4852 | Amendments to the DSC Change Management Procedures – aligning the procedures to the change process | Withdrawn | 2019-02-18 | E.ON | uklink@xoserve.com | Other | TBC | N/A: Not applicable | Yes | Yes | Yes | Yes | No | No | No | No | No | No | N/A | N/A | N/A
2019-02-14 | XRN 4853 | Interim process to monitor & manually load rejected reads into UK Link where the read was rejected for reason code MRE00458 only (UIG Recommendation 3.1 option 5) | Implemented | 2019-02-14 | Xoserve | uklink@xoserve.com | Other | 01/04/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2019-02-14 | XRN 4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | Withdrawn | 2019-02-14 | Cadent | uklink@xoserve.com | Unallocated | TBC | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | Yes | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-01-27 | XRN 4858 | Service Description Table updates February 2019 | Implemented | 2019-02-18 | Xoserve | uklink@xoserve.com | Other | 28/02/2019 |  | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | N/A | N/A
2020-07-13 | XRN 4860 | National ‘Temporary’ UIG Monitoring (1) | Withdrawn | 2019-02-14 | Npower | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2019-12-23 | XRN 4865 | Amendment to Treatment and Reporting of CYCL Reads | Implemented | 2019-03-05 | Xoserve | uklink@xoserve.com | Major | 27/06/2020 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Jun 20
2019-05-21 | XRN 4866 | Removal of validation on uncorrected read (UIG Recommendation) | Implemented | 2019-03-06 | Xoserve | uklink@xoserve.com | Major | 08/11/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Nov 19
2019-03-06 | XRN 4869 | DC Exit Programme | Current | 2019-03-06 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | Yes | No | No | Yes | No | No | No | No | No | No | In Delivery | Gemini | Standalone
2020-09-22 | XRN 4871 | Modification 0665 - Changes To Ratchet Regime | Implemented | 2019-03-06 | Gazprom Energy | uklink@xoserve.com | Major | 07/11/2020 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | Nov 20
2021-02-11 | XRN 4876 | Changes to PARR reporting – provide further data to PAFA to aid analysis of performance reporting | Current | 2019-03-05 | Gemserv | uklink@xoserve.com | Other | TBC | N/A: Not applicable | Yes | No | No | No | No | No | No | No | No | No | In Delivery | Data | Standalone
2020-04-09 | XRN 4887 | Service Description Table updates March 2019 | Implemented | 2019-03-06 | Xoserve | uklink@xoserve.com | Other | 28/02/2019 | N/A: Not applicable | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | N/A | N/A
2019-12-23 | XRN 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Implemented | 2019-03-06 | BU UK | uklink@xoserve.com | Major | 27/06/2020 | Service Area 2 (Previous Dec 18 – Mar 21): Provide Query Management | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | Jun 20
2019-03-14 | XRN 4894 | Shipperless and Unregistered Pre-Payment Supply Points Reconciliation | Withdrawn | 2019-03-14 | SGN | uklink@xoserve.com | Unallocated | TBC | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Yes | Yes | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-09-08 | XRN 4896 | Failure to Supply Gas System and Template Amendment | Implemented | 2019-07-30 | Xoserve | uklink@xoserve.com | Other | 14/08/2020 | Service Area 4 (Previous Dec 18 – Mar 21): Interruption Auction Services in accordance with UNC | Yes | Yes | No | No | No | No | No | No | No | No | Implemented |  | Standalone
2020-09-11 | XRN 4897 | Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event | Implemented | 2019-10-14 | Xoserve | uklink@xoserve.com | Major | 07/11/2020 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Nov 20
2020-05-15 | XRN 4899 | Treatment of Priority Service Register Data and Contact Details on a Change of Supplier Event | Implemented | 2019-10-14 | Xoserve | ukink@xoserve.com | Major | 07/11/2020 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Nov 20
2020-01-27 | XRN 4914 | MOD 0651- Retrospective Data Update Provisions | Current | 2019-04-04 | Cadent | uklink@xoserve.com | Major | TBC | TBC: To be confirmed | Yes | Yes | Yes | No | No | No | No | No | No | No | Awaiting Delivery | UK Link
2020-01-27 | XRN 4920 | Review of the CSSC (Central Switching Service Consequential Changes) Gemini Business Requirements Document | Current | 2019-04-17 | Xoserve | uklink@xoserve.com | Other | TBC | N/A: Not applicable | Yes | No | No | No | No | No | No | No | No | No | In Delivery | UK Link
2020-01-27 | XRN 4921 | Review of the CSSC (Central Switching Service Consequential Changes) GT and IGT Business Requirements Document | Current | 2019-04-17 | Xoserve | uklink@xoserve.com | Other | TBC | N/A: Not applicable | No | Yes | Yes | No | No | No | No | No | No | No | In Delivery | UK Link
2020-07-07 | XRN 4922 | Review of the CSSC (Central Switching Service Consequential Changes) Shipper Business Requirements Document | Current | 2019-04-17 | Xoserve | uklink@xoserve.com | Other | TBC | N/A: Not applicable | Yes | No | No | No | No | No | No | No | No | No | In Delivery | UK Link
2020-05-05 | XRN 4923 | AQ Calculation for RGMA (ONUPD) Estimate Reads | Withdrawn | 2019-07-30 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | No | No | No | No | No | No | Yes | No | No | N/A | N/A | N/A
2019-12-23 | XRN 4930 | Requirement to inform Shipper of Meter Link Code Change | Implemented | 2019-04-30 | Xoserve | uklink@xoserve.com | Major | 27/06/2020 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | Jun 20
2020-05-15 | XRN 4931 | Submission of a Space in Mandatory Data on Multiple SPA Files | Current | 2020-04-30 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Awaiting Delivery | UK Link | Ready for delivery
2019-12-23 | XRN 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Implemented | 2019-04-23 | E.ON | uklink@xoserve.com | Major | 27/06/2020 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | Jun 20
2021-05-18 | XRN 4941 | Auto updates to meter read frequency (MOD0692) | Current | 2019-05-17 | Total Gas & Power | uklink@xoserve.com | Major | 05/11/2021 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | In Delivery | UK Link | Nov 21
2019-11-04 | XRN 4946 | Reporting on Installed Meters with Conversion Capability | Withdrawn | 2019-05-30 | SSE | uklink@xoserve.com | Unallocated | TBC | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2019-10-16 | XRN 4954 | Minor Release Drop 5 | Implemented | 2019-06-05 | Xoserve | uklink@xoserve.com | Minor | 07/09/2019 | N/A: Not applicable | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | MiR5
2020-03-03 | XRN 4955 | Amendment of MDD PSR Needs Codes and Needs Code Descriptions | Implemented | 2019-05-30 | Wales & West Utilities | uklink@xoserve.com | Minor | 29/02/2020 | Service Area 18: Provision of User Reports and Information | Yes | Yes | Yes | No | Yes | No | No | No | No | No | Implemented | UK Link | MiR6
2019-07-04 | XRN 4977 | Amendments to DSC Change Management Guidelines | Implemented | 2019-07-04 | Xoserve | uklink@xoserve.com | Other | 07/08/2019 | N/A: Not applicable | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | N/A | N/A
2021-05-05 | XRN 4978 | Notification of Rolling AQ value (following transfer of ownership between M-5 and M) | Current | 2019-07-08 | British Gas | uklink@xoserve.com | Unallocated | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Capture |  | Capture
2020-01-16 | XRN 4980 | Change Supply Point Enquiry API to add in extra field and make certain other fields visible | Implemented | 2019-07-12 | Total Gas & Power | uklink@xoserve.com | Other | 12/12/2020 | Service Area 22: Specific Services | Yes | No | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2020-08-20 | XRN 4989 | Online end to End Credit Interest process - Defect 1063 | Implemented | 2020-06-02 | CDSP | uklink@xoserve.com | Minor | 20/11/2020 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | MiR7
2019-12-18 | XRN 4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | Current | 2019-08-01 | SSE | uklink@xoserve.com | Unallocated | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | No | Capture
2019-09-18 | XRN 4991 | Enabling large scale utilisation of Class 3 – MOD0700 | Implemented | 2019-08-01 | Gazprom | uklink@xoserve.com | Other | 28/09/2019 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | No | No | No | No | No | No | No | No | Implemented | UK Link | Standalone
2020-05-20 | XRN 4992 | Modification 0687 - Creation of new charge to recover Last Resort Supply Payments | Current | 2019-08-01 | Total Gas and Power | uklink@xoserve.com | Unallocated | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | No | No | No | No | No | No | No | No | Awaiting Delivery | UK Link
2019-09-04 | XRN 4993 | DSC Service Description Table cosmetic change to service line table as of April 2019 | Implemented | 2019-08-01 | Xoserve | uklink@xoserve.com | Unallocated | 28/02/2019 | N/A: Not applicable | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | Implemented | N/A | N/A
2019-08-02 | XRN 4994 | PAFA Contract Extension 2019/20 | Withdrawn | 2019-08-02 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2019-08-02 | XRN 4995 | Procurement of a Laboratory Study of within-pipe gas temperatures | On Hold | 2019-08-02 | Xoserve | uklink@xoserve.com | Other | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | Awaiting Delivery | Standalone | Standalone
2020-01-27 | XRN 4996 | June 2020 Release Delivery | Implemented | 2019-08-12 | N/A - Parent XRN | uklink@xoserve.com | Major | 27/06/2020 | N/A: Not applicable | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | Jun 20
2020-03-03 | XRN 4997 | Introducing new charge codes for GSoP3, GSoP13 and GT Voluntary Consumer Payments | Implemented | 2019-09-12 | Northern Gas Networks | uklink@xoserve.com | Minor | 29/02/2020 | Service Area 21: Data Flows and Services to Network Operators | Yes | Yes | No | No | No | No | No | No | No | No | Implemented | UK Link | MiR6
2019-11-27 | XRN 5003 | Data Access Platform DN Dashboard | Implemented | 2019-09-03 | Northern Gas Networks | uklink@xoserve.com | Other | 25/10/2019 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | No | Yes | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2019-12-13 | XRN 5004 | Golden Bullet Report | Current | 2019-09-03 | Wales & West Utilities | uklink@xoserve.com | Other | TBC | Service Area 18: Provision of User Reports and Information | No | Yes | No | No | No | No | No | No | No | No | In Delivery | Data | Standalone
2021-04-13 | XRN 5007 | Correction in the reconciliation process when volume is zero | Current | 2020-06-29 | Xoserve | uklink@xoserve.com | Major | 05/11/2021 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | No | No | No | No | No | No | No | No | In Delivery | UK Link | Nov 21
2020-01-27 | XRN 5013 | Performance Assurance Framework Administrator Access to Data Discovery Platform | Implemented | 2019-10-14 | SSE | uklink@xoserve.com | Other | 31/01/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2021-01-11 | XRN 5014 | Facilitating HyDeploy2 Live Pilot | Implemented | 2020-01-02 | Northern Gas Network | uklink@xoserve.com | Major | 07/11/2020 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | No | No | No | No | No | No | No | No | Implemented | UK Link | Nov 20
2020-01-14 | XRN 5027 | UK Link Data Cleanse of Conversion Factor in line with MOD0681S | Withdrawn | 2019-10-01 | E.ON | uklink@xoserve.com | Other | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-04-09 | XRN 5029 | Service Description Table updates October 2019 | Implemented | 2019-10-01 | Xoserve | uklink@xoserve.com | Other | 24/10/2019 | N/A: Not applicable | No | Yes | Yes | No | No | No | No | No | No | No | Implemented | N/A | N/A
2020-01-27 | XRN 5033 | Addition of low-level data to EUC Report | Implemented | 2019-11-06 | British Gas | uklink@xoserve.com | Other | 16/12/2019 | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2020-07-03 | XRN 5036 | Updates to must read process | Implemented | 2019-11-06 | Cadent Gas | uklink@xoserve.com | Minor | 04/07/2020 | Service Area 2 (Previous Dec 18 – Mar 21): Provide Query Management | No | Yes | No | No | No | No | No | No | No | No | Implemented | UK Link | MiR7
2021-04-30 | XRN 5038 | Convert Class 2, 3 or 4 meter points to Class 1 when G1.6.15 criteria are met (MOD 0691) | Implemented | 2019-11-06 | British Gas | uklink@xoserve.com | Other | 01/04/2021 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No | No | No | No | Yes | No | Implemented | Standalone | Standalone
2020-02-03 | XRN 5048 | Make an indicator available where a Supply Meter Point form part of a Network Trial | Withdrawn | 2020-01-02 | Northern Gas Network | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | No | Yes | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-07-13 | XRN 5053 | Single Sided Nominations Improvements | Implemented | 2019-12-04 | National Grid | uklink@xoserve.com | Other | 05/04/2020 | Service Area 20: UK Link Gemini System Services | Yes | No | No | Yes | No | No | No | No | No | No | Implemented | Gemini | Standalone
2020-08-12 | XRN 5054 | Negative Implied Flow Rates | Implemented | 2019-12-04 | National Grid | uklink@xoserve.com | Other | 05/04/2020 | Service Area 20: UK Link Gemini System Services | Yes | No | No | Yes | No | No | No | No | No | No | Implemented | Gemini | Standalone
2020-01-27 | XRN 5057 | Minor Release Drop 6 (Parent) | Implemented | 2019-12-18 | CDSP | uklink@xoserve.com | Minor | 29/02/2020 | N/A: Not applicable | Yes | Yes | No | Yes | No | No | No | No | No | No | Implemented | UK Link | MiR6
2020-03-31 | XRN 5064 | Meter Asset Enquiry API Enhancements | Implemented | 2019-12-18 | CDSP | uklink@xoserve.com | Other | 28/03/2020 | Service Area 18: Provision of User Reports and Information | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | Data | Standalone
2020-08-17 | XRN 5065 | Addition of Email Address to DES Last Accessed Report | Implemented | 2019-12-18 | Scottish Power | uklink@xoserve.com | Minor | 04/07/2020 | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No | No | No | No | No | No | Implemented | UK Link | MiR7
2020-01-17 | XRN 5070 | Amendment to Isolation Flag | Withdrawn | 2020-01-02 | E.ON | uklink@xoserve.com | Other | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2021-04-13 | XRN 5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes | Current | 2020-01-02 | Xoserve | ukink@xoserve.com | Major | 05/11/2021 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | Yes | No | No | No | No | No | In Delivery | UK Link | Nov 21
2021-04-06 | XRN 5080 | Failure to Supply Gas (FSG/GSOP1) – System Changes | Implemented | 2020-01-30 | Scotland and Southern Gas Networks SGN | uklink@xoserve.com | Minor | 20/03/2021 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | MiR9
2021-05-14 | XRN 5091 | Deferral of creation of Class change reads at transfer of ownership | Current | 2020-01-31 | EDF | uklink@xoserve.com | Major | TBC | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No | No | No | No | No | No | Awaiting Delivery | UK Link | Unallocated
2020-11-05 | XRN 5092 | iConversion Phase 2 | Implemented | 2020-01-31 | National Grid - Gas | uklink@xoserve.com | Other | 22/08/2020 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | Implemented | Gemini | Standalone
2020-12-14 | XRN 5093 | Update of AUG Table to reflect new EUC bands | Current | 2020-01-31 | Gazprom | uklink@xoserve.com | Major | 25/06/2021 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | No | No | No | No | No | No | No | No | No | In Delivery | UK Link | Jun 21
2020-08-12 | XRN 5097 | DSC Service Description Table cosmetic change to service line table v9 | Implemented | 2020-02-03 | CDSP - Xoserve | uklink@xoserve.com | Other | 28/02/2020 | N/A: Not applicable | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Implemented | N/A | N/A
2021-01-11 | XRN 5110 | November 20 Release Delivery | Implemented | 2020-02-27 | Xoserve | uklink@xoserve.com | Major | 07/11/2020 | N/A: Not applicable | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | Nov 20
2020-08-13 | XRN 5116 | Domestic Report - Must Read Prenotification | Withdrawn | 2020-02-28 | British Gas | uklink@xoserve,com | Unallocated | TBC | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-09-16 | XRN 5118 | Change to how ‘Actual MR date’ field is populated in UK Link | Implemented | 2020-09-02 | CDSP | uklink@xoserve.com | Minor | 21/11/2020 |  | No | No | No | No | No | No | No | No | Yes | No | Implemented | UK Link | MiR8
2020-09-11 | XRN 5120 | MAP to UKL Monthly Comparison Service | Current | 2020-02-27 | E.ON | uklink@xoserve.com | Other | TBC | Service Area 18: Provision of User Reports and Information | No | No | No | No | No | No | No | No | No | Yes | In Delivery |  | Standalone
2020-03-19 | XRN 5121 | Supplier Portfolio Service | Withdrawn | 2020-02-28 | CDSP | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | No | No | No | No | Yes | No | No | No | No | No | N/A | N/A | N/A
2021-05-18 | XRN 5122 | Gemini System Enhancements - Delivery | Current | 2020-03-02 | National Grid | uklink@xoserve.com | Other | 27/07/2021 | Service Area 20: UK Link Gemini System Services | No | No | No | Yes | No | No | No | No | No | No | In Delivery | Gemini | Standalone
2020-08-12 | XRN 5123 | DSC Service Description Table cosmetic change to Service Line Table | Implemented | 2020-03-02 | Xoserve | uklink@xoserve.com | Other | 23/03/2020 | N/A: Not applicable | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Implemented | N/A | N/A
2021-02-11 | XRN 5135 | DNO and NTS Invoices to Shippers and DNs VAT compliance | Implemented | 2020-07-23 | Wales & West Utilities | uklink@xoserve.com | Minor | 20/03/2021 | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | No | Yes | No | No | No | No | No | No | Implemented | UK Link | MiR9
2021-04-13 | XRN 5142 | New Allowable Values for DCC Service Flag in DXI File From DCC | Current | 2020-03-27 | Northern Gas Networks | uklink@xoserve.com | Major | 05/11/2021 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | No | No | No | No | No | No | No | Yes | No | No | In Delivery | UK Link | Nov 21
2020-09-22 | XRN 5143 | Discharge of Cadent, WWU and NGN NDM sampling obligations by the CDSP | Current | 2020-03-27 | Cadent Gas | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | No | No | No | No | No | No | No | No | Capture |  | Capture
2021-03-16 | XRN 5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Current | 2020-03-31 | CDSP | uklink@xoserve.com | Unallocated | TBC | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | Capture |  | Capture
2021-01-18 | XRN 5145 | DSC Service Description Table cosmetic change to Service Line Table v11 | Implemented | 2020-03-30 | CDSP - Xoserve | uklink@xoserve.com | Other | 14/10/2020 | N/A: Not applicable | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | Implemented | N/A | N/A
2021-03-16 | XRN 5146 | Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES) | Implemented | 2020-03-31 | Northern Gas | uklink@xoserve.com | Other | 15/02/2021 | Service Area 11 (Previous Dec 18 – Mar 21): NExA Supply Meter Points | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented |  | Standalone
2020-04-15 | XRN 5147 | Optimising the Must Read process for IGT Customers | Withdrawn | 2020-03-31 | BUUK | uklink@xoserve.com | Other | TBC | Service Area 22: Specific Services | No | No | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-09-11 | XRN 5152 | Minor Release Drop 7 | Implemented | 2020-09-03 | CDSP | uklink@xoserve.com | Minor | 04/07/2020 | N/A: Not applicable | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | MiR7
2020-08-26 | XRN 5153 | iConversion Phase 2 | Implemented | 2020-07-15 | Xoserve | uklink@xoserve.com | Other | 07/08/2020 | Service Area 20: UK Link Gemini System Services | No | Yes | No | No | No | No | No | No | No | No | Implemented | Gemini | Standalone
2020-07-13 | XRN 5156 | REC121 Report Amendment | Implemented | 2020-04-29 | NGN - Northern Gas Networks | uklink@xoserve.com | Other | 24/04/2020 | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | No | Yes | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2020-05-21 | XRN 5161 | UIG_Additional_National_Data_YYYYMM Frequency Change | Implemented | 2020-04-29 | Inspired Energy | uklink@xoserve.com | Other | 22/05/2020 | Service Area 15 (Previous Dec 18 – Mar 21): Demand Estimation | Yes | No | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2020-05-05 | XRN 5164 | CSEP Data Assurance Performance Monitoring Capability | Implemented | 2020-05-05 | Wales & West Utilities | ukink@xoserve.com | Other | 09/10/2020 | Service area 10 (Previous Dec 18 – Mar 21): Connected system exit points | No | Yes | Yes | No | No | No | No | No | No | No | Implemented | Data | Standalone
2020-11-09 | XRN 5167 | Report Product Class 4 Read Performance (MOD 672) | Implemented | 2020-05-04 | Scottish Power | uklink@xoserve.com | Other | 28/08/2020 | Service Area 3 (Previous Dec 18 – Mar 21): Record/submit Data in Compliance with UNC | Yes | No | No | No | No | No | No | No | No | No | Implemented | Data | Standalone
2020-11-09 | XRN 5168 | MOD0721 (Urgent) - Shipper submitted AQ Corrections during COVID-19 | Withdrawn | 2020-05-05 | Gaz Prom | uklink@xoserve.com | Other | TBC | Service Area 6 (Previous Dec 18 – Mar 21): Annual quantity, DM supply point capacity and offtake rate reviews | Yes | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-11-04 | XRN 5169 | UNMOD0722 (Urgent): Allow Users to submit Estimated Meter Reading during COVID-19 | Implemented | 2020-05-05 | Gaz Prom | uklink@xoserve.com | Other | 2020-05-12 | TBC: To be confirmed | Yes | No | No | No | No | No | No | No | No | No | Implemented | Standalone | Standalone
2020-05-14 | XRN 5170 | MOD0723 (Urgent): Use of the Isolation Flag to identify sites with abnormal load reduction during COVID-19 period | Implemented | 2020-05-05 | Northern Gas Networks | uklink@xoserve.com | Other | 2020-05-12 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | Standalone | Standalone
2020-05-14 | XRN 5171 | MOD0724 (Urgent): Amendment to Ratchet charges during COVID-19 period | Implemented | 2020-05-05 | Northern Gas Networks | ukink@xoserve.com | Other | 2020-05-12 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | Standalone | Standalone
2020-09-24 | XRN 5172 | Urgent Mod - Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19 | Withdrawn | 2020-05-11 | Gazprom | uklink@xoserve.com | Unallocated | TBC |  | Yes | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2021-01-19 | XRN 5174 | Agreed FINT Replacement Reads Incorrectly Triggering Rolling AQ Calculation | Implemented | 2020-09-02 | CDSP | uklink@xoserve.com | Minor | 21/11/2020 |  | No | No | No | No | No | No | No | No | Yes | No | Implemented | UK Link | MiR8
2021-05-14 | XRN 5180 | Inner Tolerance Validation for replacement reads and read insertions | Current | 2020-07-28 | CDSP | uklink@xoserve.com | Major | 05/11/2021 | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No | No | No | No | No | No | In Delivery | UK Link | Nov 21
2021-01-19 | XRN 5181 | Acceptance of Consumption Adjustment where meter removed after meter point set to Dead | Implemented | 2020-08-11 | CDSP | uklink@xoserve.com | Minor | 21/11/2020 | Service Area 4 (Previous Dec 18 – Mar 21): Interruption Auction Services in accordance with UNC | Yes | Yes | No | No | No | No | No | No | No | No | Implemented | UK Link | MiR8
2020-11-16 | XRN 5183 | Access to Daily Biomethane Injections | Current | 2020-08-19 | Inspired Energy PLC | uklink@xoserve.com | Minor | TBC | Service Area 18: Provision of User Reports and Information | No | Yes | No | No | No | No | No | No | No | No | In Delivery | UK Link | Standalone
2021-01-19 | XRN 5186 | Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | Current | 2020-06-01 | NGN | uklink@xoserve.com | Unallocated | TBC | Service Area 11 (Previous Dec 18 – Mar 21): NExA Supply Meter Points | Yes | Yes | No | No | No | No | No | No | No | No | Capture |  | Capture
2021-01-19 | XRN 5187 | Modification 0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Current | 2020-06-01 | Gazprom | uklink@xoserve.com | Major | TBC | Service Area 11 (Previous Dec 18 – Mar 21): NExA Supply Meter Points | Yes | Yes | No | No | No | No | No | No | No | No | Capture | UK Link | Capture
2021-05-14 | XRN 5188 | Interim Data Loads of MAP Id into UK Link | Current | 2020-06-04 | CDSP | uklink@xoserve.com | Minor | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | No | No | No | No | No | No | No | No | Yes | In Delivery | UK Link | MiR10
2020-07-03 | XRN 5192 | CMS Reference Number in Amendment Invoice Supporting Data | Withdrawn | 2020-06-29 | N Power | uklink@xoserve.com | Unallocated | TBC | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-06-29 | XRN 5193 | Stop MUR Generation of GT SMPs | Withdrawn | 2020-06-29 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 2 (Previous Dec 18 – Mar 21): Provide Query Management | Yes | Yes | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2021-01-19 | XRN 5195 | Ceased Responsibility Date Following Shipper Withdrawal (IDL) | Withdrawn | 2020-06-29 | Indigo Pipelines | uklink@xoserve.com | Unallocated | TBC | Service Area 21: Data Flows and Services to Network Operators | No | No | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-06-29 | XRN 5196 | Address Amendments Validation | Withdrawn | 2020-06-29 | BU-UK | uklink@xoserve.com | Unallocated | TBC | Service Area 21: Data Flows and Services to Network Operators | Yes | No | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-07-23 | XRN 5197 | QMP File Validation in CMS – Current Address field | Withdrawn | 2020-06-29 | Indigo Pipelines | uklink@xoserve.com | Unallocated | TBC | Service Area 21: Data Flows and Services to Network Operators | Yes | No | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-06-29 | XRN 5199 | Amendments to V12 of the SDT Service Description Table | Implemented | 2020-06-29 | Xoserve | uklink@xoserve.com | Other | 31/07/2020 | Service Area 21: Data Flows and Services to Network Operators | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | N/A | N/A
2021-03-10 | XRN 5200 | Shipper Pack Transition to Data Discovery Platform | Current | 2020-07-01 | E.ON | uklink@xoserve.com | Other | TBC | Service Area 18: Provision of User Reports and Information | Yes | No | No | No | No | No | No | No | No | No | Awaiting Delivery | Data | Standalone
2020-10-06 | XRN 5203 | Perspective Supply Metering Point AQ and EUC | Withdrawn | 2020-10-06 | Gazprom Energy | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | Yes | No | No | No | No | No | No | No | No | No | N/A | N/A | N/A
2021-01-12 | XRN 5206 | TPI/PCW Access | Implemented | 2020-07-08 | ENGIE | uklink@xoserve.com | Other | 15/01/2021 | Service Area 24: Additional Service Request or Third Party Request | No | Yes | No | No | Yes | No | Yes | No | No | No | Implemented | Data | Standalone
2021-01-19 | XRN 5209 | Amendments to the CDSP Service Document - Budget & Charging Methodology v4 | Implemented | 2020-07-16 | Xoserve | uklink@xoserve.com | Other | 01/04/2021 | N/A: Not applicable | No | No | No | No | No | No | No | No | Yes | No | Implemented | N/A | N/A
2020-11-03 | XRN 5210 | Daily CV Determination Interim Service: DN Invoicing Options | Withdrawn | 2020-09-09 | National Grid Gas | uklink@xoserve.com | Minor | TBC | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | No | Yes | No | Yes | No | No | No | No | No | No | N/A | N/A | N/A
2021-05-14 | XRN 5218 | CDSP provision of Class 1 read service | Current | 2020-08-03 | Wales and West Utilities | uklink@xoserve.com | Other | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Capture |  | Capture
2020-12-22 | XRN 5225 | Minor Release Drop 8 | Implemented | 2020-08-27 | CDSP | uklink@xoserve.com | Minor | 21/11/2020 |  | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | UK Link | MiR8
2020-09-10 | XRN 5231 | Provision of a FWACV Service | Current | 2020-08-28 | SGN | uklink@xoserve.com | Unallocated | TBC |  | Yes | Yes | No | Yes | No | No | No | No | No | No | Capture |  | Capture
2020-10-08 | XRN 5235 | Include SOQ in the “UIG Additional National Data” report (Originally introduced by XRN 4806) | Current | 2020-09-25 | Gazprom Energy | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | No | No | No | No | No | No | No | No | Capture |  | Capture
2020-10-09 | XRN 5236 | Reporting Valid Confirmed Theft of Gas into Central Systems (Modification 0734) | Current | 2020-09-25 | Gazprom Energy | uklink@xoserve.com | Unallocated | TBC | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No | No | No | No | No | No | Capture |  | Capture
2021-01-27 | XRN 5237 | Maintenance of a User relationship table for the purpose of AQ amendments (Modification 0736) | Implemented | 2020-09-24 | CDSP | uklink@xoserve.com | Other | 14/01/2021 | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No | No | No | No | No | No | Implemented | Standalone | Standalone
2021-02-22 | XRN 5238 | New Distribution Network Report – Forecast Invoice Values | On Hold | 2020-09-25 | Northern Gas Networks | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | No | Yes | No | No | No | No | No | No | No | No | Capture |  | Capture
2020-10-12 | XRN 5244 | Shared IGT Deeds of Undertaking and CDSP Administration | Current | 2020-09-25 | BUUK | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | No | No | Yes | No | No | No | No | No | No | No | Capture |  | Capture
2020-10-12 | XRN 5246 | Confirmation File (.CNF) Processing Capacity Improvement | Current | 2020-09-25 | CDSP | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | Yes | No | No | No | No | No | No | No | Capture |  | Capture
2021-05-18 | XRN 5251 | Gemini Exit Zone Change | Current | 2020-10-29 | National Grid | uklink@xoserve.com | Unallocated | TBC | Service Area 20: UK Link Gemini System Services | Yes | No | No | No | No | No | No | No | No | No | In Delivery | Gemini | Standalone
2020-10-12 | XRN 5252 | Amending the Formula Year AQ approach for 2021/2 Formula Year (Urgent MOD 0740) | Withdrawn | 2020-10-12 | EON | uklink@xoserve.com | Other | TBC | TBC: To be confirmed | Yes | Yes | Yes | No | No | No | No | No | No | No | N/A | N/A | N/A
2020-11-16 | XRN 5253 | June 21 Release | Current | 2020-10-29 | CDSP | uklink@xoserve.com | Major | 25/06/2021 | N/A: Not applicable | Yes | Yes | Yes | No | No | No | No | No | No | No | In Delivery | UK Link | Jun 21
2021-01-19 | XRN 5273 | Amendments to V14 of the Service Description Table | Implemented | 2020-10-30 | Xoserve | uklink@xoserve.com | Other | 18/11/2020 | N/A: Not applicable | Yes | Yes | Yes | No | No | Yes | No | No | No | No | Implemented | N/A | N/A
2021-03-24 | XRN 5285 | COVID-19 Capacity Retention Process (Mod 0730V) | Withdrawn | 2020-11-30 | CDSP | uklink@xoserve.com | Other | TBC | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Yes | Yes | No | Yes | No | No | No | No | No | No | N/A | Standalone | Standalone
2020-12-14 | XRN 5286 | Clarificatory change to the AQ amendment process to be applied retrospectively (Modification 0746) | Current | 2020-11-30 | CDSP | uklink@xoserve.com | Other | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | Yes | No | No | No | No | No | No | No | Capture |  | Capture
2021-05-18 | XRN 5289 | November 21 Major Release | Current | 2020-12-31 | Xoserve | uklink@xoserve.com | Major | 05/11/2021 | N/A: Not applicable | Yes | Yes | Yes | No | No | Yes | No | No | No | No | In Delivery | UK Link | Nov 21
2020-12-31 | XRN 5290 | CNC Bulk Network Report | Current | 2020-12-31 | Xoserve | uklink@xoserve.com | Other | TBC | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | No | Yes | Yes | No | No | No | No | No | No | No | Capture |  | Capture
2021-05-18 | XRN 5294 | Minor Release Drop 9 | Implemented | 2020-12-22 | CDSP | uklink@xoserve.com | Minor | 20/03/2021 | N/A: Not applicable | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | UK Link | MiR9
2021-03-04 | XRN 5298 | H100 Fife Project - Phase 1 (Initial Assessment) | Current | 2021-01-18 | SGN | uklink@xoserve.com | Unallocated | TBC | Service Area 1 (Previous Dec 18 – Mar 21): Manage Supply Point Registration | Yes | Yes | No | No | No | No | No | No | No | No | Capture |  | Capture
2021-03-04 | XRN 5299 | Future Billing Methodology (analysis only) | Current | 2021-01-21 | Cadent | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | No | Yes | No | Yes | No | No | No | No | No | No | Capture |  | Capture
2021-01-05 | XRN 5307 | Amendments to V15 of the Service Description Table | Implemented | 2021-01-05 | CDSP | uklink@xoserve.com | Other | 20/01/2021 | N/A: Not applicable | Yes | Yes | Yes | No | No | Yes | No | No | No | No | Implemented | N/A | N/A
2021-05-14 | XRN 5309 | FSG - Automating the FSR ‘Standard Liability’ process | Current | 2021-01-21 | SGN | uklink@xoserve.com | Minor | TBC | Service Area 7 (Previous Dec 18 – Mar 21): NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | No | Yes | Yes | No | No | No | No | No | No | No | In Delivery | UK Link | MiR10
2021-03-04 | XRN 5318 | Assessing Supplier MPID Reassignment | Current | 2021-02-01 | E.ON | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Capture |  | Capture
2021-03-04 | XRN 5319 | Assessing MPID Reassignment for All Party Types | Current | 2021-02-01 | E.ON | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Capture |  | Capture
2021-03-16 | XRN 5321 | PAC Ring-Fenced DSC Change Budget 21/22 | Current | 2021-02-25 | CDSP | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Capture |  | Capture
2021-03-16 | XRN 5327 | Xoserve Change Fund 2021/22 | Current | 2021-02-25 | CDSP | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Initial Review |  | Pre-capture
2021-03-23 | XRN 5329 | Amendments to V16 of the Service Description Table | Implemented | 2021-02-25 | CDSP | uklink@xoserve.com | Other | 17/03/2021 | N/A: Not applicable | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | N/A | N/A
2021-05-18 | XRN 5341 | UNC745 - Mandatory Setting of Auction Bid Parameters | Current | 2021-04-29 | National Grid | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | Yes | No | No | No | No | No | No | No | No | In Delivery | Gemini | Standalone
2021-03-29 | XRN 5343 | CMS Rebuild | Current | 2021-03-29 | Xoserve | uklink@xoserve.com | Other | TBC | N/A: Not applicable | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Capture | N/A | Capture
2021-05-05 | XRN 5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at transfer of ownership | Current | 2021-03-29 | Xoserve | uklink@xoserve.com | Unallocated | TBC | Service Area 5 (Previous Dec 18 – Mar 21): Metered Volume and Metered Quantity | Yes | No | No | No | No | No | No | No | No | No | Capture |  | Capture
2021-05-14 | XRN 5352 | Development of the REC Performance Assurance reporting structure | Current | 2021-04-29 | RECCo | uklink@xoserve.com | Unallocated | TBC | TBC: To be confirmed | Yes | No | Yes | No | No | No | No | No | No | No | Capture |  | Capture
2021-05-20 | XRN 5362 | Amendments to Service Description Table V17 | Implemented | 2021-04-29 | CDSP | uklink@xoserve.com | Unallocated | TBC | N/A: Not applicable | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Implemented | N/A | N/A
2021-05-19 | XRN 5365 | Request impact assessment on aligning Major Releases to the REC Release Schedule (Thursday release and 3 Major Releases per year) | Current | 2021-05-19 | Xoserve | uklink@xoserve.com | Other | TBC | TBC: To be confirmed | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Initial Review |  | Pre-capture