## Slide 1: Change Delivery Pipeline August 22 – December 23
CSSC Go-Live
February 23 - Major Release (XRN5533)
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992b, XRN5298
July 22
February 23
June 23 - Major Release (XRN5562)
XRN5091, XRN5186, XRN5482 (tbc)
November 22
June 23
November 23
XRN5515
XRN5231
XRN5469
November 23 – Major Release
No Major Release
XRN5236
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 28 October 2022
XRN5565
XRN5529
XRN5561
March 23 - AdHoc Release (XRN5575)
XRN5370, XRN5143, XRN5472

## Slide 2: Change Pipeline Delivery Plan - July 2022 - February 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5515 | HyDeploy Close Down | NGN | Shipper DN | DN DeCarb | N/A | 18th July 2022 | AdHoc | Delivered
5231 | FWACV Service – MOD 0793S | SGN | DN NG | DN NG | £1.198m | 1st September 22 | AdHoc | Delivered
5529 | UNC Derogation process – MOD 0800 | NGN | N/A | N/A | N/A | 1st October 22 | N/A | Delivered
5565 | CDSP as the Scheme Administrator for the Energy Price Guarantee for Domestic Gas Consumers – MOD 0824 | NGN | Shipper | Shipper | £1m – 1.5m | 1st October 22 | AdHoc | Delivered
5469 | Increase Frequency of FSG Payments | Cadent | DN | DN | £63.3k | 3rd October 22 | AdHoc | Delivered
5561 | Reform of Gas Demand Side Response (DSR) Arrangements – MOD 0822U | National Grid | NGT Shipper | NGT | N/A | 17th October 22 | AdHoc | Delivered
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | November 22 | AdHoc | Indicative
5236 | Reporting Valid Confirmed Theft of Gas in central systems – MOD 0734 | Gazprom | Shipper | Shipper | £74k | Oct / Nov 22 | CMS Rebuild Release 1 | Delivered (Not Live)
4900 | Biomethane/Propane Reduction | SGN | Shipper DNO | DN Decarb | N/A | 25th February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Firm
4989 | Residual AMT activities | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DNO | Shipper DNO | £108.7k | 25th February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm

## Slide 3: Change Pipeline March 2023 – June 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | March 23 | AdHoc | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | £75k | March 23 | AdHoc | Firm
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | Shipper DN | Shipper DN | £75k | March 23 | AdHoc | Firm
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | June 23 | Major | Indicative
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | June 23 | Major | Indicative
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper | Tbc | June 23 (tbc) | Major | Indicative

## Slide 4: Change Backlog Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | *Mod0651 – Retrospective Data Update Provisions* | Cadent | Shipper | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5517 | Hydrogen Checker Website | Cadent | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
*Mod0651 : Change Status currently on hold and will be reviewed on a monthly basis with ChMC – in line with request from UNCC

## Slide 5
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5531 | Hydrogen Village Trial | SGN | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5535 | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | DN IGT Shipper NGT | Shipper | Tbc | Tbc | Tbc | N/A
5541 | Amendments to the UIG Additional National Data Reporting | Scottish Power | Shipper | Shipper | N/A | Tbc | AdHoc | N/A
5545 | Hydrogen Trial Visualisation Dashboard | Northern Gas | DN IGT NGT Shipper | DN Decarb | Tbc | Tbc | Tbc | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | Tbc | February 2023 | Tbc | N/A
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | Tbc | Tbc | Tbc | N/A
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Tbc | Tbc | Tbc | N/A
5573 | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) – Urgent | Xoserve | DN IGT NGT Shipper | Part A – N/A ------------------ Part B - Tbc | Part A – N/A ------------------ Part B - Tbc | Part A - October 2022 ------------------------------- Part B - Tbc | Part A – AdHoc ------------------------ Part B - Tbc | Part A – Firm ------------------------ Part B – N/A
Change Backlog Details - Continued