## Sheet1
Item | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01
Shrinkage Forum | 2014-04-01: 2014-04-16; 2014-07-01: TBC; 2014-10-01: TBC; 2015-01-01: TBC
2015/16 Shrinkage Proposals | 2014-12-01: 31 Dec Initial Shrinkage Proposals Issued; 2015-01-01: Industry Consultation Period; 2015-02-01: Issue Resolution Period; 2015-03-01: 1 Mar Final Shrinkage Proposals Issued
2013/14 Shrinkage Assessment and Adjustment | 2014-07-01: 31 July Publication; 2014-08-01: 31 August Neutrality Invoice issued to Xoserve; 2014-09-01: Neutrality Invoice processed by Xoserve
Annual Shrinkage and Leakage Model Review | 2014-08-01: Development; 2014-10-01: Industry Consultation Period; 2014-11-01: Consultation Review; 2014-12-01: 31 Dec Submission to Ofgem & Industry
Bi Annual Shrinkage and Leakage Smart Metering Report | 2014-04-01: Development; 2014-06-01: Industry Consultation Period; 2014-07-01: 31 July Submission to Ofgem & Industry
Low Pressure Service Modification | 2014-04-01: Progress Update; 2014-05-01: Submission to Ofgem for Approval
Interference Damage Modification | 2014-04-01: Industry Discussion; 2014-05-01: Industry Consultation Period; 2014-06-01: Independent Review; 2014-07-01: Submission to Ofgem for Approval
AGI Venting Modification | 2014-04-01: DN Inventory Review