## Slide 1
DDP Update
18th January 2022

## Slide 2
XRN5321 Progress Update
Release 1
As PAFA I want to see how many transfer reads are being submitted, accepted / rejected each month and as a rolling 12-month view so that I can assess shipper's intent (DDP-388)
  Requirement fully developed & tested internally – PAFA testing anticipated w/e 14th January
As PAFA, for all Shippers, I want the AQ corrections dashlet to display the Reason codes for AQ correction so that I have a better understanding of the AQ correction information and the reason behind the corrections (DDP-198)
  Requirement fully developed & tested internally – PAFA testing anticipated w/e 14th January
As PAFA I want a view of AQ split by age bands for each Shipper so that I can get a view of how old the AQs are in their Portfolio (DDP-195)
DDP-22 As PAFA I want to view the Percentage of portfolio with AQ calculation split by 1, 4, 12, 24 & >36 months
  Requirement fully developed & tested internally – PAFA testing anticipated w/e 14th January
Release 2
As PAFA I want visibility of Meter Read Validity Monitoring, at Shipper & MPRN level, to provide further insight as to whether Shippers are meeting the required UNC expectations. This should provide a history of previous failures and AQ data so that the AQ "at Risk" can be determined. (DDP-193)
  Development progressing

## Slide 3
XRN5321 Plan
Release 3
As PAFA I want to see how many estimated opening reads are being replaced via the Shipper Agreed Read (SAR) process so that I can assess shipper's intent. (DDP-389)
  Development initiated
As PAFA I want to see the Isolation status on the detail view of the PAFA dashboard, so I can see if an MPRN is isolated. (DDP-401)
  Requirement fully developed & tested internally – PAFA testing anticipated w/e 14th January
As PAFA I want to see how many bypass flags are 'Open' and 'Closed' across the industry so that I can monitor how many sites are using the bypass and are not paying for gas so that I understand whether this is a risk. (DDP-402)
  Requirement fully developed & tested internally – PAFA testing anticipated w/e 14th January
Weeks | 01/10/2021 | 08/10/2021 | 15/10/2021 | 22/10/2021 | 29/10/2021 | 05/11/2021 | 12/11/2021 | 19/11/2021 | 26/11/2021 | 03/12/2021 | 10/12/2021 | 17/12/2021 | 24/12/2021 | 31/12/2021 | 07/01/2022 | 14/01/2022 | 21/01/2022 | 28/01/2022 | 04/02/2022 | 11/02/2022 | 18/02/2022 | 25/02/2022
Release 1 - (388, 195, 198) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Agile Delivery Cycle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Release Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Release 2 - (193) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Agile Delivery Cycle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Release Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Release 3 - (389, 401, 402) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Agile Delivery Cycle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Release Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 4
Backlog
Additional 4 User stories from the backlog:
  DDP-254 XRN5038 - Mod0691 - CDSP to convert Class 2, 3 or 4 sites to Class 1
  DDP-168 As PAFA I want 12 months rolling trend of count of MPRNs AQ> 732,000 where SCF is 1.02264 (XRN4932) (including auto change of SCF (MOD0681S)
  DDP-805 Read Performance Issues relating to Meter Asset & Meter Attribute Misalignment
  DDP-400 As PAFA I want to see the impact the replacement read is having on KWh reconciliation
    On hold until Reconciliation data is migrated to Big Data Platform

## Slide 5
AQ Read Performance (MOD0672)
1. AMR Categorisation
Annually Read Sites AQ <293000 w/o Smart /AMR (currently includes AMR MPRN)
Monthly Read Sites AQ <293000 With Smart /AMR (currently excludes AMR MPRN)
2. Date parameters
Currently the report is including meter reads received up to the date the report is run, as opposed to cutting off at the previous month end. E.g. The October report includes reads up to 10th October, instead of reads up to 30th September
Fixes for 1 & 2 were implemented on 30th November & the November report has now been run
3. Criteria to establish MPRN within Report
We are currently investigating the criteria for inclusion on the AQ Performance report to ensure that all relevant sites are included – exclusions will be made for Shipper gains < 12 months and change in meter read frequency.
4. Report Timing
Currently the report is run at M-1 (10th October for September position), however this will exclude some MPRN where reads are accepted after this point, that meet the D+25 read submission criteria - Xoserve will be discussing the report timing at Distribution Workgroup on 13th December & based on any decision re timing of report run changes will be made to cover any revision of requirements.