## Slide 1: CMS Rebuild Update
June Updates
Jo Williams

## Slide 2: CMS Rebuild - Progress to date
Summary of progress to date
Of the five options provided, we have now shortlisted two options to take forward Must Reads Workshop has been scheduled for the 10/06/21 to walk through additional improvement opportunities that have been identified Internal teams are revisiting the GSR process to see if additional improvements can be identified and built into the Ideal “To Be” process The requirements log has been refined and republished for review, we are instructing the previous attendees to take some time to review them before COP 15th June 2021 and advise if there are any changes required. The Project Team will assume that a nil response indicates that these high level requirements can be carried through to the Initiation and Detailed Design stage. We will continue to work with customers throughout these stages and will be establishing dedicated Design Sub Group (DSG) meetings for these. SDEP has again been raised as a potential duplication of effort so the team are liaising with another customer rep to understand their viewpoints on this tool so we can continue to assess the information The CMS Rebuild Team continue to work with the CSSC and REC team to input to the schedule reviews and identify any consequential impacts on the CMS processes Additional conversations regarding the TOG Mod have continued to ensure we are aligned with the latest updates Work has commenced on identifying the mandatory and optional data fields for all processes Preparation for the next stage of the project has now commenced
Key Milestones | Due
Capture Exit | 30/06/2021

## Slide 3: CMS Rebuild Start Up and Initiation Approval
Start Up and Initiation Details
The CMS Rebuild Team will exit Capture in June as per the indicative milestone. However, we are not yet able to determine the right solution due to: The fluidity of CSSC/Rec Code and consequence on CMS contacts Impacts to customers of an incremental or single implementation The need to finalise the high level requirements for the Must Read and GSR contacts On-going discussion on SDEP and potential duplication of functionality/process We want to ensure customers can make a fully informed decision without these current levels of risk and uncertainty. Therefore we propose that we continue into Initiation stage whereby these issues can be resolved and we can provide a fixed cost for delivery and operate. We would like to start to draw down on the CMS funds deferred from BP20 with an estimated cost of £135K We will continue with the high levels of collaboration with customers, through the introduction of a dedicated Design Sub Group (DSG) to ensure that detailed requirements and “to be” processes are fully understood and agreed. However, as promised, we will also use the Change Pack process to consult formally on design proposals to ensure all customer views are represented and considered.

## Slide 4: CMS Rebuild Approval
Capture Exit Details
We are seeking approval of the drawdown of £135K from BP20 deferred funds to source additional technical and business architects. Through more detailed analysis and design workshops we will be able to understand: The fluidity of CSSC/Rec Code and consequence on CMS contacts Impacts to customers of an incremental or single implementation High level requirements On-going discussion on SDEP and potential duplication of functionality/process Solution Identification Taking into account the forthcoming summer holidays we are anticipating that this will take 3 – 4 months.