## Slide 1: June 20 Major Release - Lessons Learned
Scope & Cost
  The scope of the release was not confirmed prior to the start of design resulting in changes being descoped after design works had already been started.
  The final costs for each of the changes were considerably higher than the initial costs quoted during capture (particularly for xrn4850). The capture process has been revisited to provide T-shirt size costings that aim to accurately reflect the complexity of the changes going forward with the BER providing final costs for scope of delivery.
Non Functional Requirements
  The volume impact, daily limits, managing bulk uploads were not fully identified in the requirements and also this could have been communicated earlier in the process. This caused timeline extensions and additional cost for Shippers who were ready to send bulk CNC files. Xoserve was able to increase the capacity of CNC batch processing enabling processing of larger CNC file volumes per day without impacting BAU processes.
Training
  Positive feedback was received from the industry for the external training provided however it was noted that it is sometimes difficult to target the correct external stakeholders in such sessions therefore limiting the audience. Following Go Live, additional sessions have been held with specific stakeholders.

## Slide 2: June 20 Major Release - Lessons Learned
File Formats
  Change Packs and training material to be enhanced to provide best practice examples of file formats. This will also include examples of an incorrect file format where the system would reject and the reasons why
  There were inputs needed or clarification required by Xoserve, which were not available at the start. For example, the CNF file formats (S66 record) were interpreted differently by different Shippers which led to unnecessary rejections immediately following implementation. At the earliest opportunity provide example files to the industry to avoid potential rework
Market Trials
  Shipper participation in Market Trials was discussed at ChMC and DSG and recommended by Xoserve. Had shippers been able to participate in Market Trials to enable cross party testing to ensure all new file formats are fully tested (both submission and response/rejections files), this could have eliminated some of the issues experienced post-go-live
  Network participants praised the Market Trials test phase. They were able to test the new functionality end to end and it gave them the opportunity to identify some additional requirements to improve the service which Xoserve are now assessing. However this test phase was not able to test the CNC shipper file flows which led to issues being experienced post go-live
Other
  The Commercial, Legal, Security and Architecture activities involved in implementing a new service requires far more time and diligence than a standard Major Release timeline allows, therefore if a new service is required in the future, to delivery outside of a major release should be explored