## Slide 1: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS DEC 2021 - DEC 2023
December 2021

## Slide 2
Programmes & Projects 2021-2023 |  |  |  | 2021 | 2022 |  |  |  |  |  |  |  |  |  |  |  | 2023
 |  |  |  | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | XRN5393 – Gemini Spring 22 Release |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | MOD0728B – UK Link & Gemini Delivered as part of CP5341 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | PM Hannah Reddy | Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Change Programme Sustain | PM Manisha Bhardwaj | Single Sign on Experience |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | API Enhancements |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Site Minder Upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS DEC 2021 – DEC 2023
Design to PIS -Dec 21 to Feb 22 – Indicative timeline
Design to PIS – Sept 21 to May 22 – Indicative timeline
PIS Gemini - Sept to Dec 21
Design to PIS – Jan 22 to Apr 22 – Indicative timeline
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk
Analysis & Design
Oct 21 – Dec 21
Testing – Dec 21 to Mar 22
PIS – From Apr 22 to Jun 22
Change Deployment
Apr 22
Pre-implementation/IDR
Mar 22 to Apr 22
Design to PIS - Nov 21 to Mar 22 – Indicative timeline