## Slide 1: XRN5562 – June 23 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking Amber, Start up and initiation phase is in progress. Build commenced and in progress ​Progress update:​ Start up and initiation phase is in progress and on track to be completed 02/02 All Level1 & Level2 milestones approved at DSC+ Change Decision board against approved detailed project plan Build phase commenced on 28/11 on track for completion against milestone of 10/02 System integration testing test cases approved Commenced system integration testing on 23/01 Decision in February ChMC: None |  | Implementation date of 24th June, with a contingency implementation date of 1st July | 
Risks and Issues | Medium 68572 - There is a risk that code changes made for different XRNs within the release will become interdependent because they will be affecting commons objects in the system(s). Mitigation Action – monitoring the risk with ongoing conversations with supplier. Currently no interdependency has been highlighted, will continue to monitor to the end of build. Expecting confirmation by 27/01 |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5091 - Deferral of creation of Class change reads at transfer of ownership XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  |  | 
Slide updated on 24th January 2023
Complete
On Track
At Risk
Overdue