## Slide 1: REC Update
Contract Management Committee
20 April 2022

## Slide 2: Planned Meetings Update & Key Milestones
CSS & GES (V3)
2020 |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  | 
Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Drafting commences​
V3 Opens
REC v2 Code Consolidation
Code Consolidation (V2)
Go Lives
Ofgem Consultation
CDSP FS
Contract Signature
REC/XO
Contractual​s'
V2 Closes
V3 Closes
GES Contract Signature
Enduring RECCo. Board Appointed
REC Manager Proc Completed
Opens
Closes
V3 Designated
V2 Designated
V1.1 Designated
REC V1.1
V2 Opens
REC V3 Fast Switching
REC V1.1 Interim Governance
Key:
Meeting Scheduled
Meeting Completed
Meeting Originally Planned
Latest Milestone Date
Original Milestone Date
Completed Milestone
REC Licence Changes
Opens
Closes
CC Statutory Licence Consultation
Opens
Closes
Opens
Closes
FS Statutory Licence Consultation
REC Consultation
Performance Assurance
Opens
Closes
Proposed Licence Changes Consultation
Designated
Designated
Response

## Slide 3: Ofgem Consultation Update V2
REC V2 - REC Code Consolidation Consultation
  Decision published 30 April 2021
  CR -D092 submitted on 21 June 2021 to implement V2 schedules, any further amendments will need to be raised via change control process.
CM Performance Assurance Consultation
  Decision published 2 July 2021
RCC Statutory Licence Changes Consultation
  Decision published 2 July 2021

## Slide 4: Ofgem Consultation Update V3
REC V3 – Faster Switching Schedules
  (Data Access Schedule; Interpretation; Data Management; Registration Service; Registrable Measurement Point Lifecycle; Address Management; Switching Service Management)
  Xoserve response to Q2.1 and Q2.2 shared with CoMC
  Xoserve submitted response 30 July
  Final version of GES SD baselined February 2022
  Xoserve seeking assurance from service provider that all requirements relating to GES provision can be met
  Update on Gate Closure Deadline discussions with Ofgem / DCC
Switching SCR
  Statutory Licence Changes to Gas Supply Licence
    Published 13 December 2021
    Closed 24 January 2022
  Statutory Licence Changes to Gas Shipper and Gas Transporter Licences
    Published 17 February 2022
    Close date 21st March 2022.

## Slide 5: SCR- Impacts to UNC
SCR –Code Consolidation REC V2 (Sept 2021)
  Amendments to UNC to align with REC (B;G;M; GT-D)
  Mod submitted by Ofgem for presentation at Mod Panel on 20 May /IGT Panel 28 May
  Notice to implement Mod768 issued 2 July
  Implementation to take effect 01 Sept 2021
SCR – Faster Switching REC V3 (summer 2022)
  Queried consequential changes published –awaiting further update
    We have been asked by Ofgem to describe the changes at DWG and RDUG
      We presented at DWG – no issues arising
      We provided the same update to IGT WG on 11/11/21
      Discussed at RDUG on 11/11/21
      Change in approach – consultation will now take place via UNC rather than RDUG as originally planned - text circulated 3rd December2021
      We are not seeking to amend from the version produced and provided to Ofgem in March 2021
      Potential change to GT-D
      Some numbering clarifications
      Further assessment required to consider Mods implemented since March 2021
Transition Mod – 0784S – Legal Text provided, WG Report to be concluded in January 2022.
SCR Mod – 0804 – Consultation closed out on 1st April 2022 – 3 supportive representations, no further detailed questions arising
PAFA – Ofgem has confirmed governance around provision of data to PAFA remains under UNC
DPM -
  DPM structure post REC – expected to retain same structure as today as PAFA will need ‘Retail’ data. CoMC will continue to approve release of this data to PAFA.
  DPM will maintain ‘Wholesale’ data permissions for other parties – e.g. Research Bodies and Local Authorities.
  Further work has progressed with RECCo on DAM – RECCo have issued DAM for review at RDUG (issued 07/04/22) – see subsequent slides on DAM / DPM alignment points

## Slide 6: Release of Protected Information to RECCo
UNC Mod 0762 and IGT UNC Mod 155 added the Retail Energy Code Company as a new User type to the Data Permissions Matrix – implemented with effect from 12 July 2021 (UNC) and 23 July 2021(IGT UNC)
Progressed work with the Performance Assurance (RPA) Code Manager in parallel with Mod development
  Anonymised data extract provided to RPA for assessment
  DRR approved at June CoMC
  Amended DRR approved at July CoMC
  Further amended DRR approved at October CoMC
We have been approached by RPA to start discussing future data requirements regarding REC v3

## Slide 7: Activities Completed
DSC CP has been raised (XRN5352 – Development of the REC Performance Assurance reporting)
  CP raised to cover support costs to:
    Perform analysis,
    Verify accessibility of data
    Generate sample reports (and redact / pseudonymise data until UNC / IGT UNC Mods approved)
  Continue to develop final RPA reporting
  First set of reports to be issued in November 2021
Discussions to be held with RECCo ahead of GES contract negotiations:
  DSC Customer access to gas enquiry services – provide verbal update following Ofgem conversations
  Scope of GES - verbal update following RECCo discussions to determine the scope of the Gas Enquiry Services RECCo will provide and the scope of the services Xoserve will provide to RECCo as the GES Provider.
Consequential changes required to SDT as a result of V2 go live approved at October CoMC

## Slide 8: Previous Discussion Points
Test Environment – until now there has been no enduring requirement
  DCC are proposing that they provide an enduring environment will now be required, we do not believe that we have a permanent test environment requirement
When does Xoserve stop onboarding new customers for services that are moving to GES? Agree no further customers to be onboarded post 01 May 2022. No further Research Body requests assessed post 01 April 2022.
Update on XRN5471 (Services to release data to UNC parties)
DSC party access to GES post CSS go live:
  DNs access as a REC Party (no separate Access Agreement)
  Shippers access as Non-Party REC Service User (sign separate Access Agreement)

## Slide 9: Next Steps
Xoserve to assess changes that will be required to the DSC at V3 go live – expect changes to fall into the following categories: cosmetic changes to align to UNC changes; changes to remove services that more into GES; removal of M Number Data File; introduction of GRDA role. Propose changes to be drafted for approval at May CoMC and to take effect from CSS Go Live.
Changes will be required to the CDSP Service Document -Third Party and Additional Services Policy (for approval at April CoMC)
  2.3.1 (e) the aggregate amount of the CDSP's turnover attributable to Third Party Services (excluding Charges payable under UK Link User Agreements) does not, and will not as a result of entering into the TPS Agreement, exceed 2.5% of the CDSP's overall turnover; and [propose to either carve out provision of GES or increase limit to 10%]
  2.4.1 ((b) other than in respect of a UK Link User Agreement with a Trader User [or the provision of the Gas Enquiry Service to RECCo], the term of the TPS Agreement does not exceed 24 months', or the CDSP may terminate the TPS Agreement without liability on not more than 24 months notice;
DSC Service Line Review has been initiated, and has progressed (see subsequent slides)
Commence work to remove M Number Data File at V3 go live – email to Ofgem requesting extension of service.
Assessing options to support DSC party access to data – discussion to be held following issue of customer communication relating to services being removed
Industry seminar held during 1st week of April – FAQs published on REC Portal and Salesforce
Further comms to be shared over coming weeks

## Slide 10: Other CM Engagements
Engagement ongoing with the Technical Assurance Code Manager
  Provision of metadata for EMAR population
  Need to define the process for provision of on-going change (and integration of the Change Management processes)
Engagement with Performance Assurance Code Manager
  Agreed scope for transition activities
  Align issuing of termination letters from Xoserve with Access Agreements from RECCo
  Discussions ongoing with RPA regarding reporting of Xoserve obligations (NB: GRDA will be covered under DSC)

## Slide 11: Other CM Engagements – for awareness
Engagement initiated with the Governance Code Manager
  Awaiting confirmation of what products are expected at what stage during the change cycle
    IA level – ROM? HLSO?
    Design products – High Level Solution options? Revised interface design formats (file formats / screens / rejection codes?)
      Impacts are not possible to assess until available
      We need to assess how this will integrate with the DSC change processes
  We understand that major releases would be implemented in line with electricity (Thursday evening), and that there will be three major releases (Feb / June / Nov)
    We anticipate that some types of releases relaxation of SLAs, amending invoice cycles

## Slide 12: Change Management Assessments
At the previous CoMC we agreed to highlight the changes received through the REC, we have proposed the following format … we provided the following as the proposal for the format – does this work?
Do we add to the CoMC agenda?
This has been added to ChMC

## Slide 13: DSC Service Lines Update
Contract Management Committee
April 2022

## Slide 14: DSC Service Lines
Mod 0804 Consultation closed out on 1st April 2022 – no detailed comments raised regarding the UNC drafting
Stable version of the SCR text against which to assess the DSC Service Lines
Completed the review of the ‘Direct Services Code Services’ – where significant number of the Changes will be required
  Propose 6 New Service Lines due to CSS – NB: plus 7th Service Line related to 0728B CNCCD
  Deletion of 1 Service Line
  Amendments to a large number of Service Lines to reflect new Code References / terminology change for CSS Supply Points
Amendments expected to ‘Agency Services GT - Non-Code’
  New Service Lines will be required
  Deletion of some existing Service Lines
Caveat! – Draft position as at 08/04/22 – update to be provided in CoMC (when JMc has validated DA work!) 

## Slide 15: Direct Services Code Services
Following CSS DSC SLs are proposed:
Following DSC Service Line is proposed for deletion:
New SL: | Equivalent of: | Comment
Respond to Detail Registration Nomination | Respond to Supply Point Nomination | 
Respond to Base Regn Nomn | Respond to SP Confirmation* | BRN provides Settlement Detail
Receipt and notification to DSC parties of relevant CSS Requests |  | CSS Request will provide Registration Detail
Receipt of Definitive Registration Notification |  | CSS Notice of Registration being Secured Active at Gate Closure
Maintain Shipper – Transporter Alliance Data | Sanction Data | 
Maintain Supplier – Shipper Alliance Data |  | Enables Shippers to authorise Suppliers to specify them as the Shipper in a CSS Request

## Slide 16: Agency Services GT - Non-Code
A number of new obligations are placed on the CDSP as the GRDA in the REC, expect that we will require New Service Lines to reflect these
We think that this is the correct approach:
  Non Code as it’s REC, not UNC
  [Doing these activities to ultimately meet your obligation in the Licence]
  [Consistent with where other REC Obligations reside]
Proposed Deletions from the Agency Services GT Non Code
  RDP File removal
  SPAA Schedule 23 / REC Transition Schedule DES Services

## Slide 17: Agency Services GT - Non-Code
Proposed Service Lines:
  Notification of Registerable Metering Point Data to CSS
    RMP Creation / move into scope of CSS
    MPL Address Change detail
    RMP Status Notification – incl Transformation of MP Status / Isolation Status / Meter Status
  Provision of [Regulatory Alliance] Data to CSS - (collated by the CDSP under the UNC as Shipper-Transporter Alliance Data G 5.8)
  Provision of [Commercial Alliance] Data to CSS - (collated by the CDSP under the UNC as Supplier-Shipper Alliance Data G 5.7)
  Notification of Supplier Agent Appointment to CSS
    MEM [and MAP] data to CSS
  Reporting on GRDA Performance for REC Performance Assurance Board
  Receipt of messages by GRDA from CSS