

## DSC Business Evaluation Report (BER)

|  |  |
| --- | --- |
| **Change Title** | XRN5231 Flow Weighted Average CV (FWACV) |
| **Xoserve reference number (XRN)** | 5231 |
| **Correla Project Manager** | Tom Lineham |
| **Email address** | Thomas.lineham@correla.com |
| **Contact number** | 0121 229 2075 |
| **Target Change Management Committee date** | 13th October 2021 |
| **Section 1: In Scope** |
| National Grid has announced it is to withdraw from providing the Distribution Network Operators (DNs) with the daily LDZ Flow-Weighted Average CV calculation (FWACV) service. As a consequence, the DNs will become responsible for calculating their own daily LDZ FWACVs and, publishing the information to Shippers. The associated 0719R Workgroup has assessed several options that might support the DNs in meeting their FWACV calculation/information provision obligations and through DSC governance the [agreed solution option](https://www.xoserve.com/media/42472/28785-mt-po-xrn5231-provision-of-a-fwacv-service-solution-review.docx) has been taken through the detailed design phase of the project as approved within the [EQR](https://www.gasgovernance.co.uk/sites/default/files/ggf/2021-08/4%20EQR%20-%20XRN5231%20-%20Flow%20Weighted%20Average%20CV%20%20V1.docx). The DNs have agreed that Xoserve should take the FWACV calculation role over in its entirety from National Grid and Xoserve are working to develop a single option solution. This BER is to approve the firm costs for the full delivery project to deliver the agreed solution option and the ongoing Manage The Business (MTB) Costs for the service to be operated.Activities covered by this BER include:* Full costs to deliver the agreed Flow Weighted Average CV solution under XRN5231.
* Indicative 1st Year MTB costs that will be confirmed at the end of the build stage following outstanding clarifications/service transition dependencies with National Grid and DNs being finalised.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **XRN** | **Title** | **Type** | **Description** | **Link to Change Proposal** | **Impacts** |
| 5231 | Provision of a FWACV Service | CP | Provision of a Flow Weighted Average CV service on behalf of the Distribution Networks to calculate daily LDZ FWACVs and, publishing the information to Shippers. | [Link](https://www.xoserve.com/media/42582/xrn5231-provision-of-a-fwacv-service-v10.pdf) | DNs |

 |
| **Section 2: Out of Scope** |
|  |
| * Any additional changes not defined in Section 1 – In Scope will be subject to change control.
* National Grid (NG) consequential changes (Gemini & Mipi) are currently out of scope of this project however it is anticipated they will need to be included and is subject to discussion with National Grid. This will be confirmed once discussions with NG are finalised.
	+ XRN5382 - Part A - PRCMS validation/processing
	+ XRN5383 – Part B - LDZ Stock Change and Embedded LDZ Unique Sites
 |
| **Section 3: Funding required to deliver the change** |
| The following section outlines the costs to deliver the project for XRN5231 and the 1st Year MTB costs to run the service (please note that finalisation of the MTB costs will be confirmed at the end of the build phase once outstanding clarifications/service transition dependencies with National Grid and Distribution Networks (DNs) are finalised). **BER Costs**

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **XRN Ref** | **HLSO** | **Design**  | **Build** | **Test (inc Market Trials & Dual Run)** | **Imp / PIS** | **1st Year MTB** | **Risk Margin** | **BER Delivery Total** | **Shipper %** | **DN%** | **IGT%** | **NTS %** |
| XRN5231 Flow Weighted Average CV |  £600,000  | £50,400  |  £123,608  |  £314,871  |  £160,681  | £67,019  |  £101,121  |  £817,700 |   | 100% |   |   |

The Design cost of £50,400 was approved via an EQR at the August 2021 ChMC for XRN5231. **Key** |
| **Section 4: Estimated impact of the service change on service charges** |
| **Manage The Business (MTB) Costs**

|  |  |  |  |
| --- | --- | --- | --- |
| **XRN** | **Xoserve Service Area & Line** | **Impact** | **(+/-) Projected Change in Annual Cost** |
| 5231 | Service Area 10 - Invoicing Customers | New Service Line being included within the Service Area | **£67,019 (**1st Year MTB**)** |
|  |  |  |  |
| **Total** | **£67,019** |

 |
| **Section 5: Project plan for delivery of the change** |
| Not BaselinedOverdueAt RiskOn TrackComplete |
| **Section 6: Additional information relevant to the proposed service change** |
|

|  |  |  |
| --- | --- | --- |
| **XRN Ref** | **Risk Margin** | **Description** |
| 5231 | £24,000 | There is a risk that changes are identified to the baselined business requirements that require rework and incur additional costs. Timebound to end of PIS |
| 5231 | £57,500 | There is a risk that PIS is required for 3 months to ensure coverage of the FWACV service following transition from National Grid to Xoserve which is dependent on agreement of the transition & cutover plan being agreed by Xoserve, National Grid & DNs |
| 5231 | £19,621 | MTB Costs could increase or decrease as we go through the release and more understanding of the MTB work post implementation is available - timebound from implementation to end of PIS |
|  |  |  |

**Specific Project Risks**

| **Risk Description** | **Impact** | **Mitigation** | **Owner** |
| --- | --- | --- | --- |
| There is a risk that the transition approach to be agreed between Xoserve, National Grid & DNs results in a Post Implementation Support period that will be required for 3 months | Cost increase for project resources | Agree transition & cutover approach with National Grid & DNs | Xoserve |
| There is a risk that National Grid have served notice to terminate the current FWACV service on the 01st March 2022 and the project cannot deliver the new service from the 01st April 2022 leading to a need to consider an extension by National Grid | Cost impact | Xoserve, National Grid and DNs to define cutover & transition approach with specific exit criteriaAgreement of implementation date to be a key decision point at the end of the build phase of the project | Xoserve, National Grid & DNs |
| There is a risk that XRN5382 & 5383 – Gemini Consequential Changes - Part A - PRCMS validation/processing & Part B (LDZ Stock Change and Embedded LDZ Unique Sites) have to be brought into scope of the project that impacts the overall FWACV delivery plan | Cost & Time impact | National Grid to complete business readiness impact assessment to confirm if this CP is a dependency to support the transition of the FWACV service to Xoserve | Xoserve & National Grid |

 |

**Please send completed form to:** **box.xoserve.portfoliooffice@xoserve.com**

**Document Version History**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Version** | **Status** | **Date** | **Author(s)** | **Summary of Changes** |
| 0.1 | Draft  | 24/09/2021 | Tom Lineham | Initial draft |
| 0.2 | For Review | 27/09/2021 | Tom Lineham / Lee Chambers | Revisions from draft review |
| 1 | For Review | 30/09/2021 | Lee Chambers | Version to seek approval at October 2021 Change Management Committee |

**Template Version History**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Version** | **Status** | **Date** | **Author(s)** | **Summary of Changes** |
| 2.0 | Approved | 17/07/18 | Rebecca Perkins | Template approved at ChMC on 11th July |
| 3.0 |  | 23/06/2021 | James Rigby | Table added to section 1More detailed table in section 3More detailed table in section 4Inserted a project plan example in section 5Table added in section 6 |