## Slide 1: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking at risk; Amber. Design phase continues for both XRNs scoped for this release. Build and testing completed as planned for 5143 and 5379. Return to green is completion of design, planned for 31st March. Progress update: Project Startup and Initiation phase complete Project Build phase complete Project Testing complete Initial implementation completed on 25th March On –track for implementation and go-live from 1st April NDM SP procurement continues Weekly engagement sessions with Technolog continue Decision in February ChMC: None |  | Initial implementation date of 25th March completed with a go-live of 1st April. | 
Risks and Issues | 68488 & 68489: (R) The design has not yet completed for the changes in this release, therefore the aspirational delivery timescales remain ‘at risk’ until design completion currently targeting 31st March |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) |  |  | 
Slide updated on 29th March 2023
Complete
On Track
At Risk
Overdue