## Slide 1: REC Change
9th November 2022

## Slide 2: Introduction
The following 6 slides have been included in this months ChMC pack to give you an overview of the ongoing REC Changes, we have broken these down into the following sections:
In progress – we are currently progressing through the Change journey
Under Prioritisation Review with Code Managers – due to workload/prioritisation
Electricity related Changes which we are monitoring for visibility
Further information on the Changes can be found on the REC Portal

## Slide 3: Overview of REC Changes (high level)
Chart: 
| In Progress | Current Xoserve action | On Hold | Elec Only
Change Requests | 13 | 5 | 13 | 25
Notes: In progress:
Approved awaiting implementation 33,36
Consultation 47,52,55
Solution development 16,37
Initial assessment 25
Awaiting authority decision 21
Scoping Testing requirements 67
Detailed IA 70,74
Final Assessment 30

## Slide 4: Overview of In progress REC Changes (high level)
Chart: 
| Approved awaiting implementation | Consultation | Solution development | Initial assessment | Awaiting authority decision | Scoping Testing requirements | Detailed IA | Final Assessment
Series 1 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 1
Notes: In progress:
Approved awaiting implementation 10,11,36
Consultation 47,52,55
Solution development 16,37
Initial assessment 25
Awaiting authority decision 21
Scoping Testing requirements 67
Detailed IA 70,74
New CR05_XoS

## Slide 5: REC Change Pipeline – In progress (Require CDSP Assessment/Action)
Title | Description | XRN | Status | Next Action date
R0016 | Resolution of Bilateral Erroneous Transfers | N/A | Solution development | 21/12/2022 – Review at Change panel
R0021 | Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier | N/A | Awaiting Authority Decision | 31/10/2022 – The Authority approve/reject the Change
R0025 | Service Provider Performance Charges (DCC) | N/A | Initial Assessment | 01/11/2022 - Deadline to provide comments
R0030 | Erroneous Transfer Cancellations | N/A | Final Assessment | 14/11/2022 – Review
R0033 | Micro-business Smart Meter Installation Reports | N/A | Approved - awaiting implementation | 04/11/2022 – Proposed Implementation date
R0036 | Extensive Housekeeping Amendments | N/A | Approved - awaiting implementation | 01/11/2022 – Appeal window closes
R0037 | Prepayment Credit Balance & Debt Transfer Processes | N/A | Solution development | 08/11/2022 – Change proposal plan to be updated
R0047 | Metering Code of Practice Consolidation Review | N/A | Consultation | 04/11/2022 – Awaiting results from consultation
R0052 | GES Service Definition Document | N/A | Consultation | 05/11/2022 – Consultation response due date
R0055 | Switching Operator Outage Notification Lead Time | N/A | Consultation | 28/10/2022 - Consultation response due date

## Slide 6: REC Change Pipeline – In progress (Require CDSP Assessment/Action)
Title | Description | XRN | Status | Next Action date
R0067 | Introduction of CSS refresh functionality | XRN 5567 | Scoping Test requirements | 02/11/2022 – Weekly Review Meeting
R0070 | Provision of Enduring Test Environments | N/A | Detailed IA awaiting approval | 01/11/2022 – REC Change Panel
R0074 | Release of Community View Data Items to MEMs in GES | N/A | Awaiting detailed IA | 19/11/2022 – Detailed IA triggered
Please note: This is a working document and therefore some of the dates and actions may have progressed since the slides were created

## Slide 7: REC Change Pipeline – Under Prioritisation Review
Title | Description | Status | Next Action date
R0006 | Missing Meter Technical Details | Initial Assessment | Reviewed weekly – Awaiting instruction from REC Code Manager to progress
R0049 | Intellectual Property Rights and Services Data Main Body changes | Initial Assessment | 
R0050 | Clarification of REC Maintenance of Qualification Schedule | Initial Assessment | 
R0051 | Switch Request Objections (Change of Occupier) | Initial Assessment | 
R0056 | EES/GES additional service request for Housing Ass to be added to the Matrix | Initial Assessment | 
R0059 | Maintenance of Qualification Schedule Change | Initial Assessment | 
R0061 | Resolution of invalid CSS data by Data Owners | Initial Assessment | 
R0063 | Addition of key information to all Service Now tickets | Initial Assessment | 
R0068 | REC Data Protection Changes | Initial Assessment | 
R0069 | Amendments to Sample Access Agreement | Initial Assessment | 
R0071 | DCC access to EES and GES | Initial Assessment | 
R0073 | Introduction of a Housekeeping Change Proposal Process | Initial Assessment | 
R0075 | Enabling Software Product Qualification | Initial Assessment | 

## Slide 8: REC Change Pipeline Electric only - Monitoring
Title | Description | Status
R0009 | Introduction of SDEP and EES User Maintenance API | These changes are specific for Electric only. We will continue to monitor should any of the Changes have a knock on impact to GES or the CDSP.
R0010 | New Meter Types for Auxiliary Proportional Controllers (APCs) | These changes are specific for Electric only. We will continue to monitor should any of the Changes have a knock on impact to GES.
R0011 | Reporting of Additional EMR Backing Data to Suppliers | 
R0017 | Invalid Requests for Site Technical Details | These changes are specific for Electric only. We will continue to monitor should any of the changes have a knock on impact to GES.
R0018 | Complex Sites process improvements | 
R0022 | Amendment to REC Data Access Matrix | 
R0026 | Whole current (WC)/Current Transformer (CT) certificates | 
R0027 | Minimum identification requirements in the Meter Operation Code of Practice | 
R0031 | Altering the Trigger Points for CT Commissioning | 
R0032 | New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS) | 
R0040 | CSS Switch Synchronisation to ERDA at SecuredActive | 
R0043 | Commissioning of Works by the Crowded Meter Room Coordinator (CMRC) to Resolve Issues In Crowded Meter Rooms | 
R0044 | MHHS Programme Changes required to Central Switching Service | 

## Slide 9: REC Change Pipeline Electric only - Monitoring
Title | Description | Status
R0053 | 24/7 Emergency Metering Service | These changes are specific for Electric only. We will continue to monitor should any of the changes have a knock on impact to GES or the CDSP.
R0054 | EES Access for Virtual Lead Parties | 
R0060 | ERDS Service Definition timezone correction | These changes are specific for Electric only. We will continue to monitor should any of the changes have a knock on impact to GES.
R0062 | Removal of ERDA meteringPointEnergyFlow change restriction | 
R0064 | Creating a Meter Operator Agent and MOCoP Installer | 
R0065 | Registration of Smart Export Guarantee (SEG) Sites | 
R0066 | Inclusion of SMRS Data Items In EES (BSC CP 1568 Consequential change) | 
R0072 | Introduction of a new Meter Asset Condition Code | 
R0076 | DNOs notifying Suppliers about Crossed Meters | 
R0077 | Resolution of EES API Search Address method discrepancies | 
R0078 | EMR Settlement Limited - additional access to ECOES | 
N/A | MHHS Supply Number Consultation |