## Slide 1: CSSC Programme Dashboard
Sept 2021

## Slide 2
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme remains at a Green status. Programme activities all remain on track. A CR has been raised to extend UEPT, which has a significant financial impact on Xoserve. This has been fed back as part of our response. BP22 submissions are also in progress. These will be shared as per the comms schedule. Our submission this year provides an updated view of the Maintain the Business cost as last year’s submissions were based on assumptions. Aspects such as service management and environment needs have now been clarified, however uncertainties exist around volumetrics (defects, queries, etc), which are reflected in this year’s submission | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Transition: LR Cycle 2 is continuing to plan. Preparatory activities towards Transition Testing is ongoing, with testing starting on 05/11. Internal & External Testing: All testing activities are on track. UEPT continues with no major impacts or defects. E2E Testing has commenced successfully. No defects to date. Business Change: Internal activities continue to plan including Target Operating Model set up Service Management: Xoserve’s CR-D072 which was aiming to change the Response SLAs has now been approved at Design Authority Data Migration: Planning ongoing to support Rel cycle 4b – due in Oct. |  |  |  | Live Rehearsal: Commence Cycle 2 Internal Test: Progress CR testing and any relevant regression tests DES:& Secondary APIs Continue Test support Transition: Continue Transition planning MAP C: Delivery continues to plan, build updates will be provided via Nov 21 updates. REC: REC v2 Go-live from 1st Sept. Business Change: Continue awareness and knowledge transfer sessions
Programme Update

## Slide 3: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | Overall Green: UEPT/E2E support continues. No defects raised to date for the external testing phases.
 |  | Testing | The overall status remains Green. UEPT and E2E continues well. At the point of writing this, no significant defects have been seen. Operational Testing with DCC is now complete, with no defects raised against Xoserve.
 |  | Service Management | CR-D072 has now been approved. Operational readiness activities are ongoing
 |  | Batch | The overall status is green, with testing support underway for UEPT/E2E activities
 |  | Gemini | The overall status is green
 |  | Reporting | An internal CR will be raised to incorporate the impact of one newly identified report that will need changes.
 |  | UK Link | Status continues to be Green with work underway to impact assess, deliver and test Switching Programme changes raised through the last few months

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC version 3 consultation is complete.
 |  | Data Migration | Planning ongoing to support Rel cycle 4b - due in Oct.
 |  | Environments | Workstream continues to be Green with all activities continuing to track to plan for all upcoming activities. Environment readiness for Transition is in progress.
 |  | MAP C (XRN-4780C) | Delivery continues to plan, UAT in progress, detailed delivery updates will be provided via Nov 21 updates.
 |  | SoLR (XRN-5144) | Engagement continues with Ofgem. SoLR options in discussions will be tabled at upcoming DSG sessions

## Slide 5: Re-assignment of Supplier Identity in the event of an appointment of a Supplier of Last Resort (SoLR).
September 2021

## Slide 6: Background - SoLR
In the event of a Supplier failure Ofgem will appoint a Supplier of Last Resort (SoLR) to ensure continuity of supply for consumers
  It is not a frequent event – 17 instances since November 2018
  Average number of impacted Meter Points is c73k per SoLR, but can be greater (for example, 5 SoLRs >100k in this period)
DB4 envisaged that the Market Participant Identity (MP Id) of the failed Supplier would transfer to the SoLR
This thinking would have helped shape the Non Functional Requirements for the Central Switch System (CSS) – including the defined Peak of Peak transactions in excess of a ‘normal’ day of Switch processing
  PERF140 – average daily volume of Switch Requests = 42,300
  PERF160 – “the system shall be capable of processing 250,000 Switch Requests in additional to a normal day’s volume”
We anticipate that the gas allocation is [45%] of PERF160 – [112,500 Switches]

## Slide 7: Background - SoLR
Currently, as a rule the Supplier MP Id does not transfer within the gas sector – unless where a full transfer of rights and obligations occurs (such as in a Trade Sale)
SoLRs are currently enacted by Registration activities initiated by the Shipper
As a consequence gas industry participants (specifically Shippers and DNs) can rely on notifications generated from UKLink systems if they need to identify the change in Supplier identity
UK Link systems can rely on receipt of these flows to define Supplier effective dates to determine which parties are entitled to data
Shipper identity will also need to be amended (if applicable) registration transactions in UKL (pre CSS) or via CSS (post CSS)

## Slide 8: Options Considered
A paper was produced by Xoserve to assess options, the shortlisted options were:
  MPID / Supplier Short Code Re assignment as per DB4 baseline / implement XRN5144
  Submission and processing of switch requests by the SoLR over a number of days, but below the CSS NFR daily Peak of Peaks, to give effect to the SoLR
  Retain separate process within UKL for maintaining Supplier in the event of SoLR event – retrospectively insert a break into the UKL history AND revert to original Supplier Id for SoLR
  Our view is that the preferred option is Option 2, but this needs to be confirmed with Market Participants

## Slide 9: Option 2: Submission and processing of switch requests by the SoLR over a number of days, but below the CSS NFR daily Peak of Peaks, to give effect to the SoLR
The SoLR Effective Date would be notified by Ofgem and utilised for Settlement – As Is
The change to the effective date would be enacted in systems by Switch Requests submitted by the SoLR to transfer from the failed Supplier identity
  Volumes of Switches per day would not exceed the allocated gas Peak of Peak volumes
  The registration of the SoLR may take longer than one day where the number of Meter Points subject to SoLR exceeds the Switch Request capacity of CSS / UKL / Supplier
Settlement may require a period of manual intervention – as today - until the Registrations are concluded
Switch Requests will be able to amend the Shipper identity as well as the SoLR Supplier Identity
Provided that each SoLR event can be concluded within a short period, this option should limit changes to CSS systems, central systems and Market Participant systems
  This opinion needs to be verified by Market Participants

## Slide 10: Option 1: MPID / Supplier Short Code Re assignment as per DB4 baseline / implement XRN5144
This process will reallocate the Supplier Identity, but will require changes to central systems to ensure that:
  Changes to UK Link systems to amend Organisation / Market Participant Roles and to allow effective dates to ensure that data release is only to the authorised party
  Changes to fulfil notices to market participants currently generated by Registration activity
Settlement would require a period of manual intervention – as today - until the Change of Shipper activity is undertaken (if applicable)
Shippers have sought assurances that this option would be optional – presumably reserving the right to utilise Switch Requests to enact this
This will require significant change to central systems and market participant systems (Transporters, and potentially Shippers / Suppliers, if mandated).

## Slide 11: Option 3: Retain separate process within UKL for maintaining Supplier in the event of SoLR event – retrospectively insert a break into the UKL history AND revert to original Supplier Id for SoLR
Retain the As Is process in UKL to allow retrospective update of the Supplier Identity using an existing industry file to update the MP Id in UK Link
  This will create the registration event to notify Market Participants and the break in UKL history
Allow MP Id reallocation in CSS
This would still require reallocation of the MP Id – Market Participants would still need to impact assess this
This option would create inconsistency [for a short period] between CSS and UKL
This will require detailed Impact Assessment to central systems and regression testing (as this process was expected to be decommissioned).
For the same reason, the extent of impacts to market participant systems would need to be determined.

## Slide 12: Summary
The following was assessed as the preferred option as it was anticipated that this limits impacts to Market Participants:
  Option 2 (Submission and processing of switch requests by the SoLR over a number of days, but below the CSS NFR daily Peak of Peaks, to give effect to the SoLR) was Assessment is required by the industry of this option
Is the above option supported?
Are there any specific impacts that need to be considered with respect to this option?
Next steps:
  Collate immediate feedback
  Raise CR

## Slide 13: Key Programme Risks (1/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
65426 |  | Transition & Cutover | There is a risk that the Go Live assumption day of Monday may get changed because various variables (factors) are being looked at by OFGEM leading to rework on Transition plan and related activities. | The Go-live principles have been approved at Delivery Group. Xoserve's concerns have been logged with Ofgem | Impact of non-Monday Go-live on Xoserve's Transition testing has been fed back to Ofgem. Internal contingency planning is underway | 30/09//21
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve have published design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | Continues to be monitored until E2E is complete | 30/11//21
65156 |  | Transition & Cutover | There is risk that the change freeze scope could impact Transition because the scope of Programme Change Freeze from 03/01/22 is not clearly defined leading to impacts during actual Transition | Work with the SI to collectively define the scope of Change Freeze | Internal discussions are ongoing within Ofgem to define the scope of this Change Freeze | 30/09/21

## Slide 14: Key Programme Risks (2/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | There is a potential that SoLR related implications during Transition may be considered for Transition Testing. Currently expected to be discussed in September. Dates have been aligned accordingly | 30/09/21
65122 |  | Transition and Cutover | There is risk that additional Transitional changes could change scope of Transition because more changes are identified as Transition planning continues at the Central Programme level leading to changes to the Transition plan and Xoserve planned activities. | Xoserve are actively involved in all Programme work groups to monitor and mitigate this risk. | The impact of CR-D059 on Transition is being assessed | 30/09/21
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | MDD data cleansing is with Customer Advocates to process. Additionally, further work is ongoing on REL reports | 30/12/22
65176 |  | Transition and Cutover | There is a risk that the Runbook may not be properly tested because schedules to be used across test phases (DM LR / Transition testing) are being developed seperately leading to potential for discrepancies and for insights from one activity being missed by the other | Liaise with the SI to ensure that all plans are aligned. Request early sight of plans to ensure adequate review in advance | Awaiting DM LR plans to compare against the latest issued Transition Test schedule | 01/03/22
65157 |  | Transition & Cutover | There is risk that the catch up processing could impact transition timelines because the catch up processing is not being exercised/rehearsed during Central Programme Transition Testing leading to impacts during actual Transition. | Work with the SI to assess if this activity can be tested in advance of Transition | Awaiting baseline of the Held Switches approach. | 30/09/21

## Slide 15
High Level Plan

## Slide 16: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Awaiting Decision
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Awaiting Decision
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £34,000.00 | 23/08/2021 | Pending PIA
Continuation of support for UEPT | CR-D098 | £308,000.00 | 03/08/2021 | Awaiting Decision
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | £0.00 | 17/08/2021 | Pending PIA
Elaborations for Service Management Requirements DB4 | CR-D104 | £0.00 | 17/08/2021 | Pending SI Response

## Slide 17: Switching Programme CR Position – CRs not impacting Xoserve ((Cost Implication)
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 18: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact

## Slide 19
Chart: 
| 43585 | 43616 | 43646 | 43677 | 43708 | 43738 | 43769 | 43799 | 43830 | 43861 | 43890 | 43921 | 43951 | 43982 | 44012 | 44043 | 44074 | 44104 | 44135 | 44165 | 44196 | 44227 | 44255 | 44286 | 44316 | 44347 | 44377 | 44408 | 44439 | 44469 | 44500 | 44530 | 44561 | 44592 | 44620 | 44651 | 44681 | 44712 | 44742 | 44773 | 44804 | 44834 | 44865 | 44895 | 44926 | 44957 | 44985 | 45016
Monthly FORECAST (Cumulative) | 363976.72 | 683029.7765 | 1009036.499 | 1468927.8937 | 1881004.6077 | 2628016.319 | 3342083.1863 | 4458203.008 | 5354404.1687 | 6043381.8373 | 7142886.031 | 8975402.7507 | 10111305.124 | 11388987.0723 | 13038342.6157 | 14439812.029 | 15676651.8173 | 16871244.8833 | 18128098.5297 | 18805264.193 | 19805071.6864 | 20880560.8003 | 21535840.0351 | 22900036.2051 | 23750781.4017 | 25230991.4217 | 26355252.4184 | 27541785.7851 | 28724820.5051 | 30261774.7117 | 31186897.4384 | 32459671.6651 | 33241845.5917 | 34235126.0184 | 35964197.1951 | 36768919.1917 | 37504162.2651 | 38440660.9384 | 39658135.6117 | 40350816.7251 | 41366875.1484 | 41979384.5717 | 42760004.9951 | 43552514.4184 | 43636585.5284 | 43828403.5284 | 43828403.5284 | 43828403.5284
Monthly BUDGET (Cumulative) | 489844.68 | 1174749.2 | 1918322.31 | 2859329.26 | 3600336.21 | 4373413.71 | 5301107.71 | 6054522.36 | 6844783.41 | 7587690.86 | 8469886.81 | 10016454.16 | 10772088.89 | 11466104.1 | 12171330.71 | 14216755.3 | 15951497.88 | 17098244.84 | 18223938.97 | 19242195.57 | 20253660.21 | 21199102.25 | 22074558.18 | 23123177.56 | 23750781.4017 | 25230991.4217 | 26355252.4184 | 27541785.7851 | 28724820.5051 | 30261774.7117 | 31186897.4384 | 32459671.6651 | 33241845.5917 | 34235126.0184 | 35964197.1951 | 36768919.1917 | 37504162.2651 | 38440660.9384 | 39658135.6117 | 40350816.7251 | 41366875.1484 | 41979384.5717 | 42760004.9951 | 43552514.4184 | 43636585.5284 | 43828403.5284 | 43828403.5284 | 43828403.5284
Monthly ACTUALS (Cumulative) | 228433.92 | 548079.88 | 1260281.72 | 2160027.93 | 2928145.54 | 3938750.3 | 4855898.385 | 5889989.03 | 6410840.7 | 6911519.115 | 7785494.945 | 8810593.43 | 9969351.24 | 11012414.495 | 13032728.295 | 14595347.525 | 16039780.755 | 16876714.6283 | 18171730.1383 | 18895026.3383 | 20150164.6083 | 21211022.3383 | 21965343.9083 | 23586832.8183 | 24501593.2083 | 25721442.9683 | 26751681.8983 | 27948867.9383 | 29131902.6583 | 30668856.865 | 31593979.5917 | 32866753.8183 | 33648927.745 | 34642208.1717 | 36371279.3483 | 37176001.345 | 37911244.4183 | 38847743.0917 | 40065217.765 | 40757898.8783 | 41773957.3017 | 42386466.725 | 43167087.1483 | 43959596.5717 | 44043667.6817 | 44235485.6817 | 44235485.6817 | 44235485.6817
Total Approved Budget | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000

## Slide 20
CR Name | CR Ref | Date Raised | Status
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transition stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Complete - No Xoserve Impact
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)