## Slide 1: CSSC Programme Dashboard
April 2021

## Slide 2
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme remains at a Green status. DMT non functional Cycle 2 testing is on track to complete this Thursday 1st April. Completion of this phase is a key milestone prior to the commencement of Live Rehearsal Testing. Xoserve’s internal Consequential Change test activities have completed this month. This has been an extensive and successful phase with minimal defects but has seen a comprehensive testing programme which included our Programme testing team alongside dedicated business SME’s providing assurance | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Transition: Internal and external preparatory activities continue towards DM Live Rehearsal and Transition test phases. Currently the Programme are progressing CRD-071 which proposes to de-scope In-Flights from the transitional period. SoLR; Discussions continue at Programme level and at ChMC. Internal Testing: Core testing has completed. Change requests are being progressed through internal testing in line with the Switching Programme release cycles and/or milestones. Data Migration: Progressing to plan, Xoserve do have a couple of defects we are tracking through to fix. Presently we are expecting the testing of at least one of the defects to take place during Live Rehearsal. Market Trials: The CR to remove Market Trials has progressed through the Ofgem Change Advisory Team meeting. The CR has now been presented to the Ofgem Testing Workgroups for the relevant milestones to be removed from the Programme Plan. |  |  |  | Live Rehearsal: Commenced smoke testing Internal Test: Progress CR testing and any relevant regression tests DES:& Secondary APIs Continue development and system test activities. Transition: Continue Live Rehearsal & Transition planning SoLR: Discussions continue MAP C: Detailed Design in progress Market Trials: Closure following Switching Programme approval REC: Continue REC schedule review as per Ofgem timelines
Programme Update

## Slide 3: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | Overall Amber/Green: due to ongoing resource constraints, mitigations are in place. Internal & External SIT support in progress. On track to delivery to internal testing ahead of external programme testing phases.
 |  | Testing | The overall status remains Green. Planning complete for all upcoming test phases such as UEPT, E2E, OT Smoke testing complete for UIT and OT
 |  | Service Management | Internal Service Management activities continue to feed into OT and internal OAT A CR has been raised (CR-072) and discussed at Change Advisory Workgroup (CAT) to align Switching Programme SLAs to match Xoserve’s existing response times. Our existing resolution times are more stringent than the Programme’s hence needs no change.
 |  | Batch | The overall status is green, with testing support underway.
 |  | Gemini | The overall status is green. Planning underway to undertake a connected Gas Day testing with UK Link.
 |  | Reporting | An internal CR will be raised to incorporate the impact of one newly identified report that will need changes.
 |  | UK Link | Status continues to be Green with work underway to impact assess, deliver and test Switching Programme changes raised through the last few months

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC consultation continues with Xoserve actively engaged in relevant RDUG meetings as well as reviewing REC schedules
 |  | Data Migration & Provision | DM NF Cycle 2 is due to complete this Thursday 1st April. Xoserve do have a defects to fix from this cycle, we will be progressing the fix and testing with the SI via a work off plan. Smoke testing for Live Rehearsal is complete. System data refresh activity will commence prior to Live Rehearsal.
 |  | Market Trials | The CR to remove Market Trials milestones from the Switching Programme Plan and discussed with Industry Parties via the CAT Working Group. Pending approval from Ofgem Testing Workgroup for milestone removal.
 |  | Environments | Workstream continues to be Green with all activities continuing to track to plan for all upcoming activities
 |  | MAP C (XRN-4780C) | Detailed Design has commenced and is progressing. Design is due to complete in the next two weeks. Change pack on track for release within April CP schedule.
 |  | SoLR (XRN-5144) | Industry discussion continue at the relevant Governance Workgroups

## Slide 5: Key Programme Risks (1/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
64569 |  | Data | There is a risk that the environment for DM live rehearsal will not be ready in time because of late running DM NF, and insufficient time allowed on the CSSIP for a full refresh to a new data copy (4 weeks) leading to late start to smoke test and test prep (TE700) | Clarity required from SI on what is or isn't needed for the various sub phases of live rehearsal | Requirements completed. Walkthrough with the environment team to be setup. DM NF currently running 3 days ahead of schedule | 02/04/21
64158 |  | Programme | There is a risk that that the Operational Choreography CR that is in progress may be approved because it might be deemed necessary by the central programme leading to further plan considerations (at both the central and individual PUI's plans) and cost implications to Xoserve | This has been raised with SI/DCC & Ofgem. This is being tracked collectively via the MAD log actions. Should this CR be approved, this action will be addressed with central bodies | CR-D060/61 still pending PIA review. Dates moved out further to accommodate. | 24/04/21
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Lankmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | This has been discussed with the SI and Xoserve and the view from the SI is that Gate Closure is the only processing dependency on CSS. Gate Closure timings have been tested as part of SIT NFR and no concerns have been noted Additionally, Xoserve will undertake Gas Day Testing simulating the Gate Closure from CSS, on the assumption that CSS will be meet the Gate Closure timelines following Go-live. Awaiting confirmation from SI on next steps | 30/04/21

## Slide 6: Key Programme Risks (2/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | Continues to be monitored until Tranche 1 of E2E is complete | 01/08/21
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | This CR has been raised and discussed in CAT. Ofgem will be raising this in Defsign Forum to understand SLA expectations better | 26/04/21
64898 |  | Data | There is a risk that the additional late requests for Rel and RegID loads for UIT can't be accommodated by the Correla data team because they are not planned activity, and the data is expected to be received w/c 12/04 just as prep work for Live rehearsal is underway leading to some missing data in UIT | Xoserve have specified dates by which these requests need to be issued in order to be in a position to fulfil these | Being monitored on a regular basis | 12/04/21
64425 |  | Programme | There is a risk that processing issues (such as key timings not being met) may crop on Day 1 because the end to end Day in Life of CSS processing has not been undertaken from a PUI perspective in any of the Switching Programme Test phases leading to potential industry wide processing challenges on Day 1. | This has been discussed with the SI and Xoserve and the view from the SI is that Gate Closure is the only processing dependency on CSS. Gate Closure timings have been tested as part of SIT NFR and no concerns have been noted | Awaiting confirmation of formal acceptance of this risk from the Switching Programme | 08/04/21

## Slide 7
High Level Plan

## Slide 8: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created

## Slide 9: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £25,500.00 | 25/01/2021 | Pending SI Response
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Pending SI Response
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Pending SI Response
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 |  | 19/03/2021 | Pending PIA
Uplift to the CSS Interface Specification | CR-D068 |  | 15/03/2021 | Pending PIA
REL Dissemination to iDNO and DNO | CR-D069 |  | 15/03/2021 | Pending PIA
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Pending SI Response

## Slide 10: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | £0.00 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | £0.00 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 | £0.00 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | £61,000.00 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | £0.00 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | £0.00 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | £0.00 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | £0.00 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | £0.00 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | £0.00 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | £3,500.00 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | £0.00 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | £0.00 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | £0.00 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | £0.00 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 | £0.00 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | £48,530.00 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 | £0.00 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | £0.00 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | £0.00 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | £0.00 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | £0.00 | N/A | Complete - No Xoserve Impact

## Slide 11: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
NCT-0073 Functional Script Master Changes | CR-D041 | £0.00 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | £0.00 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | £0.00 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | £0.00 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | £0.00 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 | £0.00 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | £0.00 | 30/11/2020 | Complete - No Xoserve Impact
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | £0.00 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | £0.00 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | £0.00 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | £0.00 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | £0.00 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | £0.00 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | £0.00 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | £0.00 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | £0.00 | 29/01/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | £0.00 | 05/03/2021 | Complete - No Xoserve Impact

## Slide 12
Chart: 
| 43585 | 43616 | 43646 | 43677 | 43708 | 43738 | 43769 | 43799 | 43830 | 43861 | 43890 | 43921 | 43951 | 43982 | 44012 | 44043 | 44074 | 44104 | 44135 | 44165 | 44196 | 44227 | 44255 | 44286 | 44316 | 44347 | 44377 | 44408 | 44439 | 44469 | 44500 | 44530 | 44561 | 44592 | 44620 | 44651
Monthly FORECAST (Cumulative) | 363976.72 | 683029.7765 | 1009036.499 | 1468927.8937 | 1881004.6077 | 2628016.319 | 3342083.1863 | 4458203.008 | 5354404.1687 | 6043381.8373 | 7142886.031 | 8975402.7507 | 10111305.124 | 11388987.0723 | 13038342.6157 | 14439812.029 | 15882176.8173 | 17060919.8833 | 18317773.5297 | 18994939.193 | 19994746.6864 | 21070235.8003 | 21725515.0351 | 23123666.4051 | 24439625.7451 | 26043365.7384 | 27359787.3917 | 28855704.8451 | 30101554.2984 | 30955217.3517 | 31908885.9351 | 33140941.2584 | 34032498.8417 | 34886815.4251 | 35948345.7784 | 37628862.4317
Monthly BUDGET (Cumulative) | 489844.68 | 1174749.2 | 1918322.31 | 2859329.26 | 3600336.21 | 4373413.71 | 5301107.71 | 6054522.36 | 6844783.41 | 7587690.86 | 8469886.81 | 10016454.16 | 10772088.89 | 11466104.1 | 12171330.71 | 14216755.3 | 15951497.88 | 17098244.84 | 18223938.97 | 19242195.57 | 20253660.21 | 21199102.25 | 22074558.18 | 23123177.56 | 24439625.7451 | 26043365.7384 | 27359787.3917 | 28855704.8451 | 30101554.2984 | 30955217.3517 | 31908885.9351 | 33140941.2584 | 34032498.8417 | 34886815.4251 | 35948345.7784 | 37628862.4317
Monthly ACTUALS (Cumulative) | 228433.92 | 548079.88 | 1260281.72 | 2160027.93 | 2928145.54 | 3938750.3 | 4855898.385 | 5889989.03 | 6410840.7 | 6911519.115 | 7785494.945 | 8810593.43 | 9969351.24 | 11012414.495 | 13032728.295 | 14595347.525 | 16039780.755 | 16876714.6283 | 18171730.1383 | 18895026.3383 | 20150164.6083 | 21211022.3383 | 21965343.9083 | 23363495.2783 | 24679454.6183 | 26283194.6117 | 27599616.265 | 29095533.7183 | 30341383.1717 | 31195046.225 | 32148714.8083 | 33380770.1317 | 34272327.715 | 35126644.2983 | 36188174.6517 | 37868691.305
Total Approved Budget | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000 | 34900000

## Slide 13: High Level Transitional Considerations for Shippers/Suppliers
A - REL will be made available for switching purposes via DES and the appropriate API’s (Supply Point Switching API for PCWs, TPIs and Suppliers, REL API for Gas Transporters)
B - REG IDs will be available for Suppliers to download during the Cutover weekend (Reference Programme CR-D037)
C – Shippers and Suppliers to hold switches for switches that will go live post CSS Go-live (Based on current design)
C – Relevant switching timelines & objection periods to be considered, based on min/max switching periods (as applicable) as Suppliers will need to hold any switches that will go live post CSS Go Live (and submit after). The plan for the submission of held switching is currently being worked through by the SI, DCC and Ofgem.
Shippers will need to hold settlement data for the held switches and submit to Xoserve in line with submission of held switches post Go Live
CR-D071 is proposing to remove in-flights from the Transitional period. Should this be approved, the above point related to (C) will no longer be relevant, however any sites requiring switching post Go Live will need to be held for the switch activity to be commenced within CSS post Go Live. CR-D071 is tabled for approval at Delivery Group on 27th April
A
B
C

## Slide 14: Current Status & Next Steps
We and all other Parties Under Integration (PUI’s) are working closely with the Switching Programme to finalise the Transition Runbook.
Once approved this runbook will form the basis of our internal, granular Transition plan, which will be collaboratively created with inputs and discussions at our CSSC DSG sessions.
Detailed planning of the elements highlighted in the previous slide will be undertaken in the next 2 months.
Additionally, the Programme Co-Ordinator PWC is compiling the E2E Cutover Approach and Plan (ECAP). This was introduced at Cutover Working Group on 07/04.
The ECAP is expected to call out all aspects that License parties need to be aware of and undertake during the Cutover to CSS. PWC will be setting up sessions for this purpose, Shippers and Suppliers will be invited to attend.