## Sheet1
Reference Number | Associated Mod Ref | Change Title | Status | Origination Date | Proposer | Release Type | Implementation Date | Timeline Status
XRN 3667a |  | Provision of Formula Year AQ/SOQ to Proposing Users | Implemented | 2019-01-10 | Npower | Other | 28/02/2019 | Implemented
XRN 4044 |  | Extension of ‘Must Read’ process to include Annual Read sites | Withdrawn | 2019-01-10 | National Grid | Unallocated | TBC | N/A
XRN 4273 | Mod 614 | Introducing IHD (In-Home Display) Installed Status of Failed MOD reference 614 | Implemented | 2019-01-15 | EDF Energy | Major | 01/02/2019 | Implemented
XRN 4376 |  | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | Implemented | 2019-01-10 | National Grid | Other | TBC | Implemented
XRN 4453 |  | Amendment to JOB / UPD Hierarchies to show ‘Irrelevant Datasets’ - Confirmation of File Format Changes and clarification on Version Control | Implemented | 2019-01-17 | Xoserve | Minor | 01/03/2019 | Implemented
XRN 4454 |  | National Grid and Cadent Enduring Invoicing Arrangements | Implemented | 2019-01-23 | National Grid | Major | 02/02/2019 | Implemented
XRN 4534 |  | Amendment to RGMA Validation Rules for Meter Asset Installation Date | Implemented | 2019-01-15 | Centrica | Major | 01/02/2019 | Implemented
XRN 4542 |  | Changes to the Shipper Portfolio Summary Report (new fields and removal of fields no longer applicable) | Implemented | 2019-03-21 | Gazprom | Other | 16/11/2018 | Implemented
XRN 4550 |  | Gemini Re-platform | Implemented | 2019-01-10 | National Grid | Other | 05/07/2020 | Implemented
XRN 4572 |  | Release 3 Detailed Design Delivery | Implemented | 2019-01-15 | Xoserve | Major | 01/02/2019 | Implemented
XRN 4621 |  | Suspension of the Validation between Meter Index and Uncoverted Converter Index | Implemented | 2019-01-11 | Orsted | Major | 08/11/2019 | Implemented
XRN 4626 |  | Provision of an alternative Consumer Enquiry Service (Mnumber) - PHASE TWO Non-Web Portal Implementation | Implemented | 2019-01-17 | Xoserve | Other | 01/07/2019 | Implemented
XRN 4627 |  | CSS Consequential Central Switching Services | Current | 2019-09-18 | Ofgem | Minor | TBC | In Delivery
XRN 4635 |  | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service (Number) | Implemented | 2019-01-11 | Xoserve | Other | 16/11/2018 | Implemented
XRN 4645 |  | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Implemented | 2019-01-17 | Xoserve | Other | 29/10/2020 | Implemented
XRN 4653 |  | National Grid Transmission iConversion Project | Implemented | 2019-01-11 | Xoserve | Other | 31/03/2020 | Implemented
XRN 4665 |  | Creation of new End User Categories | Implemented | 2019-01-11 | E.ON | Major | 31/08/2019 | Implemented
XRN 4670 |  | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | Implemented | 2019-01-17 | Xoserve | Major | 28/06/2019 | Implemented
XRN 4676 |  | Reconciliation issues with reads recorded between D-1 to D-5 | Implemented | 2019-01-17 | Xoserve | Major | 28/06/2019 | Implemented
XRN 4679 |  | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | Implemented | 2019-01-11 | Xoserve | Major | 08/11/2019 | Implemented
XRN 4686 |  | Smart Metering Report | Withdrawn | 2019-02-05 | CNG | Other | TBC | N/A
XRN 4687 |  | PSR updates for large domestic sites | Implemented | 2019-01-11 | E.ON | Major | 28/06/2019 | Implemented
XRN 4690 |  | Actual read following estimated transfer read calculating AQ of 1 | Implemented | 2019-01-11 | Npower | Minor | 16/02/2019 | Implemented
XRN 4691 |  | CSEPs: IGT and GT File Formats (CGI Files) | Withdrawn | 2019-01-11 | Wales & West Utilities | Major | TBC | N/A
XRN 4692 |  | CSEPs: IGT and GT File Formats (CIN Files) | Withdrawn | 2019-01-11 | Wales & West Utilities | Major | TBC | N/A
XRN 4693 |  | CSEPs: IGT and GT File Formats. Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | Withdrawn | 2019-01-11 | Wales & West Utilities | Major | TBC | N/A
XRN 4694 |  | CSEPs: IGT and GT File Formats (Create new data validations ) | Withdrawn | 2019-01-11 | Wales & West Utilities | Major | TBC | N/A
XRN 4695 |  | Investigating causes and contributors to levels and volatility of Unidentified Gas | Implemented | 2019-01-11 | Xoserve | Other | 30/03/2019 | Implemented
XRN 4706 |  | National Grid Gas – Test Support & Consultancy on Connectivity between Xoserve & Gemini | Implemented | 2019-01-14 | National Grid | Other | 31/10/2019 | Implemented
XRN 4713 |  | Actual read following estimated transfer read calculating AQ of 1 (linked to XRN4690) | Current | 2019-01-14 | Npower | Other | TBC | In Delivery
XRN 4716 |  | Increased Field Length – ‘Updated by’ data item | Withdrawn | 2019-02-15 | SGN | Minor | TBC | N/A
XRN 4717 |  | Use of up to date Forecast weather data in first NDM Nominations | Implemented | 2019-01-14 | Total Gas and Power | Minor | 16/02/2019 | Implemented
XRN 4725 |  | New Read Reason Type for LIS Estimate Readings | Implemented | 2019-01-14 | Xoserve | Major | 08/11/2019 | Implemented
XRN 4732 |  | June -19 Release Delivery | Implemented | 2019-04-24 | Xoserve | Major | 28/06/2019 | Implemented
XRN 4738 |  | Shipper Portfolio Update of Proposed Formula Year AQ/SOQ | Implemented | 2019-01-14 | Npower | Other | 31/03/2020 | Implemented
XRN 4747 |  | Smart Meter Upgrade Notification Report | Implemented | 2019-01-14 | Npower | Other | 18/01/2019 | Implemented
XRN 4752 |  | Meter Read Performance | Implemented | 2019-01-14 | Xoserve | Other | 15/03/2019 | Implemented
XRN 4753 |  | CMS - Increase Information Provided in QCL Response File | Withdrawn | 2019-01-14 | BU-UK | Major | 08/11/2019 | N/A
XRN 4770 | Mod 0654 | NDM Sample Data – Mod 0654 Delivery | Implemented | 2019-01-14 | E.ON | Minor | 22/02/2019 | Implemented
XRN 4772 |  | Composite Weather Variable (CWV) Improvements | Implemented | 2019-01-14 | E.ON | Major | 27/06/2020 | Implemented
XRN 4777 |  | Acceptance of Contact Details Updates | Implemented | 2019-01-11 | EDF Energy | Minor | 27/07/2019 | Implemented
XRN 4779 | Mod 0657S | UNC Modification 0657S - Adding AQ reporting to the PARR Schedule reporting suite | Implemented | 2019-01-11 | Npower | Other | 11/03/2020 | Implemented
XRN 4780 |  | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Current | 2019-01-11 | SSE | Major | 05/11/2021 | In Delivery
XRN 4785 |  | SSN Error proofing | Withdrawn | 2019-01-11 | National Grid | Unallocated | TBC | N/A
XRN 4786 |  | Provision of Gemini data to Ofgem | Withdrawn | 2019-01-11 | National Grid | Unallocated | TBC | N/A
XRN 4787 |  | Rescheduling of failed SSN | Withdrawn | 2019-01-11 | National Grid | Unallocated | TBC | N/A
XRN 4789 |  | Updating Shipper Reporting Packs and glossary | Implemented | 2019-01-11 | E.ON | Other | 31/07/2019 | Implemented
XRN 4790 | Mod0652 | Introduction of winter read/consumption reports and associated obligation (MOD0652) | Implemented | 2019-01-11 | Npower | Other | 12/07/2019 | Implemented
XRN 4795 | Mod520a | Amendments to the PARR (520a) reporting | Implemented | 2019-01-11 | Npower | Other | 15/11/2019 | Implemented
XRN 4800 |  | TSO Visibility of System Balance at Interconnection Points | On Hold | 2019-01-11 | National Grid | Unallocated | TBC | Initial Review
XRN 4801 |  | Additional information to be made viewable on DES | Implemented | 2019-01-11 | Npower | Major | 07/11/2020 | Implemented
XRN 4803 |  | Amend AQI validation/processing | Implemented | 2019-01-14 | Npower | Minor | 27/07/2019 | Implemented
XRN 4806 |  | Additional data at National Level to support UIG Allocation validation | Implemented | 2019-01-14 | Scottish Power | Other | 29/03/2019 | Implemented
XRN 4810 |  | Chat Bot Automated Gemini Assistant | On Hold | 2019-01-14 11:01 | National Grid | Unallocated | TBC | Initial Review
XRN 4813 |  | Migration of Xoserve Interfaces | Implemented | 2019-01-14 | National Grid | Other | 29/04/2019 | Implemented
XRN 4824 |  | National Grid Transmission Daily Gemini Report | Withdrawn | 2019-01-17 | National Grid Transmission | Unallocated | TBC | N/A
XRN 4828 |  | Nov-19 Release Delivery | Implemented | 2019-01-16 | Xoserve | Major | 08/11/2019 | Implemented
XRN 4833 |  | Roll Out of Business Intelligence and Data Discovery Capability | Implemented | 2019-01-16 | Xoserve | Other | 07/05/2019 | Implemented
XRN 4850 |  | Notification of Customer Contact Details to Transporters | Implemented | 2019-02-18 | Wales & West Utilities | Major | 27/06/2020 | Implemented
XRN 4851 |  | Moving Market Participant Ownership from SPAA to UNC/DSC | Implemented | 2019-02-14 | E.ON | Other | 28/02/2020 | Implemented
XRN 4852 |  | Amendments to the DSC Change Management Procedures – aligning the procedures to the change process | Withdrawn | 2019-02-18 | E.ON | Other | TBC | N/A
XRN 4853 |  | Interim process to monitor & manually load rejected reads into UK Link where the read was rejected for reason code MRE00458 only (UIG Recommendation 3.1 option 5) | Implemented | 2019-02-14 | Xoserve | Other | 01/04/2019 | Implemented
XRN 4854 |  | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | Withdrawn | 2019-02-14 | Cadent | Unallocated | TBC | N/A
XRN 4858 |  | Service Description Table updates February 2019 | Implemented | 2019-02-18 | Xoserve | Other | 28/02/2019 | Implemented
XRN 4860 |  | National ‘Temporary’ UIG Monitoring (1) | Withdrawn | 2019-02-14 | Npower | Unallocated | TBC | N/A
XRN 4865 |  | Amendment to Treatment and Reporting of CYCL Reads | Implemented | 2019-03-05 | Xoserve | Major | 27/06/2020 | Implemented
XRN 4866 |  | Removal of validation on uncorrected read (UIG Recommendation) | Implemented | 2019-03-06 | Xoserve | Major | 08/11/2019 | Implemented
XRN 4869 |  | DC Exit Programme | Current | 2019-03-06 | Xoserve | Unallocated | TBC | In Delivery
XRN 4871 | Mod 0665 | Modification 0665 - Changes To Ratchet Regime | Implemented | 2019-03-06 | Gazprom Energy | Major | 07/11/2020 | Implemented
XRN 4876 |  | Changes to PARR reporting – provide further data to PAFA to aid analysis of performance reporting | Current | 2019-03-05 | Gemserv | Other | TBC | In Delivery
XRN 4887 |  | Service Description Table updates March 2019 | Implemented | 2019-03-06 | Xoserve | Other | 28/02/2019 | Implemented
XRN 4888 |  | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | Implemented | 2019-03-06 | BU UK | Major | 27/06/2020 | Implemented
XRN 4894 |  | Shipperless and Unregistered Pre-Payment Supply Points Reconciliation | Withdrawn | 2019-03-14 | SGN | Unallocated | TBC | N/A
XRN 4896 |  | Failure to Supply Gas System and Template Amendment | Implemented | 2019-07-30 | Xoserve | Other | 14/08/2020 | Implemented
XRN 4897 |  | Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event | Implemented | 2019-10-14 | Xoserve | Major | 07/11/2020 | Implemented
XRN 4899 |  | Treatment of Priority Service Register Data and Contact Details on a Change of Supplier Event | Implemented | 2019-10-14 | Xoserve | Major | 07/11/2020 | Implemented
XRN 4914 | MOD 0651 | MOD 0651- Retrospective Data Update Provisions | Current | 2019-04-04 | Cadent | Major | TBC | Awaiting Delivery
XRN 4920 |  | Review of the CSSC (Central Switching Service Consequential Changes) Gemini Business Requirements Document | Current | 2019-04-17 | Xoserve | Other | TBC | In Delivery
XRN 4921 |  | Review of the CSSC (Central Switching Service Consequential Changes) GT and IGT Business Requirements Document | Current | 2019-04-17 | Xoserve | Other | TBC | In Delivery
XRN 4922 |  | Review of the CSSC (Central Switching Service Consequential Changes) Shipper Business Requirements Document | Current | 2019-04-17 | Xoserve | Other | TBC | In Delivery
XRN 4923 |  | AQ Calculation for RGMA (ONUPD) Estimate Reads | Withdrawn | 2019-07-30 | Xoserve | Unallocated | TBC | N/A
XRN 4930 |  | Requirement to inform Shipper of Meter Link Code Change | Implemented | 2019-04-30 | Xoserve | Major | 27/06/2020 | Implemented
XRN 4931 |  | Submission of a Space in Mandatory Data on Multiple SPA Files | Current | 2020-04-30 | Xoserve | Unallocated | TBC | Awaiting Delivery
XRN 4932 | MOD0681S | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | Implemented | 2019-04-23 | E.ON | Major | 27/06/2020 | Implemented
XRN 4941 | MOD0692 | Auto updates to meter read frequency (MOD0692) | Current | 2019-05-17 | Total Gas & Power | Major | 05/11/2021 | In Delivery
XRN 4946 |  | Reporting on Installed Meters with Conversion Capability | Withdrawn | 2019-05-30 | SSE | Unallocated | TBC | N/A
XRN 4954 |  | Minor Release Drop 5 | Implemented | 2019-06-05 | Xoserve | Minor | 07/09/2019 | Implemented
XRN 4955 |  | Amendment of MDD PSR Needs Codes and Needs Code Descriptions | Implemented | 2019-05-30 | Wales & West Utilities | Minor | 29/02/2020 | Implemented
XRN 4977 |  | Amendments to DSC Change Management Guidelines | Implemented | 2019-07-04 | Xoserve | Other | 07/08/2019 | Implemented
XRN 4978 |  | Notification of Rolling AQ value (following transfer of ownership between M-5 and M) | Current | 2019-07-08 | British Gas | Unallocated | TBC | Capture
XRN 4980 |  | Change Supply Point Enquiry API to add in extra field and make certain other fields visible | Implemented | 2019-07-12 | Total Gas & Power | Other | 12/12/2020 | Implemented
XRN 4989 |  | Online end to End Credit Interest process - Defect 1063 | Implemented | 2020-06-02 | CDSP | Minor | 20/11/2020 | Implemented
XRN 4990 | MOD0664 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (MOD0664) | Current | 2019-08-01 | SSE | Unallocated | TBC | Capture
XRN 4991 | MOD0700 | Enabling large scale utilisation of Class 3 – MOD0700 | Implemented | 2019-08-01 | Gazprom | Other | 28/09/2019 | Implemented
XRN 4992 | Mod 0687 | Modification 0687 - Creation of new charge to recover Last Resort Supply Payments | Current | 2019-08-01 | Total Gas and Power | Unallocated | TBC | Awaiting Delivery
XRN 4993 |  | DSC Service Description Table cosmetic change to service line table as of April 2019 | Implemented | 2019-08-01 | Xoserve | Unallocated | 28/02/2019 | Implemented
XRN 4994 |  | PAFA Contract Extension 2019/20 | Withdrawn | 2019-08-02 | Xoserve | Unallocated | TBC | N/A
XRN 4995 |  | Procurement of a Laboratory Study of within-pipe gas temperatures | On Hold | 2019-08-02 | Xoserve | Other | TBC | Awaiting Delivery
XRN 4996 |  | June 2020 Release Delivery | Implemented | 2019-08-12 | N/A - Parent XRN | Major | 27/06/2020 | Implemented
XRN 4997 |  | Introducing new charge codes for GSoP3, GSoP13 and GT Voluntary Consumer Payments | Implemented | 2019-09-12 | Northern Gas Networks | Minor | 29/02/2020 | Implemented
XRN 5003 |  | Data Access Platform DN Dashboard | Implemented | 2019-09-03 | Northern Gas Networks | Other | 25/10/2019 | Implemented
XRN 5004 |  | Golden Bullet Report | Current | 2019-09-03 | Wales & West Utilities | Other | TBC | In Delivery
XRN 5007 |  | Correction in the reconciliation process when volume is zero | Current | 2020-06-29 | Xoserve | Major | 05/11/2021 | In Delivery
XRN 5013 |  | Performance Assurance Framework Administrator Access to Data Discovery Platform | Implemented | 2019-10-14 | SSE | Other | 31/01/2020 | Implemented
XRN 5014 |  | Facilitating HyDeploy2 Live Pilot | Implemented | 2020-01-02 | Northern Gas Network | Major | 07/11/2020 | Implemented
XRN 5027 | MOD0681S | UK Link Data Cleanse of Conversion Factor in line with MOD0681S | Withdrawn | 2019-10-01 | E.ON | Other | TBC | N/A
XRN 5029 |  | Service Description Table updates October 2019 | Implemented | 2019-10-01 | Xoserve | Other | 24/10/2019 | Implemented
XRN 5033 |  | Addition of low-level data to EUC Report | Implemented | 2019-11-06 | British Gas | Other | 16/12/2019 | Implemented
XRN 5036 |  | Updates to must read process | Implemented | 2019-11-06 | Cadent Gas | Minor | 04/07/2020 | Implemented
XRN 5038 | MOD 0691 | Convert Class 2, 3 or 4 meter points to Class 1 when G1.6.15 criteria are met (MOD 0691) | Implemented | 2019-11-06 | British Gas | Other | 01/04/2021 | Implemented
XRN 5048 |  | Make an indicator available where a Supply Meter Point form part of a Network Trial | Withdrawn | 2020-01-02 | Northern Gas Network | Unallocated | TBC | N/A
XRN 5053 |  | Single Sided Nominations Improvements | Implemented | 2019-12-04 | National Grid | Other | 05/04/2020 | Implemented
XRN 5054 |  | Negative Implied Flow Rates | Implemented | 2019-12-04 | National Grid | Other | 05/04/2020 | Implemented
XRN 5057 |  | Minor Release Drop 6 (Parent) | Implemented | 2019-12-18 | CDSP | Minor | 29/02/2020 | Implemented
XRN 5064 |  | Meter Asset Enquiry API Enhancements | Implemented | 2019-12-18 | CDSP | Other | 28/03/2020 | Implemented
XRN 5065 |  | Addition of Email Address to DES Last Accessed Report | Implemented | 2019-12-18 | Scottish Power | Minor | 04/07/2020 | Implemented
XRN 5070 |  | Amendment to Isolation Flag | Withdrawn | 2020-01-02 | E.ON | Other | TBC | N/A
XRN 5072 |  | Application and derivation of TTZ indicator and calculation of volume and energy – all classes | Current | 2020-01-02 | Xoserve | Major | 05/11/2021 | In Delivery
XRN 5080 |  | Failure to Supply Gas (FSG/GSOP1) – System Changes | Implemented | 2020-01-30 | Scotland and Southern Gas Networks SGN | Minor | 20/03/2021 | Implemented
XRN 5091 |  | Deferral of creation of Class change reads at transfer of ownership | Current | 2020-01-31 | EDF | Major | TBC | Awaiting Delivery
XRN 5092 |  | iConversion Phase 2 | Implemented | 2020-01-31 | National Grid - Gas | Other | 22/08/2020 | Implemented
XRN 5093 |  | Update of AUG Table to reflect new EUC bands | Current | 2020-01-31 | Gazprom | Major | 25/06/2021 | In Delivery
XRN 5097 |  | DSC Service Description Table cosmetic change to service line table v9 | Implemented | 2020-02-03 | CDSP - Xoserve | Other | 28/02/2020 | Implemented
XRN 5110 |  | November 20 Release Delivery | Implemented | 2020-02-27 | Xoserve | Major | 07/11/2020 | Implemented
XRN 5116 |  | Domestic Report - Must Read Prenotification | Withdrawn | 2020-02-28 | British Gas | Unallocated | TBC | N/A
XRN 5118 |  | Change to how ‘Actual MR date’ field is populated in UK Link | Implemented | 2020-09-02 | CDSP | Minor | 21/11/2020 | Implemented
XRN 5120 |  | MAP to UKL Monthly Comparison Service | Current | 2020-02-27 | E.ON | Other | TBC | In Delivery
XRN 5121 |  | Supplier Portfolio Service | Withdrawn | 2020-02-28 | CDSP | Unallocated | TBC | N/A
XRN 5122 |  | Gemini System Enhancements - Delivery | Current | 2020-03-02 | National Grid | Other | 27/07/2021 | In Delivery
XRN 5123 |  | DSC Service Description Table cosmetic change to Service Line Table | Implemented | 2020-03-02 | Xoserve | Other | 23/03/2020 | Implemented
XRN 5135 |  | DNO and NTS Invoices to Shippers and DNs VAT compliance | Implemented | 2020-07-23 | Wales & West Utilities | Minor | 20/03/2021 | Implemented
XRN 5142 |  | New Allowable Values for DCC Service Flag in DXI File From DCC | Current | 2020-03-27 | Northern Gas Networks | Major | 05/11/2021 | In Delivery
XRN 5143 |  | Discharge of Cadent, WWU and NGN NDM sampling obligations by the CDSP | Current | 2020-03-27 | Cadent Gas | Unallocated | TBC | Capture
XRN 5144 |  | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Current | 2020-03-31 | CDSP | Unallocated | TBC | Capture
XRN 5145 |  | DSC Service Description Table cosmetic change to Service Line Table v11 | Implemented | 2020-03-30 | CDSP - Xoserve | Other | 14/10/2020 | Implemented
XRN 5146 |  | Data Cleanse of NExA information within UK Link and the Data Enquiry Service (DES) | Implemented | 2020-03-31 | Northern Gas | Other | 15/02/2021 | Implemented
XRN 5147 |  | Optimising the Must Read process for IGT Customers | Withdrawn | 2020-03-31 | BUUK | Other | TBC | N/A
XRN 5152 |  | Minor Release Drop 7 | Implemented | 2020-09-03 | CDSP | Minor | 04/07/2020 | Implemented
XRN 5153 |  | iConversion Phase 2 | Implemented | 2020-07-15 | Xoserve | Other | 07/08/2020 | Implemented
XRN 5156 |  | REC121 Report Amendment | Implemented | 2020-04-29 | NGN - Northern Gas Networks | Other | 24/04/2020 | Implemented
XRN 5161 |  | UIG_Additional_National_Data_YYYYMM Frequency Change | Implemented | 2020-04-29 | Inspired Energy | Other | 22/05/2020 | Implemented
XRN 5164 |  | CSEP Data Assurance Performance Monitoring Capability | Implemented | 2020-05-05 | Wales & West Utilities | Other | 09/10/2020 | Implemented
XRN 5167 | MOD 672 | Report Product Class 4 Read Performance (MOD 672) | Implemented | 2020-05-04 | Scottish Power | Other | 28/08/2020 | Implemented
XRN 5168 | MOD0721 | MOD0721 (Urgent) - Shipper submitted AQ Corrections during COVID-19 | Withdrawn | 2020-05-05 | Gaz Prom | Other | TBC | N/A
XRN 5169 | MOD0722 | UNMOD0722 (Urgent): Allow Users to submit Estimated Meter Reading during COVID-19 | Implemented | 2020-05-05 | Gaz Prom | Other | 2020-05-12 | Implemented
XRN 5170 | MOD0723 | MOD0723 (Urgent): Use of the Isolation Flag to identify sites with abnormal load reduction during COVID-19 period | Implemented | 2020-05-05 | Northern Gas Networks | Other | 2020-05-12 | Implemented
XRN 5171 | MOD0724 | MOD0724 (Urgent): Amendment to Ratchet charges during COVID-19 period | Implemented | 2020-05-05 | Northern Gas Networks | Other | 2020-05-12 | Implemented
XRN 5172 |  | Urgent Mod - Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19 | Withdrawn | 2020-05-11 | Gazprom | Unallocated | TBC | N/A
XRN 5174 |  | Agreed FINT Replacement Reads Incorrectly Triggering Rolling AQ Calculation | Implemented | 2020-09-02 | CDSP | Minor | 21/11/2020 | Implemented
XRN 5180 |  | Inner Tolerance Validation for replacement reads and read insertions | Current | 2020-07-28 | CDSP | Major | 05/11/2021 | In Delivery
XRN 5181 |  | Acceptance of Consumption Adjustment where meter removed after meter point set to Dead | Implemented | 2020-08-11 | CDSP | Minor | 21/11/2020 | Implemented
XRN 5183 |  | Access to Daily Biomethane Injections | Current | 2020-08-19 | Inspired Energy PLC | Minor | TBC | In Delivery
XRN 5186 | Mod 0701 | Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | Current | 2020-06-01 | NGN | Unallocated | TBC | Capture
XRN 5187 | Mod 0696 | Modification 0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Current | 2020-06-01 | Gazprom | Major | TBC | Capture
XRN 5188 |  | Interim Data Loads of MAP Id into UK Link | Current | 2020-06-04 | CDSP | Minor | TBC | In Delivery
XRN 5192 |  | CMS Reference Number in Amendment Invoice Supporting Data | Withdrawn | 2020-06-29 | N Power | Unallocated | TBC | N/A
XRN 5193 |  | Stop MUR Generation of GT SMPs | Withdrawn | 2020-06-29 | Xoserve | Unallocated | TBC | N/A
XRN 5195 |  | Ceased Responsibility Date Following Shipper Withdrawal (IDL) | Withdrawn | 2020-06-29 | Indigo Pipelines | Unallocated | TBC | N/A
XRN 5196 |  | Address Amendments Validation | Withdrawn | 2020-06-29 | BU-UK | Unallocated | TBC | N/A
XRN 5197 |  | QMP File Validation in CMS – Current Address field | Withdrawn | 2020-06-29 | Indigo Pipelines | Unallocated | TBC | N/A
XRN 5199 |  | Amendments to V12 of the SDT Service Description Table | Implemented | 2020-06-29 | Xoserve | Other | 31/07/2020 | Implemented
XRN 5200 |  | Shipper Pack Transition to Data Discovery Platform | Current | 2020-07-01 | E.ON | Other | TBC | Awaiting Delivery
XRN 5203 |  | Perspective Supply Metering Point AQ and EUC | Withdrawn | 2020-10-06 | Gazprom Energy | Unallocated | TBC | N/A
XRN 5206 |  | TPI/PCW Access | Implemented | 2020-07-08 | ENGIE | Other | 15/01/2021 | Implemented
XRN 5209 |  | Amendments to the CDSP Service Document - Budget & Charging Methodology v4 | Implemented | 2020-07-16 | Xoserve | Other | 01/04/2021 | Implemented
XRN 5210 |  | Daily CV Determination Interim Service: DN Invoicing Options | Withdrawn | 2020-09-09 | National Grid Gas | Minor | TBC | N/A
XRN 5218 |  | CDSP provision of Class 1 read service | Current | 2020-08-03 | Wales and West Utilities | Other | TBC | Capture
XRN 5225 |  | Minor Release Drop 8 | Implemented | 2020-08-27 | CDSP | Minor | 21/11/2020 | Implemented
XRN 5231 |  | Provision of a FWACV Service | Current | 2020-08-28 | SGN | Unallocated | TBC | Capture
XRN 5235 |  | Include SOQ in the “UIG Additional National Data” report (Originally introduced by XRN 4806) | Current | 2020-09-25 | Gazprom Energy | Unallocated | TBC | Capture
XRN 5236 | Mod 0734 | Reporting Valid Confirmed Theft of Gas into Central Systems (Modification 0734) | Current | 2020-09-25 | Gazprom Energy | Unallocated | TBC | Capture
XRN 5237 | Mod 0736 | Maintenance of a User relationship table for the purpose of AQ amendments (Modification 0736) | Implemented | 2020-09-24 | CDSP | Other | 14/01/2021 | Implemented
XRN 5238 |  | New Distribution Network Report – Forecast Invoice Values | On Hold | 2020-09-25 | Northern Gas Networks | Unallocated | TBC | Capture
XRN 5244 |  | Shared IGT Deeds of Undertaking and CDSP Administration | Current | 2020-09-25 | BUUK | Unallocated | TBC | Capture
XRN 5246 |  | Confirmation File (.CNF) Processing Capacity Improvement | Current | 2020-09-25 | CDSP | Unallocated | TBC | Capture
XRN 5251 |  | Gemini Exit Zone Change | Current | 2020-10-29 | National Grid | Unallocated | TBC | In Delivery
XRN 5252 | MOD 0740 | Amending the Formula Year AQ approach for 2021/2 Formula Year (Urgent MOD 0740) | Withdrawn | 2020-10-12 | EON | Other | TBC | N/A
XRN 5253 |  | June 21 Release | Current | 2020-10-29 | CDSP | Major | 25/06/2021 | In Delivery
XRN 5273 |  | Amendments to V14 of the Service Description Table | Implemented | 2020-10-30 | Xoserve | Other | 18/11/2020 | Implemented
XRN 5285 | Mod 0730V | COVID-19 Capacity Retention Process (Mod 0730V) | Withdrawn | 2020-11-30 | CDSP | Other | TBC | N/A
XRN 5286 | Mod 0746 | Clarificatory change to the AQ amendment process to be applied retrospectively (Modification 0746) | Current | 2020-11-30 | CDSP | Other | TBC | Capture
XRN 5289 |  | November 21 Major Release | Current | 2020-12-31 | Xoserve | Major | 05/11/2021 | In Delivery
XRN 5290 |  | CNC Bulk Network Report | Current | 2020-12-31 | Xoserve | Other | TBC | Capture
XRN 5294 |  | Minor Release Drop 9 | Implemented | 2020-12-22 | CDSP | Minor | 20/03/2021 | Implemented
XRN 5298 |  | H100 Fife Project - Phase 1 (Initial Assessment) | Current | 2021-01-18 | SGN | Unallocated | TBC | Capture
XRN 5299 |  | Future Billing Methodology (analysis only) | Current | 2021-01-21 | Cadent | Unallocated | TBC | Capture
XRN 5307 |  | Amendments to V15 of the Service Description Table | Implemented | 2021-01-05 | CDSP | Other | 20/01/2021 | Implemented
XRN 5309 |  | FSG - Automating the FSR ‘Standard Liability’ process | Current | 2021-01-21 | SGN | Minor | TBC | In Delivery
XRN 5318 |  | Assessing Supplier MPID Reassignment | Current | 2021-02-01 | E.ON | Unallocated | TBC | Capture
XRN 5319 |  | Assessing MPID Reassignment for All Party Types | Current | 2021-02-01 | E.ON | Unallocated | TBC | Capture
XRN 5321 |  | PAC Ring-Fenced DSC Change Budget 21/22 | Current | 2021-02-25 | CDSP | Unallocated | TBC | Capture
XRN 5327 |  | Xoserve Change Fund 2021/22 | Current | 2021-02-25 | CDSP | Unallocated | TBC | Initial Review
XRN 5329 |  | Amendments to V16 of the Service Description Table | Implemented | 2021-02-25 | CDSP | Other | 17/03/2021 | Implemented
XRN 5341 |  | UNC745 - Mandatory Setting of Auction Bid Parameters | Current | 2021-04-29 | National Grid | Unallocated | TBC | In Delivery
XRN 5343 |  | CMS Rebuild | Current | 2021-03-29 | Xoserve | Other | TBC | Capture
XRN 5345 |  | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at transfer of ownership | Current | 2021-03-29 | Xoserve | Unallocated | TBC | Capture
XRN 5352 |  | Development of the REC Performance Assurance reporting structure | Current | 2021-04-29 | RECCo | Unallocated | TBC | Capture
XRN 5362 |  | Amendments to Service Description Table V17 | Implemented | 2021-04-29 | CDSP | Unallocated | TBC | Implemented
XRN 5365 |  | Request impact assessment on aligning Major Releases to the REC Release Schedule (Thursday release and 3 Major Releases per year) | Current | 2021-05-19 | Xoserve | Other | TBC | Initial Review