## Slide 1: Change Management Committee
April 2023

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: General Change Budget BP22 YTD

## Slide 4: Forecasted Year End Spend (BP22)
The graph below illustrates the current forecast for financial year-end utilisation of the General Change investment budget (BP22) – this is subject to change should ChMC approve further change delivery
Total committed spend – no change from last month
Link to ChMC Change Budget spreadsheet
Chart: Committed to date per constituency
| Shipper | DN | IGT | NTS
Committed | 1923223.5 | 614613.5 | 13821 | 0
Uncommitted | 43938 | 569954 | 171347.5 | 69102.5

## Slide 5: Change Pipeline

## Slide 6: Change Delivery Plan January 23 – April 24
February 23 - Major Release (XRN5533)
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992b, XRN5298
Jan-23
Aug-23
June 23 - Major Release (XRN5562)
XRN5091
Apr-23
Dec-23
Apr-24
November 23 – Major Release
XRN5186, XRN5482
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and/or Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 30th March 2023
March 23 - AdHoc Release (XRN5575)
XRN5379, XRN5143
XRN5595
XRN5555
February 24 – Major Release
XRN5607, XRN5573B
XRN5535A
XRN5567
XRN5602
XRN5606
XRN5454
XRN5547
XRN5605
XRN5604

## Slide 7: Change Pipeline - Delivery Plan - January 2023 – May 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | N/A | 31st January 2023 | Adhoc | Delivered
4900 | Biomethane/Propane Reduction | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Delivered
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Delivered
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Delivered
4989 | Residual AMT activities | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Delivered
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DN | Shipper DNO | £108.7k | 25th February 23 | Major | Delivered
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Delivered
5595 | Changes to the REC Switching Operator Outage Notification Lead Time (R0055) | Xoserve | Shipper | N/A | N/A | 25th Feb 23 | Major | Delivered
5535A | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | All DSC Customers | Shipper | £44k | 10th March 23 | Adhoc | Firm
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | April 2023 | Adhoc | Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | 1st April 2023 | AdHoc | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | £75k | 1st April 2023 | AdHoc | Firm
5606 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0813) | NGT | NGT Shipper Supplier | NGT | N/A | Immediately Following Ofgem Decision | Adhoc | Indicative
5602 | Releasing of unused capacity under a specific set of circumstances (Modification 0818) | NGN | Shipper DN | DN | N/A | Immediately Following Ofgem Decision | Adhoc | Indicative

## Slide 8: Change Delivery Plan - June 2023 – February 2024
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | 24th June 23 | Major | Firm
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | July 23 | Minor | Indicative
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | Tbc | July 23 | Minor | Indicative
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper DN | £300k | November 23 | Major | Indicative
5186 | *MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | November 23 | Major | Indicative
5604 | Shipper Agreed Read (SAR) exceptions process (Modification 0811S) | SEFE | Shipper | Shipper | Tbc | November 23 | CMS Rebuild | Indicative
5605 | Amendments to the must read process (IGT159V) | Centrica | Shipper IGT | Shipper IGT | Tbc | November 23 | CMS Rebuild | Indicative
5567 | Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067) | Xoserve | All DSC Customers | Shipper | £93k | Awaiting REC Decision – expected December 23 | Adhoc | Indicative
5607 | Update to the AQ correction processes (Modification 0816S) | EON Next | Shipper DN IGT | Shipper | Tbc | *February 23 | Major | Indicative
5573B | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) | Xoserve | Shipper DN IGT | Tbc | Tbc | February 23 | Major | Indicative
*XRN5607 (Mod0816S) – Proposed Implementation in Feb-23 Release aligns with ROM response provided to Workgroup

## Slide 9
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | Tbc | Tbc | N/A
5531 | Hydrogen Village Trial | SGN | All DSC Customers | DN Decarb | Tbc | Tbc | Tbc | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Tbc | Tbc | Tbc | N/A
5585 | Flow Weighted Average Calorific Value - Phase 2 Service Improvements | Cadent | DN | DN | Tbc | Tbc | Tbc | N/A
5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | BUUK | Shipper IGT | Shipper IGT | Tbc | Tbc | Tbc | N/A
5615 | Establishing/Amending a Gas Vacant Site Process (Modification 0819) | Centrica | Shipper DN IGT | Shipper DN | Tbc | Tbc | Tbc | Tbc
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | Tbc | Tbc | Tbc | N/A
Change Backlog Details

## Slide 10: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | *Mod0651 – Retrospective Data Update Provisions* | Cadent | Shipper DN | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
*Mod0651 : 30.03.23 - Change Status remains on hold and will be reviewed on a monthly basis with ChMC – in line with request from UNCC

## Slide 11: DSC Change Pack Consultation Plan (2 month view)
April-23
May-23
June-23
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
Delivery Key
Slide produced 30th March 2023
XRN5454 – SOLR Reporting Suite
XRN5482 - Replacement of reads associated to a meter asset technical details change or update (RGMA)
XRN5605 - Amendments to the must read process (IGT159V)
XRN5604 - Shipper Agreed Read (SAR) exceptions process (Modification 0811S)
XRN5607 – Mod0816 – Updates to the AQ Correction Process
UK Link Manual - GT Rejection Codes Cosmetic Update
XRN5531 – Hydrogen Village Trial
XRN5556E – CMS Rebuild Version 1.4 - ADD/UNC Contacts
XRN5556F – CMS Rebuild Version 1.5 - RFA/CDQ Contacts

## Slide 12: REC Change
12th April 2023

## Slide 13: Introduction
The following 8 slides have been included in this months ChMC pack to give you an overview of the ongoing REC Changes, we have broken these down into the following sections:
In progress – we are currently progressing through the Change journey
Under Prioritisation Review by REC Code Managers – due to CM workload/prioritisation
Expected incoming Impact Assessments
Note: We are currently undertaking a review of all REC Change and have began removing Changes which we have confirmed have no impact to Gas services. In the coming months, we will continue to monitor the Changes listed and add/remove from this pack as required.
Further information on the Changes can be found on the REC Portal

## Slide 14: Overview of In Progress REC Changes (high level)
Chart: 
| Approved awaiting implementation | Solution development | Party Impact Assessment
In Progress | 5 | 2 | 3
Chart: All Change
| Monitoring | Currently working on | Upcoming activity | XRN Changes
All Change | 2 | 5 | 3 | 2
In Progress Change
5

## Slide 15: REC Change Pipeline – In progress
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0025 | Service Provider Performance Charges (DCC) | N/A | Deloitte (RPA) | - | Approved - awaiting implementation | 01/04/2023 – Proposed Implementation date | Standalone | High | 
This Change was raised to introduce Service Provider Performance Charges linked to performance against service levels defined in the REC. We are monitoring this change as it references future performance charges on other service providers – including the GRDS. |  |  |  |  |  |  |  |  | 
R0047 | Metering Code of Practice Consolidation Review | N/A | RECCo | - | Approved - awaiting implementation | 01/04/2023 – Proposed Implementation date | Standalone | High | N/A
This Change was raised to to consolidate the current Metering Codes of Practice into a single set of arrangements. Although we are not a directly impacted party, if and when this takes place, we may need to adapt our interactions with MEMs, DNOs and Suppliers. |  |  |  |  |  |  |  |  | 
R0063 | Addition of key information to all Service Now tickets | N/A | St Clements Ltd (on behalf of DNOs) | - | Party Impact assessment | 04/04/2023 – Extended plan presented to Change panel | TBC | Medium | N/A
This Change was raised to improve the information that’s included on DCC’s Service Now Tickets which have been asynchronously rejected. We interact with DCC via SNow so we need to monitor and input into development. |  |  |  |  |  |  |  |  | 
Please note that we have provided our view of the Change summary and impacts however we recommend that DSC Customers monitor the REC Portal to form their own opinion regarding the impact to their organisation
Currently working on
Key:
Upcoming
Monitoring

## Slide 16
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0067 | Introduction of CSS refresh functionality | XRN 5567 / UNC Mod expected | Capgemini (RTS) | GRDS | Party Impact Assessment | Scope agreed, Impact assessment response submitted | Legal text – Major, June 23 Technical Change - Standalone | High | 
This Change will introduce a resend and refresh functionality to help with the message interactions between the CSS and Switching Data Service Providers. Currently, there are cases were messages are being received after Gate Closure or not being received at all. We are one of the impacted Service Providers which means this Change is very important to us so that we are able to complete customer switches successfully. |  |  |  |  |  |  |  |  | 
R0073 | Introduction of a Housekeeping Change Proposal Process | N/A | Gemserv | - | Approved – awaiting implementation | 01/04/2023 – Proposed implementation date | Standalone | Low | N/A
This Change was introduced to create a process which allows parties to amend typographical errors, formatting, and consistency errors (such as Paragraph numbering), out-of-date references to documents and updating addresses (including email) in the Retail Energy Code. Although it is a housekeeping Change, there are also amendments to legal text that we need to be involved in. Its important we monitor the outputs of this Change to capture any amendments that might be needed to our internal documents as a result, or if it creates inadvertent Change. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring

## Slide 17
Currently working on
Key:
Upcoming
Monitoring
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0074 | Release of Community View Data Items to MEMs in GES | N/A | Xoserve | GES | Approved – awaiting implementation | 27/03/2023 – Change moved to in delivery | Changes to the DAM – Major, Feb 23 Functional Change – major, June 23 | High | 
R0088 | Make Shipper NExA values available on the GES portal | XRN 5186 MOD 0701 | Xoserve | - | Party Impact Assessment | 25/04/2023 – Impact assessment response date | Major, November 23 | Medium | 
XRN 5186 - Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs makes additional information available to GES Users which require reflection in the REC. Although all of the technical change has already been developed. |  |  |  |  |  |  |  |  | 
R0091 | Clarifications to the Theft Detection Incentive Scheme | XRN 5236 MOD 0734 | Deloitte (RPA) | - | Approved – awaiting implementation | 01/04/2023 – Proposed implementation date | Standalone | Low | N/A
Following implementation of UNC Mod 0734 the RECCo are responsible for providing details of Confirmed Theft to the CDSP. We expect this to be the REC change that implements this obligation. |  |  |  |  |  |  |  |  | 

## Slide 18
Title | Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority | Attachments
R0048 | DCC Service Organisation Control 2 (SOC2) Assessments | N/A | DCC | - | Solution development | 10/03/2023 -Preliminary Change Report and consultation closeout | TBC | Low | 
Currently, the CSS Provider is obligated to undertake system organisation control type 2 (SOC2) assessments on the CSS’s cloud-based infrastructure. This Change was raised to assess if the SOC2 assessment provides a proportionate level of assurance or the best value for money and if it should be change to ‘independently assessed’. We are monitoring to determine whether there are impacts to GRDS / GES. |  |  |  |  |  |  |  |  | 
R0070 | Provision of Enduring Test Environments | N/A | Capgemini | GRDS, GES | Solution Development | 04/2023 – Awaiting Impact Assessment from Code Managers | Standalone | High | N/A
This Change was raised to introduce an obligation under the Retail Energy Code for the CSS or the Switching Operator (SO) to provide enduring test environments for REC parties to make the necessary system changes for REC Change Proposals (CPs) or internal system updates. We need to monitor this to ensure that the obligations on GRDS are understood, and that we contribute to the development of this Change. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
REC IA Demand

## Slide 19
REC Related XRN Changes
Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority
Processing of CSS Switch Requests Received in ‘Time Period 5 | XRN 5535A | Xoserve | GRDS | Implemented | 06/03/2023 – Registrations started, Change implemented | Standalone | High
Resolution of Address Interactions between DCC and CDSP | XRN 5546 | Xoserve | GRDS | Under development | 04/03/2023 – Next steps meeting arranged between Xoserve and Correla | TBC | Medium
Currently working on
Key:
Upcoming
Monitoring

## Slide 20: (Gas) REC Change Pipeline - Under Prioritisation Review
Title | Description | Status
R0049 | Intellectual Property Rights and Services Data Main Body changes | Initial Assessment
R0051 | Switch Request Objections (Change of Occupier) | Initial Assessment
R0056 | EES/GES additional service request for Housing Associations to be added to the Matrix | Initial Assessment
R0059 | Maintenance of Qualification Schedule Change | Initial Assessment
R0068 | REC Data Protection Changes | Initial Assessment
R0069 | Amendments to Sample Access Agreement | Initial Assessment
R0071 | DCC access to EES and GES | Initial Assessment
R0075 | Enabling Software Product Qualification | Initial Assessment
R0080 | Improvements to "Failed to deliver" CSS messages | Initial Assessment
R0081 | CSS Market message retry strategy | Initial Assessment
R0082 | Formalising the Submission of PPMIP Unallocated Transaction Report (UTR) Files | Initial Assessment
R0084 | Housekeeping changes to the approved legal text for R0047 | Initial Assessment
R0085 | Switching Programme Designation of the Steady State Commencement Date | Initial Assessment
R0087 | MAP GES data access | Initial Assessment

## Slide 21: (Gas) REC Change Pipeline - Under Prioritisation Review
Title | Description | Status
R0089 | Removal of Pre-COVID AQ Value from Data Access Matrix | Initial Assessment
R0092 | DCC Service Level Agreements for the Switching Incentive Regime | Initial Assessment
R0093 | Uplift to CSS Maximum Demand Volumes during MHHS Migration Period | Initial Assessment
R0094 | Clarify obligations on gas meter exchanges that occur close to CoS | Initial Assessment
R0095 | Changes to allow DNOs to reinstate disconnected MPANs | Initial Assessment
R0096 | CSS Message Regeneration Functionality | Initial Assessment
R0099 | CSS End User Obligations | Initial Assessment
R0100 | Update to Error Handling Documents | Initial Assessment

## Slide 22: Section 3: Capture

## Slide 23: New Change Proposals
For Information
XRN5556E CMS Rebuild Version 1.4
XRN5556F CMS Rebuild Version 1.5

## Slide 24: XRN5556E CMS Rebuild Version 1.4
Customer Parties | Impacted Party
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | X
IGTs | X
For information | 
DSC Service Area Associated Funding Split | N/A – Investment funded
Proposed Funding split from Proposer | N/A
Change Description (Link to CP)
This XRN will be a child XRN to 5556. Within this version we will strive to deliver additional functionality and processes where possible, however our priority processes are Address amendments (ADD/UNC). Should we have capacity in this version release to include anything additional, this shall be communicated out via Change Packs and the forums ChMC, CoMC and the Customer Focus Group.
Change Type | Non-Regulatory
Priority | Medium
Proposer | Xoserve

## Slide 25: XRN5556F CMS Rebuild Version 1.5
Customer Parties | Impacted Party
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | X
IGTs | X
For information | 
DSC Service Area Associated Funding Split | N/A – Investment funded
Proposed Funding split from Proposer | N/A
Change Description (Link to CP)
This XRN will be a child XRN to 5556. Within this version we will strive to deliver additional functionality and processes where possible, however our priority processes are RFA (Request for Financial Adjustment) and CDQ (Consumption Dispute Query) Should we have capacity in this version release to include anything additional, this shall be communicated out via Change Packs and the forums ChMC, CoMC and the Customer Focus Group.
Change Type | Non-Regulatory
Priority | Medium
Proposer | Xoserve

## Slide 26: section 4. Design & Delivery

## Slide 27: Design Change Pack
For Approval:
XRN5556.C - Contact Management Service (CMS) Rebuild Version 1.2 – Revised
XRN5602 - Releasing of unused capacity under a specific set of circumstances (Modification 0818)
For Information:
Maintenance of a Capacity Plan
UK Link Manual X09 - X10 Record Cosmetic Update

## Slide 28: XRN5556.C - Contact Management Service (CMS) Rebuild Version 1.2 – Revised
Change Proposal | Service Area | Comments
CP is issued for information at ChMC 12/10/2022 Link to CP | N/A | None
Detailed Design Summary
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3148.1 VO - PO | 1 |  | 1
ChMC Action | Voting Parties | Impacted Parties | Release
Vote to approve the Detailed Design and progress into delivery | Shipper, DNO, IGT, NGT | Shipper, DNO, IGT, NGT | Adhoc – 30/06/2023

## Slide 29: XRN5602 - Releasing of unused capacity under a specific set of circumstances (Modification 0818)
Change Proposal | Service Area | Comments
CP approved at ChMC 11/01/2023 Link to CP | Service Area 3: Manage updates to customer portfolio | Change will be implemented/made available immediately following Ofgem approval of Modification 0818
Detailed Design Summary
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3148.2 VO - PO | 2 |  | 
ChMC Action | Voting Parties | Impacted Parties | Release
Vote to approve the Detailed Design and progress into delivery | Shipper, DNO | Shipper, DNO | Adhoc - TBC

## Slide 30: Maintenance of a Capacity Plan
Change Proposal | Service Area | Comments
N/A | N/A | Within the Change Pack, Users have been invited to send their forecasts to Xoserve to enable planning for future capacity within UK Link
Detailed Design Summary
ChMC Action | Voting Parties | Impacted Parties | Release
For information | N/A | Shipper, DNO, IGT, NGT | N/A
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3148.3 VO - PO | 1 |  | 

## Slide 31: UK Link Manual X09 - X10 Record Cosmetic Update
Change Proposal | Service Area | Comments
N/A | N/A | N/A
Detailed Design Summary
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3148.4 - VO – PO | No representations received |  | 
ChMC Action | Voting Parties | Impacted Parties | Release
For information | N/A | Shippers | Adhoc

## Slide 32: Standalone Change Documents for Approval (BER, CCR, EQR)

## Slide 33: Standalone Change Documents for Approval (BER, CCR, EQR)
Document link | XRN | Voting
Link to CCR | XRN5595 Changes to the REC Switching Operator Outage Notification Lead Time (R0055) | Shipper

## Slide 34: November 23 Major Release Scope proposal - for approval

## Slide 35: Proposed Scope
Release | November 23 Major Release
Implementation Date | 4th / 5th November 2023 (no REC changes in scope so proposing weekend go live)
Contingency Implementation Date | 11th / 12th November 2023
BER Approval being sought from ChMC | 10th May 2023 subject to prior approval of scope
Note: | XRN 5186 has been partially delivered by the June 23 Major Release but was descoped at the end of regression testing. The cost that will be presented in the BER for November 23 Release will include the remaining costs to complete delivery, shown above, plus whatever risk/contingency is identified as part of the November release
Decision: | Required from the committee on proposed scope above
XRN | Title | Proposer | Benefitting | Funded by | Cost estimate | System Components | Design Change Pack Approved
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs​ | NGN | Shipper DNO | Service Area 3 | £66k (Remaining from June 23) | UK Link GES | Yes (July 2022)
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Service Area 4 | £300k (HLSO) | UK Link | No (May 2023)
 |  |  |  | Total | £366k |  | 

## Slide 36: November 23 CMS Release Scope proposal – for information

## Slide 37: November 23 CMS Release Scope
In addition to the two changes proposed in scope for the November 23 Major Release, the intention is also to deliver the following in November 23 as part of a CMS release:
Solution options for these changes are being Change Packed in May, ahead of submitted for approval at ChMC in June
The delivery approach for CMS related changes is done through an agile methodology
This will support a reduced overall timeline for development and delivery of the changes for customers
A BER for the November 23 CMS Release will be presented to ChMC for approval once design has been completed and approved by customers
XRN | Title | Proposer | Benefitting | Funded by | Cost est. | System Components | Design Change Pack Approved
5604 | Shipper Agreed Read (SAR) exceptions process (MOD 0811S) | SEFE | Shipper | Service Area 1 | £70-130k (ROM) | CMS UK Link | No
5605 | Amendments to the must read process (IGT159V) | Centrica | Shipper IGT | Service Area 4 | £30-70k (ROM) | CMS UK Link | No

## Slide 38: February 23 Release

## Slide 39: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, all XRNs have been successfully implemented on 25/02 and Post Implementation Support (PIS) completed on 24/03. Closedown is progress, on track for 30/06. Progress update: Implementation go live completed on 25/02 First usage completed XRN4978 First usage for XRN4992B and XRN4990 will be completed in May 23 and July 23 respectively by June 23 Project Team First usage of XRN4900 to be completed following go live of the Biomethane project (go live date TBC) First usage of XRN5298 to be completed following go live of the H100 project (go live date scheduled between June-Sept 24). Project closedown in progress, on track to complete by 30/06 Change Completion Report (CCR) to be issued out for approval at June’s ChMC Decision in April ChMC: None |  | Successful Implementation of 25th February 23 | 
Risks and Issues | There is a risk that the solutions being delivered under XRN4900 and XRN5298 may not work as expected at the point SGN go live with the Biomethane and H100 projects, due to the gap between these changes being delivered within the Feb 23 release and the respective go live dates of the projects. Update - SGN have confirmed that the first H100 connection will be sometime between June-Sept 2024. CDSP are awaiting further clarification regarding the go live date of the Biomethane project. Discussions are underway regarding options for carrying out additional testing closer to the project go live dates, which may incur additional charges that weren't originally accounted for. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0797 - Last Resort Supply Payments Volumetric Charges XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 28th March 2023
Complete
On Track
At Risk
Overdue

## Slide 40: March 23 Adhoc Release

## Slide 41: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking at risk; Amber. Design phase continues for both XRNs scoped for this release. Build and testing completed as planned for 5143 and 5379. Return to green is completion of design, planned for 31st March. Progress update: Project Startup and Initiation phase complete Project Build phase complete Project Testing complete Initial implementation completed on 25th March On –track for implementation and go-live from 1st April NDM SP procurement continues Weekly engagement sessions with Technolog continue Decision in February ChMC: None |  | Initial implementation date of 25th March completed with a go-live of 1st April. | 
Risks and Issues | 68488 & 68489: (R) The design has not yet completed for the changes in this release, therefore the aspirational delivery timescales remain ‘at risk’ until design completion currently targeting 31st March |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) |  |  | 
Slide updated on 29th March 2023
Complete
On Track
At Risk
Overdue

## Slide 42: June 23 Release

## Slide 43: XRN5562 – June 23 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | The overall status is Green; implementation planned for 24/06. Implementation contingency date 01/07 Decision received from ChMC on the 08/03 to descope XRN5186. XRN5186 will be descoped at the end of the regression testing phase on the 19/05 System integration testing for all ISU build completed on 03/03 Build in progress for Market Flow changes to complete on 07/04 GES build in progress for xrn5186 to complete on 11/04 User acceptance testing execution and assurance in progress to be completed on 07/04 Regression test case scenarios in review to be approved by 07/04 Regression testing execution to commence on 11/04 Decision in April ChMC:.No decision required |  | Implementation date of 24th June, with a contingency implementation date of 1st July | 
Risks and Issues | Risk 68719 - There is a risk that some of the customer data held is inaccurate prior to the implementation of XRN5186. Mitigation Action – Xoserve are currently working with customers to understand the best solution for this prior to the implementation of this change Risk 68721 - There is an associated risk (68719) that the current migration rules pre-implementation for XRN5186 are not currently defined and agreed. Mitigation Action - There is an action on June23 project team to provide further detail around current working assumptions for all scenarios at Go-live to be provided on 06/04. This will require validation by customers. Dependency 68747 - There is a dependency on Xoserve to provide clarification on the migration rules to be applied for XRN5186 prior to implementation. Mitigation Action - Project team to provide all possible scenarios and current working assumptions that could impact the implementation of xrn5186 and data volumes for each scenario 06/04. Dependency 68748 - There is a dependency on DNS to provide updated details around the NExA SHQ/SOQ held in the system before the capacity window closes on the 31st of October. Mitigation Action – Xoserve to continue to send out monthly report as per the agreed interim process to all DNs/Shippers notifying them of current vales held in the system Dependency 68754 - There is a dependency on RECCO to update the data permission matrix prior to the implementation of XRN5186. Mitigation Action - Delivery timeline has been shared with RECCO regular conversations in place between BA on June23 project and RECCO |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5091 - Deferral of creation of Class change reads at transfer of ownership XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  |  | 
Slide updated on 29th March 2023
Complete
On Track
At Risk
Overdue

## Slide 44: XRN5564 Gemini Sustain Plus Programme Update

## Slide 45: XRN5564 Gemini Sustain Plus
March 2023 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is Green as Gemini Sustain plus is currently tracking to planned timescales. Programme Objective Overview:​ The programme is on track to deliver the following during the current iteration. Approval of the High Level Design Review of the Low Level Design document. Completion of the Azure DevOps initial build. Service extraction for a further 3 microservices is in progress. 6 have completed. All 9 Scrums are resourced and fully mobilized and operating within an Agile framework​. Programme next steps: Obtain approval of the Low Level Design and security framework. Development of microservice's. Begin test execution on developed microservice's Continue the service extraction activity. Commencement of Training and Business Readiness planning. The programme wants to reiterate that industry engagement is a key pillar of the delivery of Sustain Plus. The engagement approach is currently being created and will be shared in the coming months Programme Governance Updates: ​ 3rd party contracts are in place for the next phase of delivery. Project status: ​ Milestones to track delivery progress are being monitored on the Sustain+ Solution Roadmap. Planning activity will soon commence to shape the delivery objectives for the next programme increment. | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  | Due to the length of the programme we will be showing a rolling 12 month view of the POAP | 
Risks and Issues | There are no key issues or risks within the programme. Due to the amount of parallel teams that are working on the programme and the mitigation plans that are place there is nothing that needs to beflagged at a programme level | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Forecasting costs within approved spend | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5564 – Gemini sustain – The re-platform and development of the Gemini application and its processes, for further information on Gemini Sustain Plus please visit the Xoserve website; Gemini changes overview (xoserve.com) | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 

## Slide 46: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS MAR 2023 – FEB 2025
MARCH 2023

## Slide 47
Programmes & Projects 2023-2025 |  |  | 2023 |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 | 
 |  |  | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
MAJOR RELEASES | Gemini Sustain + | CP5564 Gemini Change Programme Sustain + |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MAJOR RELEASES | Regulatory / Customer Requested Change | XRN5579 Gemini Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS 2023 – 2025
Design to PIS Oct 22 to Oct 24
CV01
LTFS
XRN5579 CV01 Long Term Flow Swap automation implemented successfully on 19th March into Gemini
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.

## Slide 48: DDP April CHMC update

## Slide 49: Agenda
Roadmap update
Latest Sprint update

## Slide 50
Roadmap
PRODUCT DEVELOPMENT AND ROLLOUT
2022
04
05
06
07
08
09
10
11
12
01
02
03
04
05
06
07
08
09
10
11
12
01
02
2023
2024
Release 1 – Shipper Pack
03
ACTIVITY
Change freeze
Issue – (Requires escalation/support)
At risk - (Risk is being managed)
On track
KEY
Complete
Milestone
Release 2 – Golden Bullet forecast & IGT MDD data analysis
Release 3 – Golden Bullet invoice
Release 4 – XRN4990
Release 5 – XRN4990
Release 6 –XRN 4990 implement and DN financial reporting
Release 1 – Golden Bullet enhancement and
REC data model prep
Release 2 – REC
Release 3 – REC

## Slide 51
Data Discovery Platform | Current Sprint (part of release 6)
Goals: Complete MOD664 Shipper testing - Complete in line with milestone Complete MOD664 PAC testing – Complete in line with milestone Implement MOD664 Shipper dashboards – in progress Implement MOD664 PAC dashboards – in Progress Refine and prioritise DN financial reporting user stories – Complete Deliver | 
Outcomes: XRN4990 (MOD664) testing milestone met – complete Implement Shipper MOD664 dashboards Implement PAC MOD664 dashboard Implement new functionality to highlight sites to be updated by CDSP and auto loaded into CDSP dataset. Refine Financial reporting user stories with DNs in preparation for the next sprint | 

## Slide 52: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 53: April ChMC CMS Rebuild Update

## Slide 54: Progress to Date
XRN5556.d – The Isolation (ISO) and DTL processes will be going live on 24th April 2023. To support this the following will be arranged:
  Customer Focus Group (11/04/23) – a run through of the processes
  Additional end to end process walkthrough week commencing 17/04/23
  Bridge call support sessions
  Training Material published
Two additional child XRNs have been created to support the next two releases, should there be any capacity within these two version releases other processes or functionality will be brought in scope for delivery with the agreement of the Customer Focus Group:
  XRN5556.e - Address Amendments (ADD/UNC)
  XRN5556.f – Request for Adjustments (RFA) and Consumption Dispute Query (CDQ)
We are working with the UKLink Change team to deliver two change proposals as part of the CMS Rebuild November Release:
  XRN5604 – Shipper Agreed Reads
  XRN5605 – IGT Must Reads
The Customer Focus Group placeholders for the remainder of the year have now been issued and these will be updated on the Xoserve Webpage
The CMS Rebuild webpage (https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild/) contains the link to register for future Customer Focus Groups which are captured below, please note the agenda for the Focus Groups will be issued between 3 - 7 days prior to the session.

## Slide 55
XRN 5556.b
Release Content
Now
Next
Later
A little Later
Supplier Theft of Gas (SUT)
Meter Number Creation (MNC)
Duplicate MPRNs (DUP)
Set to Extinct
Isolations
(ISO)
Dead to Live
(DTL)
DUP Enhancements
Generic to desk workflows – AGG, PSI, PSR
Address Amendments (ADD/ UNC)
Enhancements to MNC Process including Network
Generic to desk
workflows – GIC
Main Release
Additional Stretch Enhancements
Request for Adjustment (RFA)
Consumption Dispute Query (CDQ)
Generic to desk
workflows – FLE
Gas Safety Regulation
(GSR)
Manage Unregistered Sites
(MUS)
SUT Enhancements
XRN 5556.a
New Process
New MPRN Creation
(FOM)
Daily Metered Query (DMQ)
XRN 5556.d
24th April 2023
Bulk Upload file
XRN 5556.c
Targeted
30th June 2023
CMS Rebuild Roadmap
XRN 5556.e
Targeted
30th June 2023
XRN 5556.f
Targeted late August 2023
Network Raised Theft of Gas
(TOG)
Must Reads
(MUR)
Shipper Agreed Reads
(SAR)
XRN 5604
IGT159 Must Reads
XRN5605
Targeted October
2023
Targeted October 2023
Reprioritised to accommodate
November release 2023

## Slide 56: Section 6: AnY Other Business

## Slide 57: Q3 KVI Change Management Survey Results

## Slide 58: KVI Change Management Survey – January 2023
Score decreased from 9.5 to 8.0 from last survey
YTD Scorecard for 22/23 has decreased from 9.5 to 8.8
Number of participants stayed the same @ 4
Chart: Change KVI Survey: Rolling Performance
| Jan-22 | Apr-22 | Oct-22 | Jan-23
% of positive answers per survey | 0.79 | 0.71 | 0.95 | 0.8
# of responding organisations | 9 | 5 | 4 | 4

## Slide 59: Q4 KVI Customer Change Survey
We would like to request your feedback on our Change Management performance
The scope of your feedback should include changes that we have developed and delivered for DSC customers within the last quarter
The KVI Survey will be open between Monday 3rd April – 17th April

## Slide 60: Appendix

## Slide 61: DDP Appendix

## Slide 62
Data Discovery Platform | Previous sprint (part of release 5)
Goals: Complete Build – complete Establish besta team – complete Establish DN sprint goal for release 6 – ongoing | 
Outcomes: XRn4490 build milestone met – complete Beta team working with delivery team refine dashboards in preparation for implementation (in line with feb release) – ongoing Work with DNs to establish sprint goal ahead of release 6 | 

## Slide 63
Data Discovery Platform | Release 4
Goals: Complete detailed design Complete source to target Build 50% data model Enable additional Shipper Pack reports to be self served via DDP Facilitate MDD vs UKLink analysis for IGTs – Stretch | 
Outcomes: Detailed Design for the XRN4990 Solution pertaining to DDP Source to target completed for XRN4990 50% of XRN4990 data model built Additional Shipper pack delivery enabling Incorrect read factor and units to be self served via DDP Additional shipper pack delivery Shipper read frequency giving shipper portfolio count by MRF and a view of the average industry % by MRF code Stretch Targets: Additional analysis of UKLink / MDD data quality Industry view of read rejections by reasons code to compare company performance against industry average | 

## Slide 64
Data Discovery Platform | Release 2
Goal: Enable Distribution Network Users to access a financial forecasting report (part of the golden bullet), to understand variances between formula year AQ / SOQ and rolling AQ / SOQ to understand the impact this has on revenue. | 
User Stories: As a DN I want a view of my Formula year AQ/ SOQ and Rolling AQ / SOQ simulation data grouped by: LDZ, Exit Zone, Shipper Short, EUC, Code, Charge Type, Charge Rate, Asset Type, AQ Band and Class As a DN I want total FY AQ / SOQ and Rolling AQ / SOQ displayed in kwh and as a percentage, and the difference between the two As a DN I want total charges by Rolling and Formula Year AQ / SOQ totals and difference As a DN I want the number of MPRNs grouped by charge type between Formula year AQ / SOQ and Rolling AQ /SOQ (by kwh and percentage difference) so I can see how many MPRNs fall into each group and the difference between FY and Rolling for each charge type in both kwh and percent age and split by LDZ, Exit Zone, Class, AQ band, Shipper Short Code and Asset Type Charge types: ZCA, 891, CCA, CFI, ECN, C04 As a DN I want a trend view between Formula Year and Rolling AQ and SOQ with the total charge position for both Stretch element: As a DN I want the number of MPRNs grouped by % difference between FY AQ and rolling AQ and between FY SOQ and Rolling SOQ As a DN I want the number of MPRNs grouped by kwh difference between FY AQ and Rolling AQ and FY SOQ and rolling SOQ so I can see how many MPRNs fall into each group As a DN I want to see the total number of MPRNs that have had a rate change within the last month, and have these split by reason for the rate change (Shipper change, Class change, other) so I can understand how rate changes are affecting my revenues | 

## Slide 65
Data Discovery Platform | Release 3
Goals: Complete model to enable the aggregated invoice element of the Golden Bullet Report Enable more elements of the Shipper pack to be self served | 
User Stories: Build the data model to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on aswell that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year As a Shipper I want to be able to report on Dead meters via a monthly snapshot and see a trend over 12 months, so that the dead report in the Shipper pack can be retired As a Shipper I want my read performance for class 3 sites to be displayed as 'MET' when I have achieved 90% of reads accepted so that I can monitor my read performance Analysis of the below user story; As a Shipper I want an industry view of read rejection reasons so that I can compare my performance with industry Read rejections by reason code (numbers). Existing report need enhancing to give; Read rejections by reason code percentage value for a Shipper needs to be added to current dashboard Industry average number of read rejections (number and percentage) needs adding Performance enhancement to give a greater user experience of the large volumes Stretch targets: As a Shipper I want to see a list of sites in my portfolio containing plot addresses so that I can assess and update the address details correctly & in a timely manner. As a Shipper I want the WAR Bands dashboard to be moved out of UIG area of DDP and added to the Reads area of DDP so that it sits more logically from a business process perspective | 

## Slide 66
Data Discovery Platform | Inflight Sprint (part of release 3)
Goals: Build the golden bullet invoice report Build the detailed design for the XRN4990 solution | 
User Stories: Build the dashboards to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on as well that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year Performance optimisation for read dashboards Detailed Design for the XRN4990 Solution pertaining to DDP Stretch Target: Must read enhancement to align BAU enhancement to DDP Industry view of number of MPRN associated to MRF (part of Shipper Pack XRN 5200) | 

## Slide 67: Portfolio POAP