## Slide 1: Change Management Committee
December 2022

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: General Change Budget BP22 YTD

## Slide 4: Forecasted Year End Spend (BP22)
The graph below illustrates the current forecast for financial year-end utilisation of the General Change investment budget (BP22) – this is subject to change should ChMC approve further change delivery
Committed spend has increased since last month by £156k (Shipper +£11k, DNs -£168k)
Link to Change Budget
Chart: Committed to date per constituency
| Shipper | DN | IGT | NTS
Committed | 1413960.59 | 674440.41 | 13455 | 0
Uncommitted | 465400.8629 | 457255.9219 | 163447.9397 | 66021.5255
Note: Committed spend reflects all approved funds up to 28th November

## Slide 5: Change Pipeline

## Slide 6: Change Delivery Pipeline August 22 – December 23
CSSC Go-Live
February 23 - Major Release (XRN5533)
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992b, XRN5298
July 22
February 23
June 23 - Major Release (XRN5562)
XRN5091, XRN5186, XRN5482 (tbc)
November 22
June 23
November 23
XRN5515
XRN5231
XRN5469
November 23 – Major Release
No Major Release
XRN5236
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 28 November 2022
XRN5565
XRN5529
XRN5561
March 23 - AdHoc Release (XRN5575)
XRN5379, XRN5143, XRN5472
XRN5541
XRN5573A

## Slide 7: Change Pipeline - Delivery Plan - July 2022 - February 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5515 | HyDeploy Close Down | NGN | Shipper DN | DN DeCarb | N/A | 18th July 2022 | AdHoc | Delivered
5231 | FWACV Service – MOD 0793S | SGN | DN NG | DN NG | £1.198m | 1st September 22 | AdHoc | Delivered
5529 | UNC Derogation process – MOD 0800 | NGN | N/A | N/A | N/A | 1st October 22 | N/A | Delivered
5565 | CDSP as the Scheme Administrator for the Energy Price Guarantee for Domestic Gas Consumers – MOD 0824 | NGN | Shipper | Shipper | £1m – 1.5m | 1st October 22 | AdHoc | Delivered
5469 | Increase Frequency of FSG Payments | Cadent | DN | DN | £63.3k | 3rd October 22 | AdHoc | Delivered
5561 | Reform of Gas Demand Side Response (DSR) Arrangements – MOD 0822U | National Grid | NGT Shipper | NGT | N/A | 17th October 22 | AdHoc | Delivered
5236 | Reporting Valid Confirmed Theft of Gas in central systems – MOD 0734 | Gazprom | Shipper | Shipper | £74k | Oct / Nov 22 | CMS Rebuild Release 1 | Delivered (Not Live)
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | December 22 | AdHoc | Indicative
5541 | Amendments to the UIG Additional National Data Reporting | Scottish Power | Shipper | Shipper | N/A | 23rd December 22 | AdHoc | Indicative
4900 | Biomethane/Propane Reduction | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Firm
4989 | Residual AMT activities | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DN | Shipper DNO | £108.7k | 25th February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm

## Slide 8: Change Pipeline March 2023 – June 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | March 23 | AdHoc | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | £75k | March 23 | AdHoc | Firm
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | Shipper DN | Shipper DN | £75k | March 23 | AdHoc | Firm
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | June 23 | Major | Indicative
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | June 23 | Major | Indicative
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper | £300k | June 23 (tbc) | Major | Indicative

## Slide 9
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | Tbc | Tbc | N/A
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5531 | Hydrogen Village Trial | SGN | All DSC Customers | DN Decarb | Tbc | Tbc | Tbc | N/A
5535 | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | All DSC Customers | Shipper | Tbc | Tbc | Tbc | N/A
5545 | Hydrogen Trial Visualisation Dashboard | Northern Gas | All DSC Customers | DN Decarb | Tbc | Tbc | Tbc | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | Tbc | February 2023 | Tbc | N/A
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | Tbc | Tbc | Tbc | N/A
5567 | Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067) | Xoserve | All DSC Customers | Shipper | Tbc | Tbc | Tbc | N/A
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Tbc | Tbc | Tbc | N/A
5573 | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) – Urgent | Xoserve | All DSC Customers | Part A – N/A ------------------ Part B - Tbc | Part A – N/A ------------------ Part B - Tbc | Part A - October 2022 ------------------------------- Part B - Tbc | Part A – AdHoc ------------------------ Part B - Tbc | Part A – Firm ------------------------ Part B – N/A
5584 | Procurement of Climate Change Methodology for Demand Estimation Purposes | Xoserve | DN Shipper | DN Shipper | Tbc | Mid 2023 | AdHoc | Indicative
5585 | Flow Weighted Average Calorific Value - Phase 2 Service Improvements | Cadent | DN | DN | Tbc | Tbc | Tbc | N/A
Change Backlog Details - Continued

## Slide 10: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | *Mod0651 – Retrospective Data Update Provisions* | Cadent | Shipper DN | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
*Mod0651 : 28.11.22 - Change Status remains on hold and will be reviewed on a monthly basis with ChMC – in line with request from UNCC

## Slide 11: REC Change
7th December 2022

## Slide 12: Introduction
The following 5 slides have been included in this months ChMC pack to give you an overview of the ongoing REC Changes, we have broken these down into the following sections:
In progress – we are currently progressing through the Change journey
Under Prioritisation Review with Code Managers – due to workload/prioritisation
There are 2 additional slides showing all Electricity related Changes which we are monitoring for visibility, these have been included in the appendix
Note: In the New Year, we will be undertaking a review of all REC Change and as a result, will stop monitoring and remove from this pack any Changes that have no impact to Gas services. This will be largely, but not limited to Electricity Change. We will advise the Committee of which Changes we will be excluding.
Further information on the Changes can be found on the REC Portal

## Slide 13: Overview of REC Changes (high level)
Chart: 
| In Progress | Current Xoserve action | Implemented | Under Prioritisation Review | Electricity only
Column1 | 11 | 5 | 2 | 15 | 26
Total count of current REC Change:
59

## Slide 14: Overview of In progress REC Changes (high level)
Chart: 
| Approved awaiting implementation | Consultation | Solution development | Awaiting authority decision | Detailed IA/Party Impact Assessment | Final Assessment
Series 1 | 2 | 1 | 2 | 1 | 2 | 3
Notes: In progress:
Approved awaiting implementation 10,11,36
Consultation 47,52,55
Solution development 16,37
Initial assessment 25
Awaiting authority decision 21
Scoping Testing requirements 67
Detailed IA 70,74
New CR05_XoS

## Slide 15: REC Change Pipeline – In progress
Title | Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority
R0016 | Resolution of Bilateral Erroneous Transfers | N/A | Ben Atkinson | - | Solution development | 21/12/2022 – Review at Change panel | TBC | Low
R0021 | Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier | N/A | Gemserv (RPS) | - | Awaiting Authority Decision | 30/06/2023 – Proposed Implementation date | Major | Medium
R0025 | Service Provider Performance Charges (DCC) | N/A | Deloitte (RPA) | TBC | Consultation | 06/12/2022 – Consultation closeout | TBC | High
R0030 | Erroneous Transfer Cancellations | N/A | Scottish Power | - | Approved - awaiting implementation | 30/06/2023 – Proposed Implementation date | Major | Low
R0033 | Micro-business Smart Meter Installation Reports | N/A | EDF Energy | - | Implemented | 04/11/2022 – Confirmed Implementation date | Standalone | Low
R0036 | Extensive Housekeeping Amendments | N/A | Gemserv (RPS) | - | Implemented | 04/11/2022 – Confirmed Implementation date | Standalone | Medium
R0037 | Prepayment Credit Balance & Debt Transfer Processes | N/A | Utilita Energy Ltd | - | Solution development | 17/01/2022 – Change proposal plan to be updated | TBC | Low
Currently working on
Key:
Under assessment

## Slide 16: REC Change Pipeline – In progress
Please note: This is a working document and therefore some of the dates and actions may have progressed since the slides were created
Title | Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority
R0047 | Metering Code of Practice Consolidation Review | N/A | RECCo | - | Approved - awaiting implementation | 01/04/2023 – Proposed Implementation date | TBC | High
R0052 | GES Service Definition Document | N/A | Deloitte | GES | Final Assessment | 24/02/2023 – Proposed Implementation date | Major | Medium
R0055 | Switching Operator Outage Notification Lead Time | XRN 5595 | DCC | GRDS, GES | Final Assessment | 24/02/2023 – Proposed Implementation date | Major | Medium
R0067 | Introduction of CSS refresh functionality | XRN 5567 | Capgemini (RTS) | GRDS | Party Impact Assessment | 09/12/2022 – Response deadline | Standalone | High
R0070 | Provision of Enduring Test Environments | N/A | Capgemini | GES | Final Assessment – Environment delivered | 30/11/2022 – Review | Standalone | High
R0074 | Release of Community View Data Items to MEMs in GES | N/A | Xoserve | GES | Party Impact Assessment | 19/12/2022 – Response deadline | Major | High
Currently working on
Key:
Under assessment

## Slide 17: REC Change Pipeline – Under Prioritisation Review
Title | Description | Status | Next Action date
R0006 | Missing Meter Technical Details | Initial Assessment | Reviewed weekly – Awaiting instruction from REC Code Manager to progress
R0049 | Intellectual Property Rights and Services Data Main Body changes | Initial Assessment | 
R0050 | Clarification of REC Maintenance of Qualification Schedule | Initial Assessment | 
R0051 | Switch Request Objections (Change of Occupier) | Initial Assessment | 
R0056 | EES/GES additional service request for Housing Ass to be added to the Matrix | Initial Assessment | 
R0059 | Maintenance of Qualification Schedule Change | Initial Assessment | 
R0061 | Resolution of invalid CSS data by Data Owners | Initial Assessment | 
R0063 | Addition of key information to all Service Now tickets | Initial Assessment | 
R0068 | REC Data Protection Changes | Initial Assessment | 
R0069 | Amendments to Sample Access Agreement | Initial Assessment | 
R0071 | DCC access to EES and GES | Initial Assessment | 
R0073 | Introduction of a Housekeeping Change Proposal Process | Initial Assessment | 
R0075 | Enabling Software Product Qualification | Initial Assessment | 
R0080 | Improvements to "Failed to deliver" CSS messages | Initial Assessment | 
R0081 | CSS Market message retry strategy | Initial Assessment | 

## Slide 18: Section 3: Capture

## Slide 19: New Change Proposals
For Approval
XRN5579 Regulatory Change 2022
For Information
XRN5595 Changes to the REC Switching Operator Outage Notification Lead Time (R0055)
XRN5597 Amendments to v27 of the Service Description Table

## Slide 20: XRN5579 Regulatory Change FY22
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | 
National Grid Transmission | X
IGT’s | 
DSC Service Area: | Service Area 14: Gemini Services
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
National Grid Gas Transmission and Metering has introduced a new agile way of working known as SAFe. Gemini system development has moved to this new framework and a faster governance process is required to be able to submit work to the programme backlog ready for planning in future Programme Increments (PIs). Currently there is only one Change Proposal (CP) in the Gemini Regulatory programme (CP5455) - Gemini Autumn Release 22. Work on this is due to complete in November 2022. Once it has completed there will be no active Change Proposal against which work can be booked. The intention is for an umbrella Change proposal to be created for the remainder of FY22/23 under which CVs can be submitted to accommodate changes to UNC and other regulatory work as required.
Change Type | Regulatory
Priority Score | High

## Slide 21: XRN5595 Changes to the REC Switching Operator Outage Notification Lead Time (R0055)
Customer Class Impacted | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
For Information Only | 
DSC Service Area | Service Area 1: Manage Shipper Transfers
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
Within the Switching Operator Service Definition document, the Central Switching Service (CSS) Provider (DCC) is required to provide 10 Working Days’ (WDs) notice of planned system outages. However, within the CSS Provider’s processes and the Switching Operator Change Management Process Category 3 document, an 8 WD lead time is set out. This change seeks to address this discrepancy and align the code documentation. The approved Solution that has been agreed under the REC is Solution Option 1, which seeks to amend the notice period from 10WD to 8WD within the Switching Operator Service Definition document. As a result of this, the CDSP, as a Switching Data Service Provider, needs to amend processes surrounding interactions with the CSS Provider to ensure this is reflected. Note: This will be implemented in line with the Feb 23 release
Change Type | Regulatory
Priority Score | Low

## Slide 22: XRN5597 Amendments to v27 of the Service Description Table
Customer Class Impacted | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
For information and will be presented to CoMC for approval on 14/12/22 | 
DSC Service Area | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
This Change Proposal is to seek approval at CoMC on 14th December 2022 for the removal of the following temporary service line (introduced under XRN5452 which was approved at CoMC in November 2021):- Temporary community access to pre-COVID AQ values for Shippers – Service Expiry as of 01 November 2022 DSC ref:- DS-NCS-SA2-01 In addition, following consultation at a recent DN Constituency meeting it is proposed to remove the ASGT-CS-SA5-08 service line as it is no longer relevant.
Change Type | Documentation Change
Priority Score | N/A

## Slide 23: Change Proposals – Post Solution Review for Approval
XRN5482 Replacement of reads associated to a meter asset technical details change or update (RGMA)

## Slide 24: XRN5482 Replacement of reads associated to a meter asset technical details change or update (RGMA)
Solution Review Consultation Summary
Change Pack Ref | HLSO Cost | Service Area | Funding Split (Voting) | Impacted Parties | Preferred Option | Proposed Delivery | Link to CP | Representation Summary |  | 
 |  |  |  |  |  |  |  | Approve | Defer | Reject
3110.1 - VO - PO | £175k - £300k | Service Area 4 | Shippers 33%, DNOs 67% | Shippers | Option 1 | TBC | Link to CP |  |  | 
Org | Status | Comments
 |  | No Representations Received

## Slide 25: section 4. Design & Delivery

## Slide 26: Design Change Pack
For approval
XRN5541 Amendment to the UIG Additional National Data Reporting
CMS Rebuild – Standard of Service Query Management – Revised Change Pack
XRN5298 H100 Fife Project Phase 1
Description correction within the S15 Record
For Information
XRN5573 - Part A - Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) – Urgent
Amendments to DSC Budget and Charging Methodology v5_CDSP Service Description V5

## Slide 27: XRN5541 Amendment to the UIG Additional National Data Reporting
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Impacted | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  |  | Approve | Defer | Reject
3110.2 - VO - PO | Service Area 9: Customer Reporting (all forms) Zero cost change | Shipper | Shipper | Adhoc - December 2022 | Link to CP | 1 |  | 
Org | Status | Comments
Scottish Power | Approve | Thank You for adding in our additional requirements to the change request, this is exactly what we were looking from the report.

## Slide 28: CMS Rebuild – Standard of Service Query Management – Revised Change Pack
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Impacted | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  |  | Approve | Defer | Reject
3110.3 - VO - PO | N/A CMS Investment funded | Shipper, DNO, IGT, NTS | Shipper, DNO, IGT, NTS | Adhoc date TBC | Link to CP | 2 |  | 
Org | Status | Comments
WWU | Support | WWU supports this change and has the follow feedback to the questions in the DD: Is the reporting utilised within your organisation? Yes, our operational teams utilise this report to support the efficient processing of queries. Do you foresee an ongoing need to have this reporting available in new CMS? CMS would be the most appropriate location to receive reports.
NGN | Support | At the time of writing, and after internal review, we are not aware of any reason why the Query Management SoS reporting should be replicated in the CMS rebuild.

## Slide 29: XRN5298 H100 Fife Project Phase 1
Detailed Design Consultation Summary – From May 2022 ChMC
Change Pack Ref | Funding | Voting | Impacted Parties | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  |  | Approve | Defer | Reject
3015.3 - RT - PO | N/A Decarb investment budget | Shipper, DNO | Shipper, DNO | February 23 | Link to CP | 1 |  | 
Organisation | Status | Comments
Wales & West | Approve | We support this change as it advances the use of Hydrogen in networks and works towards net zero targets.
This Detailed Design was previously deferred in May 2022 due to the Modification 0799 awaiting Ofgem decision, and issued for information in October 2022 to clarify the design. Ofgem have now approved Modification 0799, which is to be implemented on a date to be confirmed. Shippers and DNOs are to vote for Design approval. Please note this is within scope of February 23 Release.

## Slide 30: Description correction within the S15 Record
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Impacted | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  |  | Approve | Defer | Reject
3110.5 - VO - PO | N/A | Shippers | Shippers | Immediately after ChMC approval | N/A |  |  | 
Org | Status | Comments
 |  | No Representations Received

## Slide 31: XRN5573 - Part A - Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) – Urgent
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Impacted | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  |  | Approve | Defer | Reject
3108 - RT - PO | Service Area 3 Split: 90% Shipper, 10% DNO | N/A – For Information Only | DNO, Shipper, IGT, NTS | Part A – October 2022 Part B - TBC | Link to CP |  |  | 
Org | Status | Comments
 |  | No Representations Received

## Slide 32: Amendments to DSC Budget and Charging Methodology v5_CDSP Service Description V5
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Impacted | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  |  | Neutral | Defer | Reject
3110.4 - VO - PO | N/A | N/A – For Information Only | Shipper, DNO, IGT, NTS | 1st April 2023 | N/A | 1 | 1 | 
Org | Status | Comments
WWU | Defer | If these services are mandated by the UNC and are provided to all Shippers or GDNs as seems to be case with the services described, then why are they not Direct Services – Code Services. If they are not Code Services, and we would argue that the FWACV service is not a Code Service as it is provided to fulfil the obligations on GTs of the Gas (calculation of) Thermal Energy Regulations, then they are Direct Services – non-Code Services. If a new Service Area that provides for 100% DN funding is required, then this can be created within the existing categories of Services. If a new Shipper Service Area is required for CSS Services, then this can be likewise accommodated within the existing categories of Services. We think that this change should be deferred until the above points are resolved. The concept of Mandatory Specific Services could be used for the new service line introduced by UNC modification 0710 under which the CDSP will provide Class 1 read services to Shippers with a Class 1 Supply Point, but that justification is not part of this change proposal. Regarding the legal text we suggest that, if implemented, proposed new clause should have “by a Customer” added as shown below for clarity. 2.3.2 Mandatory Specific Services are a subcategory of Specific Services and are those that are not ordered by a Customer but are provided as mandated by UNC to Mandatory Specific Service Recipients.
NGN | Neutral | We are unclear as to the distinction of “Mandatory Specific Service” from the existing code related services. The definition provided in the proposed changes to the CDSP Service Document, under in 2.3.2 states that these are ‘not ordered but are provided as mandated by UNC’, which seems unclear and needs additional clarity.
This will go to CoMC for approval on 14th December 2022

## Slide 33: Standalone Change Documents for Approval (BER, CCR, EQR)

## Slide 34: Standalone Change Documents for Approval (BER, CCR, EQR)
BER for XRN5579 Gemini Regulatory Change
  Voting NTS
BER for XRN5565 Appointment of CDSP as the Scheme Administrator for the Energy Price Guarantee (EPG) for Domestic Gas Consumers (Gas) (UNC0824)
  Voting Shippers

## Slide 35: December 2022 - ChMC Mod0800 Introducing the concept of a derogation framework into Uniform Network Code (UNC) Recap of Solution and Proposed Next Steps with CCR

## Slide 36: Purpose of ChMC Update
Confirm the process for any future Derogation requests
Propose the next steps
Closedown XRN5529

## Slide 37: Background
UNC Modification 0800 - Introducing the concept of a derogation framework into Uniform Network Code (UNC), was raised to introduce a framework for derogation as a concept in the UNC, defining when and how these can be requested (Use Cases), as well as the process around consideration and approval or rejection of derogation requests. Also includes a Use Case for ‘Net Zero Innovation’ including the parameters, and evidence required.
Modification 0800 was approved by Ofgem on 30 May 2022 and was implemented on 01 October 2022.
DSC Change Proposal XRN5529 was raised to support Modification 0800 and to ensure the CDSP had a process in place to receive, handle and manage derogation requests which require impact assessment.

## Slide 38: Agreed Steps
This is a process and governance change - no technical changes have been identified for customers
Any future changes that look to use the derogation process will follow the normal change process and be impact assessed

## Slide 39: Derogation Request Process
To undertake any central system and process impact assessment for a UNC Derogation request, the existing Rough Order of Magnitude (ROM) process should be utilised
Where a ROM is being requested for a UNC Derogation request, the existing ROM Request Template should be populated by the requesting party and sent to the following box account.
  box.xoserve.decarbonisation@xoserve.com
  Please note – for UNC Derogation ROM requests, the box account to send the request to is different.
For reference, the ROM Request Template can be located on the Joint Office website here.
Please note, parties must ensure that it is clearly stated on the ROM form that this is a request for UNC Derogation under Modification 0800

## Slide 40: Proposed Next Steps
Xoserve are looking to provide clarity on the UNC Derogation process for any future requests
CCR for XRN5529 UNC Derogation process – MOD 0800
  - Voting Shipper, DNO, IGT, NTS

## Slide 41: February 2023 Major Release

## Slide 42: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, UK Link system testing phase completed on 28/10 as per plan. Currently on track to complete user acceptance testing phase 08/12, with regression testing prep in progress and test execution commencing on 12/12 Progress update: UK Link system testing completed on 28/10 DDP build for XRN4990 in progress, delivery on track to complete by 20/01 User acceptance testing on track to complete 08/12 Regression testing preparation in progress, test case execution to commence on 12/12 Decision in December ChMC: XRN5298 Detailed design change pack approval |  |  | 
Risks and Issues | XRN5298: There is a risk that UNC Modification 0799 will not be approved, leading to delays in build activities or a need to rework the proposed solution being delivered under XRN5298 in its entirety. While ChMC approved the move to deliver this change at risk under the assumption that the MOD will be approved, any potential regret spend associated with this change should this not be the case increases as build activities continue to progress. Update – UNC799 was approved on 18/11/22. Detailed design change pack to be presented for approval in December ChMC |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0687 - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process - Inner for replacement reads and read insertions​ XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 24th November 2022
Complete
On Track
At Risk
Overdue

## Slide 43: March 23 Adhoc Release

## Slide 44: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking at risk; Amber, Design phase continues for all three XRNs scoped for this release. Build due to commence from 28th November for 5379 and 5472 but this is at risk due to status of design. Return to green is completion of design as planned and approved detailed project plan for delivery including touch-points with DM and NDM service providers. Progress update: Workshops to aide understanding of the changes, in lieu of design completion taking place Commenced engagement with the DM service provider for 5379 Project in startup and initiation phase including development of detailed project plan and project artefacts Decision in December ChMC: None |  |  | 
Risks and Issues | 68488 & 68489: The design has not yet completed for the changes in this release, therefore the aspirational build timescales are at risk 68126: The NDM service provider (SP) is not yet agreed, until the NDM SP is engaged and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April 68498: The DM SP is agreed, but not yet fully engaged, until the DM SP is engaged and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) XRN5472 - Creation of a UK Link API to consume daily weather data for Demand Estimation processes |  |  | 
Slide updated on 24th November 2022
Complete
On Track
At Risk
Overdue

## Slide 45: XRN5231 Provision of a FWACV Service

## Slide 46: XRN5231 Flow Weighted Average CV
December 2022 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is tracking at Green as the FWACV service went live 1st September and monitoring and tracking of the service will continue for the remainder of PIS. Cutover and Transition plan presented to Project Focus Group on 12th July BER was approved at Change Management Committee on 13th July Successfully delivered the awareness session to DN’s, positive feedback was obtained all round 27th July Dual Run/ Market Trials completed on 11th August Updated Design Change Pack Baselined and new version published to project stakeholders 17th August FWACV service went live on 1st September PIS commenced on the 1st September and till 28th October Completed handover to BAU 28th October Next Steps: Commence Closedown activities and documentation The CP for FWACV 2 was presented at last month's CHMC, scope and requirements will now be progressed with the DNs | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  |  | 
Risks and Issues | N/a | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Forecasting costs within approved spend | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change parts A & B - A - PRCMS validation/processing & Part B - LDZ Stock Change and Embedded LDZ Unique Sites | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 

## Slide 47: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS NOV 2022 – OCT 2024
NOVEMBER 2022

## Slide 48
Programmes & Projects 2022-2024 |  |  | 2022 | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
MAJOR RELEASES | Regulatory / Customer Requested Change | XRN5455 Autumn Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain Yr 1 | XRN5368 Gemini Change Programme Sustain Yr1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain + | CP5564 Gemini Change Programme Sustain + |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS 2022 – 2024
Closedown
in Progress
Oct 22 to Jan 23
Design to PIS Oct 22 to Oct 24
Closedown
in Progress
Nov 22 to Jan 23
Closedown
in Progress
Oct 22 to Jan 23
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.

## Slide 49: DDP December CHMC update

## Slide 50: Agenda
Roadmap update
Latest Sprint update
Appendix
3.A Customer priorities
3.B Previous release updates

## Slide 51
Roadmap
PRODUCT DEVELOPMENT AND ROLLOUT
2022
04
05
06
07
08
09
10
11
12
01
02
03
04
05
06
07
08
09
10
11
12
01
02
2023
2024
Release 1 – Shipper Pack
03
ACTIVITY
Change freeze
Issue – (Requires escalation/support)
At risk - (Risk is being managed)
On track
KEY
Complete
Milestone
Release 2 – Golden Bullet forecast & IGT MDD data analysis
Release 3 – Golden Bullet invoice
Release 4 – XRN4990
Release 5 – XRN4990
Release 6 – DN tbc

## Slide 52
Data Discovery Platform | Inflight Sprint (part of release 4)
Goals: Complete detailed design Complete source to target Build 50% data model Enable additional Shipper Pack reports to be self served via DDP Facilitate MDD vs UKLink analysis for IGTs – Stretch | 
Outcomes: Detailed Design for the XRN4990 Solution pertaining to DDP Source to target completed for XRN4990 50% of XRN4990 data model built Additional Shipper pack delivery enabling Incorrect read factor and units to be self served via DDP Additional shipper pack delivery Shipper read frequency giving shipper portfolio count by MRF and a view of the average industry % by MRF code Stretch Targets: Additional analysis of UKLink / MDD data quality Industry view of read rejections by reasons code to compare company performance against industry average | 

## Slide 53: Appendix

## Slide 54: DDP Roadmap
Key:
Themes
Deliverable

## Slide 55
Data Discovery Platform | Release 2
Goal: Enable Distribution Network Users to access a financial forecasting report (part of the golden bullet), to understand variances between formula year AQ / SOQ and rolling AQ / SOQ to understand the impact this has on revenue. | 
User Stories: As a DN I want a view of my Formula year AQ/ SOQ and Rolling AQ / SOQ simulation data grouped by: LDZ, Exit Zone, Shipper Short, EUC, Code, Charge Type, Charge Rate, Asset Type, AQ Band and Class As a DN I want total FY AQ / SOQ and Rolling AQ / SOQ displayed in kwh and as a percentage, and the difference between the two As a DN I want total charges by Rolling and Formula Year AQ / SOQ totals and difference As a DN I want the number of MPRNs grouped by charge type between Formula year AQ / SOQ and Rolling AQ /SOQ (by kwh and percentage difference) so I can see how many MPRNs fall into each group and the difference between FY and Rolling for each charge type in both kwh and percent age and split by LDZ, Exit Zone, Class, AQ band, Shipper Short Code and Asset Type Charge types: ZCA, 891, CCA, CFI, ECN, C04 As a DN I want a trend view between Formula Year and Rolling AQ and SOQ with the total charge position for both Stretch element: As a DN I want the number of MPRNs grouped by % difference between FY AQ and rolling AQ and between FY SOQ and Rolling SOQ As a DN I want the number of MPRNs grouped by kwh difference between FY AQ and Rolling AQ and FY SOQ and rolling SOQ so I can see how many MPRNs fall into each group As a DN I want to see the total number of MPRNs that have had a rate change within the last month, and have these split by reason for the rate change (Shipper change, Class change, other) so I can understand how rate changes are affecting my revenues | 

## Slide 56
Data Discovery Platform | Release 3
Goals: Complete model to enable the aggregated invoice element of the Golden Bullet Report Enable more elements of the Shipper pack to be self served | 
User Stories: Build the data model to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on aswell that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year As a Shipper I want to be able to report on Dead meters via a monthly snapshot and see a trend over 12 months, so that the dead report in the Shipper pack can be retired As a Shipper I want my read performance for class 3 sites to be displayed as 'MET' when I have achieved 90% of reads accepted so that I can monitor my read performance Analysis of the below user story; As a Shipper I want an industry view of read rejection reasons so that I can compare my performance with industry Read rejections by reason code (numbers). Existing report need enhancing to give; Read rejections by reason code percentage value for a Shipper needs to be added to current dashboard Industry average number of read rejections (number and percentage) needs adding Performance enhancement to give a greater user experience of the large volumes Stretch targets: As a Shipper I want to see a list of sites in my portfolio containing plot addresses so that I can assess and update the address details correctly & in a timely manner. As a Shipper I want the WAR Bands dashboard to be moved out of UIG area of DDP and added to the Reads area of DDP so that it sits more logically from a business process perspective | 

## Slide 57
Data Discovery Platform | Inflight Sprint (part of release 3)
Goals: Build the golden bullet invoice report Build the detailed design for the XRN4990 solution | 
User Stories: Build the dashboards to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on as well that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year Performance optimisation for read dashboards Detailed Design for the XRN4990 Solution pertaining to DDP Stretch Target: Must read enhancement to align BAU enhancement to DDP Industry view of number of MPRN associated to MRF (part of Shipper Pack XRN 5200) | 

## Slide 58: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 59: December ChMC CMS Rebuild Update

## Slide 60: Progress to Date
I am pleased to confirm that the Duplicates (DUP) and Set to Extinct Process (STE) will be going live on 12 December 2022, this is subject to a Go No Go meeting on the 7th December.
On launch date the new user emails will be issued from 09:30 to prevent email server disruption. There will be User Support sessions, which will be a daily occurrence for the first week where users can dial in and raise any questions they may have. Further information can be found on the following slide for December’s activities.
We are confirming launch dates for Q1 2023 and an update will be provided in January’s ChMC.
We will provide an update as soon as we know when the relevant REC change is due to be implemented to ensure you have as much notice as possible of the SUT / Modification 0734 process commencing (and the cessation of the current Shipper "TOG" process).
The CMS Rebuild webpages and CMS page have both been updated to reflect the Launch activities, FAQs and training materials – the latter will be completed W/C 5th December
https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild/
https://www.xoserve.com/products-services/data-products/contact-management-service-cms/
The Link to the training material is on both pages, however for reference it can be accessed using this link, please note that the training materials will be updated in the week commencing 5th December: https://rise.articulate.com/share/dgQzl3ax38sN6oVrNCenQW1RKMFHStYO#/
The CMS Rebuild webpage (https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild-product/ ) contains the link to register for future Customer Focus Groups, please note the agenda for the Focus Groups will be issued 7 days prior to the session.

## Slide 61
WC 28/11
WC 21/11
WC 14/11
WC 07/11
External – CMS Rebuild December Launch
Plan on a page
Communications
Activities
Communications
Confirmation of soft launch Go live and reminder of URLs
GONG
PIS
External UAT
Training Published
Web page – FAQs and “How - tos”
Customer Experience/ UKLink box Go live Notification
User cleansing & set up
WC 05/12
WC 12/12
WC 19/12
WC 26/12
WC 02/01
Customer Focus Group
ChMC
CoMC
ChMC
CoMC
Customer Focus Group
Connectivity testing
External UAT
User Support sessions

## Slide 62
XRN 5556.b
CMS Rebuild Delivery Roadmap
Release Content
Now
Next
Later
A little Later
Supplier Theft of Gas (SUT)
Meter Number Creation (MNC)
Duplicate MPRNs (DUP)
Set to Extinct
Isolations
(ISO)
Dead to Live
(DTL)
DUP Enhancements
Generic to desk workflows – AGG, PSI, PSR
Address Amendments (ADD/ UNC)
New MPRN Creation
(FOM)
Enhancements to MNC Process including Network
Generic to desk
workflows – GIC
Main Release
Additional Stretch Enhancements
Request for Adjustment (RFA)
Daily Metered Query (DMQ)
Consumption Dispute Query (CDQ)
Theft of Gas
(TOG)–
Network Raised
Generic to desk
workflows – FLE
Must Reads
(MUR)
Manage Unregistered Sites
(MUS)
Gas Safety Regulation
(GSR)
SUT Enhancements
Swapped Address
(SWA)
Generic Enhancements
XRN 5556.a
New Process
Early
Q1 2023
No later than end of Q3 2023
Early
Q4 2022

## Slide 63: Section 6: Any Other Business

## Slide 64: REC Update: Late Gate Closure Messages and Missing Messages ChMC – December 2022

## Slide 65: ‘Missing’ Gate Closure
First ticket was raised on 24th July, and each day that we had a missing GC message a further ticket has been raised
At 23rd November – last incidence of missing GC message was 22nd November
  Total missing messages 164 by this point (121 missing on 2nd August)
  NB: 9 now resolved following confirmation of Cancellation of Registration from Switching Operator
DCC indicated a fix has been deployed 25th August that would resolve the exceptions that were causing this issue, but noted that this would take some time to work through CSS (so to expect some additional missing messages post fix date (NB: we have recorded Missing Messages post 25th August)
We have reported 93.75% (Sub average volumes) and 80% (Average to Peak volumes) success against the REC Performance Assurance target for October of all messages being received within target each day – 4 days with missed messages
  We believe that these have all related to Supplier-less Supply Meter Points, so expect this to be a different functional issue

## Slide 66: Latest Position
Statistics as at 20th November:
  Pot 1 – ‘Pending DCC Rec’ incl. Server Shut Down – estimate that these will require Registration
  Pot 2 – Server Drift - estimate that these will require Registration
  Pot 3 – ‘New’ recent instances to be investigated with DCC
  Pot 4 ‘Supplierless’ – we believe that this is a functional issue and will require system change (and potentially REC change)
  Resolved – 9 Cancelled Registrations – removed from UKL
Note: all statistics and conclusions for ‘pots’ are subject to Reconciliation and confirmation from the Switching Operator
RCA | Count Missing SAM
PENDING | 164
Pot 1 Pending DCC REC | 31
Pot 2 Server Drift Issue | 119
Pot 3 New | 9
Pot 4 Isolated (Supplierless) | 5
RESOLVED | 9
(blank) | 
(blank) | 
Grand Total | 173

## Slide 67: CRD061
We believe that the issue of Missing Gate Closure messages would have been mitigated by ‘resend’ functionality
  DCC implemented this prior to CSS for Smart DSP
  Could not be implemented for others prior to CSS Go Live without impacting Implementation Date
We have been arguing that this is a Programme Deliverable and ELS should not be completed without this functionality being delivered
  Potentially will be progressed as a REC Urgent Change
  This is still being progressed Xoserve are reviewing the proposed solution with REC / DCC
We are performing the Impact Assessment on this change (R0067) … this will not resolve all issues with Missing Messages as some Registrations will not be at a status to permit resend

## Slide 68: 2nd August – ‘Missing Messages’
On 2nd August we identified 122 ‘Missing Messages’:
  On 15th September DCC indicated that they had identified that some of this population had different characteristics to others being investigated under this issue
  Identified that the GRDA System had rejected messages with a time related error
    Our investigations indicate that this was because the GRDA System considered the messages for a future date or time
    We expect that this is because server clock time drift between CSS and GRDA – and GRDA lagging behind CSS by as little as 0.5 second
    CSS and GRDA systems are exchanging messages in millisecond timings – therefore this drift would cause this rejection
    MS Azure clock times are guaranteed within 2 seconds – but drift is considered very unlikely
    Our investigation attributed this error incorrectly to the CSS Missing Message issue
    Fixes planned:
      To allow for drift between servers – e.g. set a +/- buffer time in the validation - Deployed
      Recording rejected messages for a short period to investigate the original message payload – we relied on the messages to be provided by Switching Operator to investigate – In progress

## Slide 69: Next Steps
This position has largely not changed from last month – we had asked DCC to focus on stopping further instances of Missing Messages:
  Need confirmation which of the Missing Gate Closure messages were intended to result in Registration or Cancellation
    We are still waiting for the Reconciliation position
  Need to understand options from DCC …
    DCC have indicated that these should be set Live, but cannot generate the Secured Active Messages to us
    We have asked DCC to provide a notification of the Registrations that need to be set Live in lieu of the Secured Active Notification – we plan to use this as a proxy Secured Active Notification
    UNCC accepted the proposed approach that we set the Registrations Live for the ‘Server Shut Down’ Issue using a proxy Secured Active Notification
  XRN5535 was raised to determine what to do if we received a message after 03:00 on D
    We are using this Change Proposal to assess what needs to be done for the ‘missing’ Registrations – we have no Retro Registration functionality so solution needs to be identified – e.g. increment Registration Effective Date and adjustment

## Slide 70: Proposed Solution
We plan to progress these changes as Prospective fixes – i.e. once we have developed and tested the functionality
We will set the ‘missed Registration’ Live prospectively for any missed messages for Switches***
  If there has been Registration subsequent to the CSS Effective Date, or another Registration is imminent (within D+[5] calendar days) – we will not process the ‘missed Registration’
Still require reconciliation from Switching Operator
We have progressed these proposals whilst we wait for confirmation of which Registrations need to be set Live
We are developing a system solution to generate the Registration in UKL in lieu of the Secure Active Notification from CSS
  This should reduce risk of manual error in the process
  Simulate the Secured Active Notification to enable UKL processes (e.g. association with Base Registration Notification) to remain as is
  *** We are looking at applying the Registration in line with CSS dates for Initial Registrations (TBC)

## Slide 71: Proposed Solution - Challenges
If there are updates to the Supply Point from the current Shipper that have yet to become effective (e.g. future dated Capacity Changes; MRF Changes; Class Changes) these will be cancelled – this is a BAU process, we will not provide any further information to the incoming (prospective) Shipper
  We expect that this is data related to the previous Shipper Supply Point so not required
  If this is required, this will give us a Data Permission challenge to make a new set available to the ‘Community’ Shipper
The UKL Registered Shipper has updated the Supply Point Register post the CSS Registration EFD – these will be retained in UKL (and will not be backed out)
  If we need to provide the information related to these updates to the incoming (prospective) Shipper, we will need to identify the type of updates that are required to be provided and make reporting available
  We have seen small numbers of accepted transactions but the type of transactions considered are:
    Meter Readings (9); AQ Corrections (1); Class Change (1) and Meter Asset Updates (1)
    Customer Contact Updates – if required, we could just flag that there has been an update, rather than content of update
  If this is needed, suggest we agree release of this data explicitly through DPM
The UKL system has rejected updates to the Supply Point Register post the CSS Registration EFD from the Prospective Incoming Shipper (i.e. CSS Registered Shipper)
  Propose that we collate the rejected information and provide to the Incoming Shipper (to assist them to determine what activities they need to resend: MAM Updates (7); SMSO Update (3); Readings (12); Meter Asset Updates (7)
  Propose we flag the Supply Meter Points where a Customer Contact Update has been rejected

## Slide 72: Proposed Solution - Challenges
Base Registration Nominations may be held in the system (these are valid for 60 days), but recommend that the Incoming Shipper generates a new BRN
  This would supersede any BRNs in UKL and reduces risk of SP having incorrect Settlement data (or CDSP associating default Settlement data)
  If not, we will use any valid (e.g. non expired) BRNs … Note: BRNs may reject for other reasons – e.g. Capacity Reduction Window
  Otherwise, we would use defaults as defined in UNC TPD G Annex G-1
Propose NOT to suppress any UKL transactions associated with the Registration
  Outgoing files will continue to be generated – e.g. BRR; ASN; TMC; URN
  Incoming transactions would be allowed – e.g. Opening Meter Reads

## Slide 73: Proposed Solution - Challenges
An Opening and Closing Meter Read will be generated for the UKL Registration Effective Date
  This will be issued to both Shippers as per BAU process
We could insert an estimated Meter Reading for the CSS Registration Date – this would be a CYCL (i.e. not an Opening Reading) but would be beneficial for Reconciliation (if required) and potential settlement between Shippers / Suppliers
  Note: if this requires replacement it would require the ‘old’ Shipper to replace (i.e. UKL Registered Shipper) and not the CSS Registered Shipper (and replacement would not lead to notification for the CSS Registered Shipper by UKL)
  Note: would not be recorded with an explicit reason
  Alternatively, Shippers / Suppliers could agree and insertion by ‘old’ Shipper?

## Slide 74: Further Considerations
Assessing Invoicing position
  Materiality is not expected to be large
  164 impacted Supply Meter Points, of which 162 are SSP (noting 9 confirmed Registration cancellations)

## Slide 75: Verbal Update presented by David Addison on the additional May 8th Bank Holiday

## Slide 76: Project 1Stop Part 2 – December Update
Megan Troth

## Slide 77: Background
The new iteration of the Xoserve website was developed in November 2018.
Since this implementation, based on customer feedback, we have been looking to identify various ways in which we can improve the change pages and the overall customer journey, particularly in relation to change (both DSC and Investment).
Project 1Stop was created in order to completely understand of our customer’s needs, alleviate their pain points, and to create an overall more positive experience when navigating through Xoserve change information.
Part 1 of this iteration was delivered at the start of this year, and we have been working through customer driven user stories to deliver Part 2 of this Project

## Slide 78: What has been delivered to date?
For part 1 of Project 1Stop, three User Stories were initially prioritised and delivered which included:
Consistent UKL Release Information across the website
An up to date and accurate change register that is simple and easy to use
Overhaul of the Change Proposal webpages with a breakdown of individual change documentation

## Slide 79: Project 1Stop part 2
We have now aimed to deliver the remaining user stories for the final iteration of this project (full details on the following slides):
As a new customer working on DSC and Investment change, I would like to be given an overview of the change process in order to give me a further understanding of how change works in Xoserve
As a customer I want to be able to provide and update industry responses before final submission so that I can ensure I seek opinion from impacted teams within my organisation and give a single rounded response

## Slide 80: New online Change Process
Roles defined in process sections e.g. seeing where you feed in as the customer
Option of high level overview of step and detailed sub-steps available to view

## Slide 81: New Change Pack Representation Features
New feature enables you to populate the form as normal, with the option ‘Save’ your representation response for later and circulate it internally among your organisation without having to repopulate the form once you are ready to submit
As per feedback received, an additional feature has also been added whereby customers will automatically receive an email copy of their final representation responses once they have submitted them.

## Slide 82: Next Steps
Changes above will be delivered in January 2023. An email communication will go out to customers once the date for implementation has been confirmed.

## Slide 83: December Change Pack close out date
Change packs are due to close out on 28th December. This will give 9 working days prior to the Christmas holidays (12th – 23rd) and 1 day during the holiday season.
Proposed Change Packs for December
  XRN4900 – This change pack has previously been approved but will contain a revision that will require approval following agreement to proceed with a change request
We are asking if the committee if they want the Change Pack consultation period extending.

## Slide 84: Appendix

## Slide 85: REC Change Appendix
7th December 2022

## Slide 86: REC Change Pipeline Electric only - Monitoring
Title | Description | Status
R0009 | Introduction of SDEP and EES User Maintenance API | These changes are specific for Electric only. We will continue to monitor should any of the Changes have a knock on impact to GES or the CDSP.
R0010 | New Meter Types for Auxiliary Proportional Controllers (APCs) | These changes are specific for Electric only. We will continue to monitor should any of the Changes have a knock on impact to GES.
R0011 | Reporting of Additional EMR Backing Data to Suppliers | 
R0017 | Invalid Requests for Site Technical Details | These changes are specific for Electric only. We will continue to monitor should any of the changes have a knock on impact to GES.
R0018 | Complex Sites process improvements | 
R0022 | Amendment to REC Data Access Matrix | 
R0026 | Whole current (WC)/Current Transformer (CT) certificates | 
R0027 | Minimum identification requirements in the Meter Operation Code of Practice | 
R0031 | Altering the Trigger Points for CT Commissioning | 
R0032 | New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS) | 
R0040 | CSS Switch Synchronisation to ERDA at SecuredActive | 
R0043 | Commissioning of Works by the Crowded Meter Room Coordinator (CMRC) to Resolve Issues In Crowded Meter Rooms | 
R0044 | MHHS Programme Changes required to Central Switching Service | 

## Slide 87: REC Change Pipeline Electric only - Monitoring
Title | Description | Status
R0053 | 24/7 Emergency Metering Service | These changes are specific for Electric only. We will continue to monitor should any of the changes have a knock on impact to GES or the CDSP.
R0054 | EES Access for Virtual Lead Parties | 
R0060 | ERDS Service Definition timezone correction | These changes are specific for Electric only. We will continue to monitor should any of the changes have a knock on impact to GES.
R0062 | Removal of ERDA meteringPointEnergyFlow change restriction | 
R0064 | Creating a Meter Operator Agent and MOCoP Installer | 
R0065 | Registration of Smart Export Guarantee (SEG) Sites | 
R0066 | Inclusion of SMRS Data Items In EES (BSC CP 1568 Consequential change) | 
R0072 | Introduction of a new Meter Asset Condition Code | 
R0076 | DNOs notifying Suppliers about Crossed Meters | 
R0077 | Resolution of EES API Search Address method discrepancies | 
R0078 | EMR Settlement Limited - additional access to ECOES | 
R0079 | Addition of Previous MEM to the EES API | 
N/A | MHHS Supply Number Consultation | 

## Slide 88: Portfolio POAP