## Slide 1: Change Management Committee
11th January 2023

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: DSC Change Budget BP22 YTD

## Slide 4: Forecasted Year End Spend (BP22)
The graph below illustrates the current forecast for financial year-end utilisation of the General Change investment budget (BP22) – this is subject to change should ChMC approve further change delivery
Committed spend has increased since last month by £156k (shipper +£11k, DNs -£168k)
Chart: Committed to date per constituency
| Shipper | DN | IGT | NTS
Committed | 1413960.59 | 674440.41 | 13455 | 0
Uncommitted | 465400.8629 | 457255.9219 | 163447.9397 | 66021.5255

## Slide 5: Change Pipeline

## Slide 6: Change Delivery Pipeline August 22 – December 23
CSSC Go-Live
February 23 - Major Release (XRN5533)
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992b, XRN5298
July 22
February 23
June 23 - Major Release (XRN5562)
XRN5091, XRN5186, XRN5482 (tbc)
November 22
June 23
November 23
XRN5515
XRN5231
XRN5469
November 23 – Major Release
No Major Release
XRN5236
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 03 January 2023
XRN5565
XRN5529
XRN5561
March 23 - AdHoc Release (XRN5575)
XRN5379, XRN5143, XRN5472
XRN5541
XRN5573A
XRN5595
XRN5555

## Slide 7: Change Pipeline - Delivery Plan - July 2022 - February 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5515 | HyDeploy Close Down | NGN | Shipper DN | DN DeCarb | N/A | 18th July 2022 | AdHoc | Delivered
5231 | FWACV Service – MOD 0793S | SGN | DN NG | DN NG | £1.198m | 1st September 22 | AdHoc | Delivered
5529 | UNC Derogation process – MOD 0800 | NGN | N/A | N/A | N/A | 1st October 22 | N/A | Delivered
5565 | CDSP as the Scheme Administrator for the Energy Price Guarantee for Domestic Gas Consumers – MOD 0824 | NGN | Shipper | Shipper | £1m – 1.5m | 1st October 22 | AdHoc | Delivered
5469 | Increase Frequency of FSG Payments | Cadent | DN | DN | £63.3k | 3rd October 22 | AdHoc | Delivered
5561 | Reform of Gas Demand Side Response (DSR) Arrangements – MOD 0822U | National Grid | NGT Shipper | NGT | N/A | 17th October 22 | AdHoc | Delivered
5236 | Reporting Valid Confirmed Theft of Gas in central systems – MOD 0734 | Gazprom | Shipper | Shipper | £74k | Oct / Nov 22 | CMS Rebuild Release 1 | Delivered (Not Live)
5541 | Amendments to the UIG Additional National Data Reporting | Scottish Power | Shipper | Shipper | N/A | 23rd December 22 | AdHoc | Delivered
4900 | Biomethane/Propane Reduction | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Firm
4989 | Online end to End Credit Interest process - Defect 1063 (Part C) | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DN | Shipper DNO | £108.7k | 25th February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm
5595 | Changes to the REC Switching Operator Outage Notification Lead Time (R0055) | Xoserve | Shipper | N/A | N/A | 25th Feb 23 | Major | Firm

## Slide 8: Change Pipeline March 2023 – June 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | 1st April 2023 | AdHoc | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | £75k | 1st April 2023 | AdHoc | Firm
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | Shipper DN | Shipper DN | £75k | 1st April 2023 | AdHoc | Firm
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | 24th June 23 | Major | Firm
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | 24th June 23 | Major | Firm
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper | £300k | June 23 (tbc) | Major | Indicative

## Slide 9
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | January 2023 | AdHoc | Indicative
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | Tbc | Tbc | N/A
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5531 | Hydrogen Village Trial | SGN | All DSC Customers | DN Decarb | Tbc | Tbc | Tbc | N/A
5535 | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | All DSC Customers | Shipper | Tbc | Tbc | Tbc | N/A
5545 | Hydrogen Trial Visualisation Dashboard | Northern Gas | All DSC Customers | DN Decarb | Tbc | Tbc | Tbc | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | Tbc | February 2023 | Tbc | N/A
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | N/A | January 2023 | Adhoc | Indicative
5567 | Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067) | Xoserve | All DSC Customers | Shipper | Tbc | Tbc | Tbc | N/A
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Tbc | Tbc | Tbc | N/A
5573 | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) – Urgent | Xoserve | All DSC Customers | Part A – N/A ------------------ Part B - Tbc | Part A – N/A ------------------ Part B - Tbc | Part A - October 2022 ------------------------------- Part B - Tbc | Part A – AdHoc ------------------------ Part B - Tbc | Part A – Firm ------------------------ Part B – N/A
5584 | Procurement of Climate Change Methodology for Demand Estimation Purposes | Xoserve | DN Shipper | DN Shipper | Tbc | Mid 2023 | AdHoc | Indicative
5585 | Flow Weighted Average Calorific Value - Phase 2 Service Improvements | Cadent | DN | DN | Tbc | Tbc | Tbc | N/A
Change Backlog Details - Continued

## Slide 10: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | *Mod0651 – Retrospective Data Update Provisions* | Cadent | Shipper DN | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
*Mod0651 : 03.01.23 - Change Status remains on hold and will be reviewed on a monthly basis with ChMC – in line with request from UNCC

## Slide 11: REC Change
January 2023

## Slide 12: Introduction
The following 3 slides have been included in this months ChMC pack to give you an overview of the ongoing REC Changes, we have broken these down into the following sections:
In progress – we are currently progressing through the Change journey
Under Prioritisation Review with Code Managers – due to workload/prioritisation
The electricity slides that have been included in previous months have now been removed from this pack, but as stated, they can still be found on the REC Portal.
Note: We are currently undertaking a review of all REC Change and have began removing Changes which we have confirmed have no impact to Gas services. In the coming months, we will continue to monitor the Changes listed and add/remove from this pack as required.
Further information on the Changes can be found on the REC Portal

## Slide 13: Overview of In progress REC Changes (high level)
Chart: 
| Approved awaiting implementation | Consultation | Solution development | Awaiting authority decision | Detailed IA/Party Impact Assessment | Final Assessment
Series 1 | 3 | 1 | 1 | 1 | 2 | 0
Notes: In progress:
Approved awaiting implementation 10,11,36
Consultation 47,52,55
Solution development 16,37
Initial assessment 25
Awaiting authority decision 21
Scoping Testing requirements 67
Detailed IA 70,74
New CR05_XoS

## Slide 14: REC Change Pipeline – In progress
Title | Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority | Attachments
R0025 | Service Provider Performance Charges (DCC) | N/A | Deloitte (RPA) | - | Awaiting Authority decision | 01/04/2023 – Proposed Implementation date | TBC | High | 
R0047 | Metering Code of Practice Consolidation Review | N/A | RECCo | - | Approved - awaiting implementation | 01/04/2023 – Proposed Implementation date | TBC | High | N/A
R0052 | GES Service Definition Document | N/A | Deloitte | GES | Approved - awaiting implementation | 24/02/2023 – Proposed Implementation date | Major | Medium | N/A
R0055 | Switching Operator Outage Notification Lead Time | XRN 5595 | DCC | GRDS, GES | Approved - awaiting implementation | 24/02/2023 – Proposed Implementation date | Major | Medium | N/A
R0063 | Addition of key information to all Service Now tickets | N/A | St Clements Ltd (on behalf of DNOs) | - | Solution development | 07/02/2023 – Solution Development closeout date | TBC | Medium | N/A
R0067 | Introduction of CSS refresh functionality | XRN 5567 | Capgemini (RTS) | GRDS | Party Impact Assessment – DIA under review with Code Managers | 16/01/2022 – Review | Standalone | High | N/A
R0070 | Provision of Enduring Test Environments | N/A | Capgemini | GES | Consultation | 16/01/2022 – Review | Standalone | High | N/A
R0074 | Release of Community View Data Items to MEMs in GES | N/A | Xoserve | GES | Party Impact Assessment – DIA under review with Code Managers | 16/01/2022 – Review | Major | High | N/A
Currently working on
Key:
Under assessment
Monitoring

## Slide 15: REC Change Pipeline – Under Prioritisation Review
Title | Description | Status
R0049 | Intellectual Property Rights and Services Data Main Body changes | Initial Assessment
R0050 | Clarification of REC Maintenance of Qualification Schedule | Withdrawn – to remove next month
R0051 | Switch Request Objections (Change of Occupier) | Initial Assessment
R0056 | EES/GES additional service request for Housing Ass to be added to the Matrix | Initial Assessment
R0059 | Maintenance of Qualification Schedule Change | Initial Assessment
R0061 | Resolution of invalid CSS data by Data Owners | Initial Assessment
R0068 | REC Data Protection Changes | Initial Assessment
R0069 | Amendments to Sample Access Agreement | Initial Assessment
R0071 | DCC access to EES and GES | Initial Assessment
R0073 | Introduction of a Housekeeping Change Proposal Process | Initial Assessment
R0075 | Enabling Software Product Qualification | Initial Assessment
R0080 | Improvements to "Failed to deliver" CSS messages | Initial Assessment
R0081 | CSS Market message retry strategy | Initial Assessment
R0082 | Formalising the Submission of PPMIP Unallocated Transaction Report (UTR) Files | Initial Assessment
R0084 | Housekeeping changes to the approved legal text for R0047 | Initial Assessment
R0085 | Switching Programme Designation of the Steady State Commencement Date | Initial Assessment
Note: Please be aware that some Changes may have progressed further since the slides in this pack were submitted

## Slide 16: Section 3: Capture

## Slide 17: New Change Proposals
For Approval
XRN5602 Releasing of unused capacity under a specific set of circumstances (Modification 0818)
XRN5604 Shipper Agreed Read (SAR) exceptions process (Modification 0811S)
XRN5605 Amendments to the must read process (IGT159V)
XRN5606 Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0813)
XRN5607 Update to the AQ correction processes (Modification 0816S)
For information
XRN5610 New Service Lines to Support the FWACV Service
XRN5556.d CMS Rebuild Version 2

## Slide 18: XRN5602 Releasing of unused capacity under a specific set of circumstances (Modification 0818)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGTs | 
DSC Service Area: | Service Area 3: Manage updates to customer portfolio
Proposed Funding split | Shipper 90% DNO 10%
Sponsor Representative | Xoserve
Change Description
This change has been raised to deliver the requirements set out under Modification 0818. This Modification has been raised to release unused capacity (only where an SMP meets a specific criteria). This will implement a process to deliver the Mod 0818 requirements involving: - A DNO can request that a Shipper reduces a SMPs capacity if the SMP meets a strict criteria and is on an area of the network with restricted capacity available to other Registered Users / end consumers. - The relevant Shipper of the SMP will have the opportunity to appeal the reduction in capacity. - If following the appeal process, a capacity reduction is still required, the Shipper should submit a Supply Point Amendment to reduce the capacity from 01 October in the relevant year. - If the relevant Shipper does not submit a successful Supply Point Amendment to reduce the capacity to the DNO agreed values by 31 October, the CDSP will reduce the capacity on their behalf. Link to CP
Change Type | Regulatory
Priority Score | High

## Slide 19: XRN5604 Shipper Agreed Read (SAR) exceptions process (Modification 0811S)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGTs | 
DSC Service Area: | Service Area 1 Manage Shipper Transfers
Proposed Funding split | Shipper 100%
Sponsor Representative | Xoserve
Change Description
This change has been raised in to deliver the requirements set out under UNC Modification 0811S, in order to provide a remedy for SARs that have failed to be progressed (exceptions) within a reasonable period, to be proactively managed by the Central Data Services Provider (CDSP). Both Shippers should attempt to amend the transfer read in line with the SAR within 2 months after it was agreed. Currently only the Proposing User can submit the SAR to the CDSP. If this has not occurred, then under this change, the CDSP can be contacted for support and ensure the new agreed read is recorded centrally. When the CDSP needs to be contacted for support, the Shipper should provide them with suitable evidence of the new agreed read. The CDSP will then notify the other Shipper of the new agreed read and will, in the absence of any relevant rejection, process the new agreed read centrally. Link to CP
Change Type | Regulatory
Priority Score | High

## Slide 20: XRN5605 Amendments to the must read process (IGT159V)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGTs | X
DSC Service Area: | Service Area 4 Meter Read/Asset processing Service Area 22 Specific Services
Proposed Funding split | Shipper 90% IGT 10% (This is the proposed funding split for the implementation of the change)
Sponsor Representative | Xoserve
Change Description
This Change Proposal has been raised to deliver the requirements set out under IGT UNC Modification 159V – Amendments to the must read process. This Modification was raised to update the IGT must read process to include timescales for a site to enter the process and to introduce timeframes for procuring and returning a read that align with read validation. For further information please see the Change Proposal. Link to CP
Change Type | Regulatory
Priority Score | High

## Slide 21: XRN5606 Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0813)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | 
National Grid Transmission | X
IGTs | 
DSC Service Area: | Service Area 8 Energy Balancing (Credit Risk Management)
Proposed Funding split | NGT 100% (Expected to be zero cost)
Sponsor Representative | Xoserve
Change Description
This change has been raised to deliver the requirements set out under UNC Modification 0813 Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers. This Modification has been raised to allow the utilisation of Revision of Virtual Last Resort User (‘VLRU’) and Contingent Procurement of Supplier Demand (‘CPSD’) mechanisms where a User is subject to UK Government sanctions. Link to CP
Change Type | Regulatory
Priority Score | High

## Slide 22: XRN5607 Update to the AQ correction processes (Modification 0816S)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGTs | X
DSC Service Area: | Service Area 2 Monthly AQ Processes
Proposed Funding split | Shipper 100%
Sponsor Representative | Xoserve
Change Description
This Change Proposal has been raised to deliver the requirements set out under UNC Modification 0816 - Update to AQ correction processes. This Modification proposes to add two further ‘eligible causes’ to the Annual Quantity (AQ) amendment process within TPD G2.3.21 and to prevent AQ amendments being processed where there is no change in value to the AQ. Link to CP
Change Type | Regulatory
Priority Score | High

## Slide 23: XRN5610 New Service Lines to Support the FWACV Service
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGT’s | 
For information only. To be presented at CoMC on 18/01/2023 for approval. | 
DSC Service Area: | N/A
Proposed Funding split | N/A
Sponsor Representative | Xoserve
Change Description
This Change Proposal is to seek approval for the introduction of five new Service Lines which have been introduced to support the Flow Weighted Average Calorific Value (FWACV) service which was successfully implemented on 1st September 2022. Please note that 4 of the Service lines are to be included in Service Area 17 -Distribution Network Funded Service Activities which was approved as a new service area by CoMC on 14th December 2022 and it will become effective from 1st April 2023. Link to CP
Change Type | Documentation Change
Priority Score | N/A

## Slide 24: XRN5556.d CMS Rebuild Version 2
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | 
National Grid Transmission | 
IGTs | 
N/A – For information | 
DSC Service Area: | N/A CMS Investment funded
Proposed Funding split | N/A
Sponsor Representative | Xoserve
Change Description
The current CMS system is dated and at end of life support. New customer classes have joined the market but the workflows have not been updated to cater fully for the new customers or improved for existing customers. Therefore customers required a newly built solution. This is an agile delivery and so contact codes will be delivered incrementally to ensure that customers receive benefits as soon as practically possible. This XRN will be a child XRN to 5556 and covers the Isolations (ISO) and Dead to Live (DTL) processes with minor enhancements to the UI of the new system. Link to CP
Change Type | Non-Regulatory
Priority Score | N/A

## Slide 25: section 4. Design & Delivery

## Slide 26: Design Change Pack
For approval
XRN5555 Amend Existing Large Load Site Reporting
For information
XRN4900 Biomethane Sites with Reduced Propane Injection
Notice of additional Non-Business Day and Non-Supply Point System Business Day for 8th May 2023 bank holiday for the coronation of King Charles III

## Slide 27: XRN5555 Amend Existing Large Load Site Reporting
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Impacted | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  |  | Approve | Defer | Reject
3120.1 - VO - PO | Service Area 9 - Customer Reporting (all forms) Split: DNO and IGT 59%, Shipper 34% , NGT 7% | DNO | DNO | Adhoc | Link to CP | 1 |  | 
Org | Status | Comments
SGN | Support | Support - As proposer of this change SGN supports the changes to the existing DN Large Loads Report.

## Slide 28: XRN4900 Biomethane Sites with Reduced Propane Injection
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Impacted | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  |  | Approve | Defer | Reject
3120.2 - VO - PO | Decarb Investment | N/A - For information | Shipper DNO | February 23 | Link to CP |  |  | 
Org | Status | Comments
 |  | For information – No representations received.

## Slide 29: Notice of additional Non-Business Day and Non-Supply Point System Business Day for 8th May 2023 bank holiday for the coronation of King Charles III
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Impacted | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  |  | Approve | Defer | Reject
3120.3 - VO - PO | N/A For information | N/A For information | All Parties | Following presentation at ChMC | N/A |  |  | 
Org | Status | Comments
 |  | For information – No representations received.

## Slide 30: Standalone Change Documents for Approval (BER, CCR, EQR)

## Slide 31: Standalone Change Documents for Approval (BER, CCR, EQR)
BER for XRN5567 Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067)
  Voting Shippers
CCR for XRN5541 - Amendment to the UIG Additional National Data Reporting
  Voting Shippers

## Slide 32: February 2023 Major Release

## Slide 33: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, UK Link user testing phase completed on 08/12 as per plan. Currently on track to complete regression testing phase 19/01 Progress update: User acceptance testing complete on 08/12 Regression testing in progress, on track to complete on 19/01 DDP build for XRN4990 in progress, delivery on track to complete by 20/01 DDP testing for XRN4990 in progress, on track to complete by 21/02 Decision in January ChMC: None |  | Implementation date of 25th February; with a contingency implementation date of 4th March | 
Risks and Issues | There is a risk that the solution being delivered under XRN5298 may not work as expected at the point SGN go live with the H100 project. Due to a significant gap between XRN5298 being delivered as part of the Feb 23 release, and the date at which the H100 project itself is scheduled to go live Update – SGN have confirmed that Q4 2024 is when the first H100 connections will go live. Discussions underway regarding options for carrying out additional regression testing closer to the H100 go live |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0797 - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 20th December 2022
Complete
On Track
At Risk
Overdue

## Slide 34: March 2023 Adhoc Release

## Slide 35: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking at risk; Amber, Design phase continues for all three XRNs scoped for this release. Build commenced as planned from 28th November for 5379 and 5472 but this is at risk due to status of design. Return to green is completion of design as planned and approved detailed project plan for delivery including touch-points with DM and NDM service providers. Progress update: Build continues as planned for 5379 and 5472, build for 5143 due to commence in January 2023 Workshops to aide understanding of the changes, in lieu of design completion have completed for 5379 and 5472 Engagement with DM service provider continues for 5379 including resolving of design queries Project in startup and initiation phase including development of detailed project plan and project artefacts Decision in December ChMC: None |  | Implementation date of 25th March with a go-live of 1st April, the contingency implementation date is 1st April with a go-live of 1st April | 
Risks and Issues | 68488 & 68489: (R) The design has not yet completed for the changes in this release, therefore the aspirational build timescales are at risk 68126: (R) The NDM service provider (SP) is not yet agreed, until the NDM SP is engaged, and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April 68498: (R) The DM SP is agreed, but not yet fully engaged, until the DM SP is engaged, and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April 68501: (I) Build of March-23 will commence before detailed design is complete |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) XRN5472 - Creation of a UK Link API to consume daily weather data for Demand Estimation processes |  |  | 
Slide updated on 20th December 2022
Complete
On Track
At Risk
Overdue

## Slide 36: June 2023 Major Release

## Slide 37: XRN5562 – June 23 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking Amber, Start up and initiation phase is in progress. Build commenced on 28th November and is in progress. ​Progress update:​ Start Up and Initiation phase is currently in progress all documents being produced including the detailed project plan that underpins the high-level timeline Build phase commenced on 28th December on track for completion 10/02/23 System Testing scenarios review in progress, approval expected 06/01/23 Return to Green: Approved detailed project plan expected 30th December Decision in January ChMC: None |  | Implementation date of 24th June; with a contingency implementation date of 1st July | 
Risks and Issues | None to raise |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5091 - Deferral of creation of Class change reads at transfer of ownership XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  |  | 
Slide updated on 20/12/2022
Complete
On Track
At Risk
Overdue

## Slide 38: XRN5231 Provision of a FWACV Service

## Slide 39: XRN5231 Flow Weighted Average CV
January 2023 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is tracking at Green as the FWACV service went live 1st September and monitoring and tracking of the service will continue for the remainder of PIS. Cutover and Transition plan presented to Project Focus Group on 12th July BER was approved at Change Management Committee on 13th July, CCP was signed the 19th July Successfully delivered the awareness session to DN’s, positive feedback was obtained all round 27th July Dual Run/ Market Trials completed on 11th August Updated Design Change Pack Baselined and new version published to project stakeholders 17th August FWACV service went live on 1st September PIS commenced on the 1st September and till 28th October Completed handover to BAU 28th October FWACV passed stage Gate E 15th December Next Steps: Complete closedown activities | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  |  | 
Risks and Issues | N/a | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Forecasting costs within approved spend | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change parts A & B - A - PRCMS validation/processing & Part B - LDZ Stock Change and Embedded LDZ Unique Sites | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 

## Slide 40: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS DEC 2022 – NOV 2024
DECEMBER 2022

## Slide 41
Programmes & Projects 2022-2024 |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
MAJOR RELEASES | Regulatory / Customer Requested Change | XRN5455 Autumn Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain Yr 1 | XRN5368 Gemini Change Programme Sustain Yr1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain + | CP5564 Gemini Change Programme Sustain + |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Regulatory / Customer Requested Change | XRN5579 Gemini Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS 2022 – 2024
Closedown
in Progress
Oct 22
to
Jan 23
Design to PIS Oct 22 to Oct 24 Dec
Closedown
in Progress
Nov 22
to
Jan 23
Closedown
in Progress
Oct 22
to
Jan 23
Jan 23 to Mar 23
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.

## Slide 42: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 43: CMS Rebuild Update

## Slide 44: Progress to Date
I am pleased to confirm that the Duplicates (DUP) and Set to Extinct Process (STE) was successfully launched on 12 December 2022, with an immediate uptake on users raising the new contact codes. In the first 24 hours 73 DUPs and STEs were raised.
Multiple training and walk through sessions have been facilitated and positive feedback has been received from users, mostly commenting on the ease of the system and simplified process.
Our next version will be under the XRN of 5556.D and it will contain the Isolations (ISO) and Dead to Lives (DTL) ISOs and DTLs, we are targeting a launch date of Late Feb / Early March, this will be firmed up over the next month. The Change Pack for these processes will be issued in time for Feb ChMC.
The CMS Rebuild webpages and CMS page continue to be updated to reflect the Launch activities, FAQs and training materials:
  https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild/
  https://www.xoserve.com/products-services/data-products/contact-management-service-cms/
The CMS Rebuild webpage (https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild/) contains the link to register for future Customer Focus Groups which are captured below, please note the agenda for the Focus Groups will be issued 7 days prior to the session.

## Slide 45
XRN 5556.b
CMS Rebuild Delivery Roadmap
Release Content
Now
Next
Later
A little Later
Supplier Theft of Gas (SUT)
Meter Number Creation (MNC)
Duplicate MPRNs (DUP)
Set to Extinct
Isolations
(ISO)
Dead to Live
(DTL)
DUP Enhancements
Generic to desk workflows – AGG, PSI, PSR
Address Amendments (ADD/ UNC)
New MPRN Creation
(FOM)
Enhancements to MNC Process including Network
Generic to desk
workflows – GIC
Main Release
Additional Stretch Enhancements
Request for Adjustment (RFA)
Daily Metered Query (DMQ)
Consumption Dispute Query (CDQ)
Theft of Gas
(TOG)–
Network Raised
Generic to desk
workflows – FLE
Must Reads
(MUR)
Manage Unregistered Sites
(MUS)
Gas Safety Regulation
(GSR)
SUT Enhancements
Swapped Address
(SWA)
Generic Enhancements
XRN 5556.a
New Process
Early
Q1 2023
No later than end of Q3 2023
Early
Q4 2022

## Slide 46: Section 6: AnY Other Business

## Slide 47: Appendix

## Slide 48: Portfolio POAP