## Slide 1: Change Management Committee
November 2022

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: General Change Budget BP22 YTD

## Slide 4: Forecasted Year End Spend (BP22)
The graph below illustrates the current forecast for financial year-end utilisation of the General Change investment budget (BP22) – this is subject to change should ChMC approve further change delivery
Committed spend has increased since last month by £67k (shipper £37.5k, DNs £29.5k)
Link to Change Budget
Chart: Committed to date per constituency
| Shipper | DN | IGT | NTS
Committed | 1425449 | 506440 | 13455 | 0
Uncommitted | 453912.4529 | 625256.3319 | 163447.9397 | 66021.5255

## Slide 5: Change Pipeline

## Slide 6: Change Delivery Pipeline August 22 – December 23
CSSC Go-Live
February 23 - Major Release (XRN5533)
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992b, XRN5298
July 22
February 23
June 23 - Major Release (XRN5562)
XRN5091, XRN5186, XRN5482 (tbc)
November 22
June 23
November 23
XRN5515
XRN5231
XRN5469
November 23 – Major Release
No Major Release
XRN5236
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 28 October 2022
XRN5565
XRN5529
XRN5561
March 23 - AdHoc Release (XRN5575)
XRN5370, XRN5143, XRN5472

## Slide 7: Change Pipeline Delivery Plan - July 2022 - February 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5515 | HyDeploy Close Down | NGN | Shipper DN | DN DeCarb | N/A | 18th July 2022 | AdHoc | Delivered
5231 | FWACV Service – MOD 0793S | SGN | DN NG | DN NG | £1.198m | 1st September 22 | AdHoc | Delivered
5529 | UNC Derogation process – MOD 0800 | NGN | N/A | N/A | N/A | 1st October 22 | N/A | Delivered
5565 | CDSP as the Scheme Administrator for the Energy Price Guarantee for Domestic Gas Consumers – MOD 0824 | NGN | Shipper | Shipper | £1m – 1.5m | 1st October 22 | AdHoc | Delivered
5469 | Increase Frequency of FSG Payments | Cadent | DN | DN | £63.3k | 3rd October 22 | AdHoc | Delivered
5561 | Reform of Gas Demand Side Response (DSR) Arrangements – MOD 0822U | National Grid | NGT Shipper | NGT | N/A | 17th October 22 | AdHoc | Delivered
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | November 22 | AdHoc | Indicative
5236 | Reporting Valid Confirmed Theft of Gas in central systems – MOD 0734 | Gazprom | Shipper | Shipper | £74k | Oct / Nov 22 | CMS Rebuild Release 1 | Delivered (Not Live)
4900 | Biomethane/Propane Reduction | SGN | Shipper DNO | DN Decarb | N/A | 25th February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Firm
4989 | Residual AMT activities | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DNO | Shipper DNO | £108.7k | 25th February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm

## Slide 8: Change Pipeline March 2023 – June 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | March 23 | AdHoc | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | £75k | March 23 | AdHoc | Firm
5472 | Creation of a UK Link API to consume daily weather data for Demand Estimation | CDSP | Shipper DN | Shipper DN | £75k | March 23 | AdHoc | Firm
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | June 23 | Major | Indicative
5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | June 23 | Major | Indicative
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper | Tbc | June 23 (tbc) | Major | Indicative

## Slide 9: Change Backlog Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | *Mod0651 – Retrospective Data Update Provisions* | Cadent | Shipper | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5517 | Hydrogen Checker Website | Cadent | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
*Mod0651 : Change Status currently on hold and will be reviewed on a monthly basis with ChMC – in line with request from UNCC

## Slide 10
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5531 | Hydrogen Village Trial | SGN | DN IGT Shipper NGT | DN Decarb | Tbc | Tbc | Tbc | N/A
5535 | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | DN IGT Shipper NGT | Shipper | Tbc | Tbc | Tbc | N/A
5541 | Amendments to the UIG Additional National Data Reporting | Scottish Power | Shipper | Shipper | N/A | Tbc | AdHoc | N/A
5545 | Hydrogen Trial Visualisation Dashboard | Northern Gas | DN IGT NGT Shipper | DN Decarb | Tbc | Tbc | Tbc | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | Tbc | February 2023 | Tbc | N/A
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | Tbc | Tbc | Tbc | N/A
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Tbc | Tbc | Tbc | N/A
5573 | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) – Urgent | Xoserve | DN IGT NGT Shipper | Part A – N/A ------------------ Part B - Tbc | Part A – N/A ------------------ Part B - Tbc | Part A - October 2022 ------------------------------- Part B - Tbc | Part A – AdHoc ------------------------ Part B - Tbc | Part A – Firm ------------------------ Part B – N/A
Change Backlog Details - Continued

## Slide 11: Section 3: Capture

## Slide 12: New Change Proposals
For Approval
XRN5584 Procurement of a Climate Change Methodology for Demand Estimation Purposes
XRN5585 Flow Weighted Calorific Value - Phase 2 Service Improvements
For Information
XRN5575 March 23 Adhoc Release
XRN5581 Amendments to v26 of the Service Description Table

## Slide 13: XRN5584 Procurement of a Climate Change Methodology for Demand Estimation Purposes
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | 
DSC Service Area: | Service Area 5 – Demand Estimation Obligations
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
Procurement of a new Climate Change Methodology which enables CDSP to gain the following capabilities; Capability to reflect climate change information more accurately into the derivation of Seasonal Normal Basis – allowing for a more reflected dataset to be used in a host of downstream processes. These processes include but are not limited to the following; NDM Allocation Peak Day demand estimation Annual Quantity processes Reconciliation
Change Type | Non-Regulatory
Priority Score | Medium

## Slide 14: XRN5585 Flow Weighted Calorific Value - Phase 2 Service Improvements
Customer Class | Voting Party?
Shipper | 
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | 
DSC Service Area: | TBC
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
Following successful implementation of XRN5231 – Provision of a FWACV Service, the CDSP now operates the calculation of Local Distribution Zone (LDZ) average Calorific Values, which are utilised in several industry processes. To ensure the Service could be delivered to the necessary timescales, a number of Distribution Network requirements and process improvement opportunities which were identified during the delivery phase were agreed to be deferred until a later date. These requirements and process improvement will enable the service to be operated in a more efficient and effective manner, from a CDSP perspective and in turn will improve the interactions that Distribution Network operational teams manage.
Change Type | Non-Regulatory
Priority Score | Medium

## Slide 15: XRN5575 March 23 Adhoc Release
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
For information only | 
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
A parent XRN is required for March 23 Adhoc Release There are 3 changes within this release XRN5143 Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 DM Class 1 Read Service XRN5472 Creation of a UK Link API to consume daily weather data for Demand Estimation
Change Type | N/A
Priority Score | N/A

## Slide 16: XRN5581 Amendments to v26 of the Service Description Table
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
For information and will be presented to CoMC for approval on 16/11/22 | 
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Sponsor Representative | Xoserve
Change Description
The Service lines as listed in the CP have been updated to add clarity following and internal review and in consultation with the relevant Customer Group via industry meetings. A new Service line has been created as a result of the introduction of urgent Modification 0822 Reform of Gas Demand Side Response (DSR) Arrangements.
Change Type | Documentation Change
Priority Score | N/A

## Slide 17: section 4. Design & Delivery

## Slide 18: Design Change Pack
  For Approval
  XRN4900 Biomethane Sites with Reduced Propane Injection
  XRN5541 Amendment to the UIG Additional National Data Reporting
  XRN5556B Contact Management Service (CMS) Rebuild Version 1.1
  XRN5556C Contact Management Service (CMS) Rebuild Version 1.2
  Query Management Standards of Service reporting related to MOD566
  XRN5379 Class 1 Read Service Procurement Exercise - MOD 0710
  For Awareness
  XRN5561 Reform of Gas Demand Side Response (DSR) Arrangements (Urgent Modification 0822)

## Slide 19: XRN4900 Biomethane Sites with Reduced Propane Injection
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3098.1 - RT - PO | Decarb Investment | DNO | February 23 | Link to CP | 2 |  | 
Org | Status | Comments
W&W | Approve | WWU supports this change.
SSE | Approve | No additional comments

## Slide 20: XRN5541 Amendment to the UIG Additional National Data Reporting
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3098.2 - RT - PO | Service Area 9:Customer Reporting Split: Shipper 34%, NTS 7% & DNO/IGT 59% | Shipper, NTS, DNO & IGT | Adhoc – date tbc | Link to CP | 2 |  | 
Org | Status | Comments
Scottish Power | Approve | We approve the general approach of the solution i.e. a new tab within the existing report containing the sub EUC breakdown. However, would it be possible for the totals for EUC bands 3-9 to also be included for each class in that new tab?
SSE | Approve | No additional comments

## Slide 21: XRN5556B Contact Management Service (CMS) Rebuild Version 1.1
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3098.3 - RT - PO | CMS Investment funded | Shipper, DNO, IGT, NTS | Adhoc proposed 12th December | Link to CP | 2 |  | 
Org | Status | Comments
W&W | Approve | WWU supports this change.
SSE | Approve | No additional comments

## Slide 22: XRN5556C Contact Management Service (CMS) Rebuild Version 1.2
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3098.4 - RT - PO | CMS Investment funded | Shipper, DNO, IGT, NTS | Adhoc date tbc | Link to CP | 1 |  | 
Org | Status | Comments
SSE | Approve | No additional comments

## Slide 23: Query Management Standards of Service reporting related to MOD566
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3098.5 - RT - PO | CMS Investment funded | Shipper, DNO, IGT, NTS | Adhoc date tbc | Link to CP | 1 |  | 
Org | Status | Comments
SSE | Approve | Support. We do not utilise the SoS QM reporting and so support not replicating this in the new CMS rebuild.

## Slide 24: XRN5379 Class 1 Read Service Procurement Exercise - MOD 0710
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3098.7 - RT - PO | New service lines to be created – Multiple Service Areas impacted | Shipper, DNO, IGT, NTS | March 23 Adhoc Release | Link to CP |  |  | 
Org | Status | Comments
W&W | Approve | WWU supports this change.
SSE | Approve | No additional comments
This vote is for design only; funding to be determined under Section 4 BER approval

## Slide 25: XRN5561 Reform of Gas Demand Side Response (DSR) Arrangements (Urgent Modification 0822)
Detailed Design Consultation Summary
Change Pack Ref | Funding | Voting | Release | Link to CP | Representation Summary |  | 
 |  |  |  |  | Approve | Defer | Reject
3098.6 - RT - PO | Service Area 8 Energy Balancing (Credit Risk Management) Split:100% NTS | N/A – For Awareness | Adhoc 17/10/22 | Link to CP | 2 |  | 
Org | Status | Comments
W&W | Approve | WWU supports this change.
SSE | Approve | No additional comments

## Slide 26: Standalone Change Documents for Approval (BER, CCR, EQR)

## Slide 27: Standalone Change Documents for Approval (BER, CCR, EQR)
BER for XRN5564 Gemini Sustain Plus Programme
  Voting NTS
BER for XRN5561 Reform of Gas Demand Side Response (DSR) Arrangements (Urgent Modification 0822)
  Voting NTS & Shippers
CCR for XRN5561 Reform of Gas Demand Side Response (DSR) Arrangements (Urgent Modification 0822)
  Voting NTS & Shippers
CCR for XRN5463 Technical Debt reduction- Prime and Sub process enhancement
  Voting Shipper & DNO
CCR for XRN5464 Technical Debt reduction- Enhancement to asset exchange process for Class 1 and 2 Meter Points
  Voting Shipper & DNO

## Slide 28: Standalone Change Documents for Approval (BER, CCR, EQR)
BER for XRN5575 March 23 Adhoc Release
  Voting Shipper & DNO
BER for XRN5562 June 23 Major Release
  Voting Shipper & DNO

## Slide 29: February 2023 Major Release

## Slide 30: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, UK Link build phase completed on 30/09 as per plan. Currently on track to complete system testing phase 28/10, with UAT testing prep in progress and execution commencing on 02/11 Progress update: UK Link build completed on 30/09 DDP build for XRN4990 in progress, delivery on track to complete by 20/01 System Testing on track to complete 28/10 User Acceptance Testing (UAT) preparation in progress, test case execution to commence on 02/11 Decision in October ChMC: None |  |  | 
Risks and Issues | XRN5298: There is a risk that UNC Modification 0799 will not be approved, leading to delays in build activities or a need to rework the proposed solution being delivered under XRN5298 in its entirety. While ChMC approved the move to deliver this change at risk under the assumption that the MOD will be approved, any potential regret spend associated with this change should this not be the case increases as build activities continue to progress. Update - SGN confirmed that Ofgem are due to provide an update on the status of the Modification w/c 24/10/22. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0687 - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process - Inner for replacement reads and read insertions​ XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 27th October 2022
Complete
On Track
At Risk
Overdue

## Slide 31: XRN5231 Provision of a FWACV Service

## Slide 32: XRN5231 Flow Weighted Average CV
November 2022 ChMC Dashboard |  | Overall Project RAG Status |  |  | 
 |  | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  |  | 
Status Justification |  |  |  |  | 
Schedule | Overall RAG status is tracking at Green as the FWACV service went live 1st September and monitoring and tracking of the service will continue for the remainder of PIS. Cutover and Transition plan presented to Project Focus Group on 12th July BER was approved at Change Management Committee on 13th July, CCP was signed the 19th July Successfully delivered the awareness session to DN’s, positive feedback was obtained all round 27th July Dual Run/ Market Trials completed on 11th August Updated Design Change Pack Baselined and new version published to project stakeholders 17th August FWACV service went live on 1st September PIS commenced on the 1st September and till 28th October Next Steps: Complete Handover to BAU 28th October Commence Closedown activities and documentation | Overall RAG status is tracking at Purple as project is now in re-planning phase due to the position that we will not be able to implement by 1st April 22. The project has continued with its planned activities alongside the replan. To support the re-plan activity the project is conducting a Gap Analysis exercise on the defined requirements to ensure we have a baselined position for Day 1 Implementation. An Impact Assessment will then be conducted against the change variations to support the re-plan activity UAT execution and assurance is in progress, revised completion date to be confirmed as part of re-plan Dual Run Preparation continues with Connectivity Testing and Master Data Readiness. Resolution of the Master Data Issue is a significant step forward to support Dual Run Testing and Data Migration approach for cutover Re-planning to be completed post completion of Gap Analysis activity with the intention to agree revised plan in March and present updated BER for approval at April ChMC Next Steps: Finalise Gap Analysis exercise with DNs and National Grid to agree Day 1 Must Have requirements & any decisions in order to meet a proposed Go Live date (Mid June 22) Define full re-plan based on Gap Analysis Impact Assessment and Business Readiness requirements Target to issue revised BER from replan for approval at the April 22 ChMC Risk of FWACV Imp to CSSC is in assessment, this is deemed low risk as there is no code conflict |  |  | 
Risks and Issues | There was an issue on the 19th October when an incorrect value was uploaded into UKLink impacting the CV for 100 sites. After investigation this was found to be process issue in which a CV of 28.1 instead of 38 was uploaded into UKLink and used for the FWACV calculation impacting 100 sites. There have been actions taken by the DN to ensure that incorrect values are not sent via email templates in the future, a lesson learnt/future requirement to put restrictions on the values UKLink will accept for FWACV and offline adjustments will be made for the impacted sites. The communication XCE1984 was sent out by the customer experience team and can be referred to for further information. | The dependencies for NG to provide Master data and DNs connectivity details for Dual Run/MT have not been provided as per the plan defined in the approach leading to a delay to this phase of testing Update: A plan was defined to mitigate this issue through validating and cross-checking data with National Grid and Distribution Networks (DNs). Plan is nearing completion with final checks now being completed by DNs. Issue to be closed once Data loaded to testing environment The Project is not able to meet its planned Implementation Date of 1st April due to delays to the start of Dual Run, volume of parallel activity required prior to the planned implementation and identification of gaps in the As Is and To Be processes that could lead to further changes to approved solution Update: The project is carrying out a re-plan activity with the priority being to complete Analysis on approved scope/processes to confirm Day 1 must have requirements. The plan and activities has been agreed with Xoserve, NG and DNs on 22/02 and the activities are tracking to plan |  |  | 
Cost | Forecasting costs within approved spend | Forecast costs tracking to approved BER costs at present. Revised plan options will require a full cost assessment to be completed on the replan position for Day 1 |  |  | 
Scope | XRN5231 Flow Weighted Average (CV) Gemini consequential change parts A & B - A - PRCMS validation/processing & Part B - LDZ Stock Change and Embedded LDZ Unique Sites | XRN5231 Flow Weighted Average (CV) Gemini consequential change part A - PRCMS validation/processing Gemini consequential change part B - LDZ Stock Change and Embedded LDZ Unique Sites |  |  | 

## Slide 33: XRN4914 (Modification 0651) Retrospective Data Update Provisions
It was agreed by UNCC members that it would be pragmatic to hold off on any further development for XRN4914 Retrospective Data Update Provisions until Modification 0825 (raised to remove the remaining RAASP elements) has gone through the development (Mod) process.
UNCC were very keen to not set a precedent that an Ofgem approved Modification would be delayed because another Modification was raised to remove it, but they were satisfied this was a unique situation and being pragmatic was the sensible approach.
To ensure XRN4914 doesn’t ‘drop off the radar’, it was requested that it remains on the agenda for ChMC for the duration of Mod 0825 development.
Xoserve to sign post that XRN4914 is on hold during Section 2 Change Pipeline

## Slide 34: NG TRANSMISSION CHANGE HORIZON PLAN

## Slide 35
Programmes & Projects 2022-2024 |  |  | 2022 |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
MAJOR RELEASES | Regulatory / Customer Requested Change | XRN5455 Autumn Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain Yr 1 | XRN5368 Gemini Change Programme Sustain Yr1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain + | CP5564 Gemini Change Programme Sustain + |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS 2022 – 2024
Closedown
in Progress
Oct 22 to Jan 23
Design to PIS
Apr 22
to
Nov 22
Functionality Parameterised
Ofgem Decision
23rd Dec
Design to PIS
Oct 22 to Oct 24
Closedown
in Progress
Oct 22 to Jan 23
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.

## Slide 36: DDP November CHMC update

## Slide 37: Agenda
Roadmap update
Latest Sprint update
Appendix
3.A Customer priorities
3.B Previous release updates

## Slide 38
Roadmap
PRODUCT DEVELOPMENT AND ROLLOUT
2022
04
05
06
07
08
09
10
11
12
01
02
03
04
05
06
07
08
09
10
11
12
01
02
2023
2024
Release 1 – Shipper Pack
03
ACTIVITY
Change freeze
Issue – (Requires escalation/support)
At risk - (Risk is being managed)
On track
KEY
Complete
Milestone
Release 2 – Golden Bullet forecast & IGT MDD data analysis
Release 3 – Golden Bullet invoice
Release 4 – XRN4990
Release 5 – XRN4990
Release 6 – tbc
Ti

## Slide 39
Data Discovery Platform | Inflight Sprint (part of release 4)
Goals: Complete detailed design Complete source to target Build 50% data model Enable additional Shipper Pack reports to be self served via DDP Facilitate MDD vs UKLink analysis for IGTs – Stretch | 
Outcomes: Detailed Design for the XRN4990 Solution pertaining to DDP Source to target completed for XRN4990 50% of XRN4990 data model built Additional Shipper pack delivery enabling Incorrect read factor and units to be self served via DDP Additional shipper pack delivery Shipper read frequency giving shipper portfolio count by MRF and a view of the average industry % by MRF code Stretch Targets: Additional analysis of UKLink / MDD data quality Industry view of read rejections by reasons code to compare company performance against industry average | 

## Slide 40: DDP Appendix

## Slide 41: DDP Roadmap
Key:
Themes
Deliverable

## Slide 42
Data Discovery Platform | Release 2
Goal: Enable Distribution Network Users to access a financial forecasting report (part of the golden bullet), to understand variances between formula year AQ / SOQ and rolling AQ / SOQ to understand the impact this has on revenue. | 
User Stories: As a DN I want a view of my Formula year AQ/ SOQ and Rolling AQ / SOQ simulation data grouped by: LDZ, Exit Zone, Shipper Short, EUC, Code, Charge Type, Charge Rate, Asset Type, AQ Band and Class As a DN I want total FY AQ / SOQ and Rolling AQ / SOQ displayed in kwh and as a percentage, and the difference between the two As a DN I want total charges by Rolling and Formula Year AQ / SOQ totals and difference As a DN I want the number of MPRNs grouped by charge type between Formula year AQ / SOQ and Rolling AQ /SOQ (by kwh and percentage difference) so I can see how many MPRNs fall into each group and the difference between FY and Rolling for each charge type in both kwh and percent age and split by LDZ, Exit Zone, Class, AQ band, Shipper Short Code and Asset Type Charge types: ZCA, 891, CCA, CFI, ECN, C04 As a DN I want a trend view between Formula Year and Rolling AQ and SOQ with the total charge position for both Stretch element: As a DN I want the number of MPRNs grouped by % difference between FY AQ and rolling AQ and between FY SOQ and Rolling SOQ As a DN I want the number of MPRNs grouped by kwh difference between FY AQ and Rolling AQ and FY SOQ and rolling SOQ so I can see how many MPRNs fall into each group As a DN I want to see the total number of MPRNs that have had a rate change within the last month, and have these split by reason for the rate change (Shipper change, Class change, other) so I can understand how rate changes are affecting my revenues | 

## Slide 43
Data Discovery Platform | Release 3
Goals: Complete model to enable the aggregated invoice element of the Golden Bullet Report Enable more elements of the Shipper pack to be self served | 
User Stories: Build the data model to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on aswell that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year As a Shipper I want to be able to report on Dead meters via a monthly snapshot and see a trend over 12 months, so that the dead report in the Shipper pack can be retired As a Shipper I want my read performance for class 3 sites to be displayed as 'MET' when I have achieved 90% of reads accepted so that I can monitor my read performance Analysis of the below user story; As a Shipper I want an industry view of read rejection reasons so that I can compare my performance with industry Read rejections by reason code (numbers). Existing report need enhancing to give; Read rejections by reason code percentage value for a Shipper needs to be added to current dashboard Industry average number of read rejections (number and percentage) needs adding Performance enhancement to give a greater user experience of the large volumes Stretch targets: As a Shipper I want to see a list of sites in my portfolio containing plot addresses so that I can assess and update the address details correctly & in a timely manner. As a Shipper I want the WAR Bands dashboard to be moved out of UIG area of DDP and added to the Reads area of DDP so that it sits more logically from a business process perspective | 

## Slide 44
Data Discovery Platform | Inflight Sprint (part of release 3)
Goals: Build the golden bullet invoice report Build the detailed design for the XRN4990 solution | 
User Stories: Build the dashboards to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on as well that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year Performance optimisation for read dashboards Detailed Design for the XRN4990 Solution pertaining to DDP Stretch Target: Must read enhancement to align BAU enhancement to DDP Industry view of number of MPRN associated to MRF (part of Shipper Pack XRN 5200) | 

## Slide 45: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 46: CMS Rebuild Update

## Slide 47: Progress to Date
The New CMS was successfully launched on 24 and 26 October 2022. There were no issues or incidents relating to to the launch of the new system. There were five Customer Support bridges set up throughout the week where users were advised to dial in should they have any issues with only one user dialling in.
There have been a few issues where incorrect email addresses had been provided which has caused some rework to disable the accounts and create new accounts with the correct details.
The new Shipper Raised Meter Number Creation (MNC) is now live in the system. Please be advised if any users submit MNC requests via the previous email process, they will not be accepted and they will be notified and redirected to use the new system.
We are now planning the activities for Version 1.1 and we are targeting a launch date of 12 December, this date will be confirmed in the next two weeks.
We will provide an update as soon as we know when the relevant REC change is due to be implemented to ensure you have as much notice as possible of the SUT / Modification 0734 process commencing (and the cessation of the current Shipper "TOG" process).
The CMS Rebuild webpages and CMS page have both been updated to reflect the Launch activities, FAQs and training materials. The Link to the training material is on both pages, however for reference it can be accessed using this link.
The CMS Rebuild webpage (https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild-product/ ) contains the link to register for future Customer Focus Groups which are captured below, please note the agenda for the Focus Groups will be issued 7 days prior to the session.

## Slide 48: REC Change
9th November 2022

## Slide 49: Introduction
The following 6 slides have been included in this months ChMC pack to give you an overview of the ongoing REC Changes, we have broken these down into the following sections:
In progress – we are currently progressing through the Change journey
Under Prioritisation Review with Code Managers – due to workload/prioritisation
Electricity related Changes which we are monitoring for visibility
Further information on the Changes can be found on the REC Portal

## Slide 50: Overview of REC Changes (high level)
Chart: 
| In Progress | Current Xoserve action | On Hold | Elec Only
Change Requests | 13 | 5 | 13 | 25
Notes: In progress:
Approved awaiting implementation 33,36
Consultation 47,52,55
Solution development 16,37
Initial assessment 25
Awaiting authority decision 21
Scoping Testing requirements 67
Detailed IA 70,74
Final Assessment 30

## Slide 51: Overview of In progress REC Changes (high level)
Chart: 
| Approved awaiting implementation | Consultation | Solution development | Initial assessment | Awaiting authority decision | Scoping Testing requirements | Detailed IA | Final Assessment
Series 1 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 1
Notes: In progress:
Approved awaiting implementation 10,11,36
Consultation 47,52,55
Solution development 16,37
Initial assessment 25
Awaiting authority decision 21
Scoping Testing requirements 67
Detailed IA 70,74
New CR05_XoS

## Slide 52: REC Change Pipeline – In progress (Require CDSP Assessment/Action)
Title | Description | XRN | Status | Next Action date
R0016 | Resolution of Bilateral Erroneous Transfers | N/A | Solution development | 21/12/2022 – Review at Change panel
R0021 | Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier | N/A | Awaiting Authority Decision | 31/10/2022 – The Authority approve/reject the Change
R0025 | Service Provider Performance Charges (DCC) | N/A | Initial Assessment | 01/11/2022 - Deadline to provide comments
R0030 | Erroneous Transfer Cancellations | N/A | Final Assessment | 14/11/2022 – Review
R0033 | Micro-business Smart Meter Installation Reports | N/A | Approved - awaiting implementation | 04/11/2022 – Proposed Implementation date
R0036 | Extensive Housekeeping Amendments | N/A | Approved - awaiting implementation | 01/11/2022 – Appeal window closes
R0037 | Prepayment Credit Balance & Debt Transfer Processes | N/A | Solution development | 08/11/2022 – Change proposal plan to be updated
R0047 | Metering Code of Practice Consolidation Review | N/A | Consultation | 04/11/2022 – Awaiting results from consultation
R0052 | GES Service Definition Document | N/A | Consultation | 05/11/2022 – Consultation response due date
R0055 | Switching Operator Outage Notification Lead Time | N/A | Consultation | 28/10/2022 - Consultation response due date

## Slide 53: REC Change Pipeline – In progress (Require CDSP Assessment/Action)
Title | Description | XRN | Status | Next Action date
R0067 | Introduction of CSS refresh functionality | XRN 5567 | Scoping Test requirements | 02/11/2022 – Weekly Review Meeting
R0070 | Provision of Enduring Test Environments | N/A | Detailed IA awaiting approval | 01/11/2022 – REC Change Panel
R0074 | Release of Community View Data Items to MEMs in GES | N/A | Awaiting detailed IA | 19/11/2022 – Detailed IA triggered
Please note: This is a working document and therefore some of the dates and actions may have progressed since the slides were created

## Slide 54: REC Change Pipeline – Under Prioritisation Review
Title | Description | Status | Next Action date
R0006 | Missing Meter Technical Details | Initial Assessment | Reviewed weekly – Awaiting instruction from REC Code Manager to progress
R0049 | Intellectual Property Rights and Services Data Main Body changes | Initial Assessment | 
R0050 | Clarification of REC Maintenance of Qualification Schedule | Initial Assessment | 
R0051 | Switch Request Objections (Change of Occupier) | Initial Assessment | 
R0056 | EES/GES additional service request for Housing Ass to be added to the Matrix | Initial Assessment | 
R0059 | Maintenance of Qualification Schedule Change | Initial Assessment | 
R0061 | Resolution of invalid CSS data by Data Owners | Initial Assessment | 
R0063 | Addition of key information to all Service Now tickets | Initial Assessment | 
R0068 | REC Data Protection Changes | Initial Assessment | 
R0069 | Amendments to Sample Access Agreement | Initial Assessment | 
R0071 | DCC access to EES and GES | Initial Assessment | 
R0073 | Introduction of a Housekeeping Change Proposal Process | Initial Assessment | 
R0075 | Enabling Software Product Qualification | Initial Assessment | 

## Slide 55: REC Change Pipeline Electric only - Monitoring
Title | Description | Status
R0009 | Introduction of SDEP and EES User Maintenance API | These changes are specific for Electric only. We will continue to monitor should any of the Changes have a knock on impact to GES or the CDSP.
R0010 | New Meter Types for Auxiliary Proportional Controllers (APCs) | These changes are specific for Electric only. We will continue to monitor should any of the Changes have a knock on impact to GES.
R0011 | Reporting of Additional EMR Backing Data to Suppliers | 
R0017 | Invalid Requests for Site Technical Details | These changes are specific for Electric only. We will continue to monitor should any of the changes have a knock on impact to GES.
R0018 | Complex Sites process improvements | 
R0022 | Amendment to REC Data Access Matrix | 
R0026 | Whole current (WC)/Current Transformer (CT) certificates | 
R0027 | Minimum identification requirements in the Meter Operation Code of Practice | 
R0031 | Altering the Trigger Points for CT Commissioning | 
R0032 | New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS) | 
R0040 | CSS Switch Synchronisation to ERDA at SecuredActive | 
R0043 | Commissioning of Works by the Crowded Meter Room Coordinator (CMRC) to Resolve Issues In Crowded Meter Rooms | 
R0044 | MHHS Programme Changes required to Central Switching Service | 

## Slide 56: REC Change Pipeline Electric only - Monitoring
Title | Description | Status
R0053 | 24/7 Emergency Metering Service | These changes are specific for Electric only. We will continue to monitor should any of the changes have a knock on impact to GES or the CDSP.
R0054 | EES Access for Virtual Lead Parties | 
R0060 | ERDS Service Definition timezone correction | These changes are specific for Electric only. We will continue to monitor should any of the changes have a knock on impact to GES.
R0062 | Removal of ERDA meteringPointEnergyFlow change restriction | 
R0064 | Creating a Meter Operator Agent and MOCoP Installer | 
R0065 | Registration of Smart Export Guarantee (SEG) Sites | 
R0066 | Inclusion of SMRS Data Items In EES (BSC CP 1568 Consequential change) | 
R0072 | Introduction of a new Meter Asset Condition Code | 
R0076 | DNOs notifying Suppliers about Crossed Meters | 
R0077 | Resolution of EES API Search Address method discrepancies | 
R0078 | EMR Settlement Limited - additional access to ECOES | 
N/A | MHHS Supply Number Consultation | 

## Slide 57: Section 6: AnY Other Business

## Slide 58: January ChMC Paper Submission & Change Pack close out date
Papers for the January ChMC are due to be sent to the JO by 12:00 on Tuesday 3rd January so they can publish by COP to give customers a full 5 day review period
This may result in out of date material being published due to the holiday season
Xoserve would like to propose that we send papers over to the JO by 12:00 Wednesday 4th reducing the review period by 1 day
Change packs are due to close out on 28th December. This will give 9 working days prior to the Christmas holidays (12th – 23rd) and 1 day during the holiday season.
We are asking if the committee would agree to the shortened timescale for ChMC paper review and do they want the Change Pack consultation period extending.

## Slide 59: Appendix

## Slide 60: Portfolio POAP