## Slide 1: Provision of Metering Information to support GDN Metering Upgrades
Start
OAD
Notice
On Site
Delivery
OAD
Supplemental
Start
End
Meter Test
Items prior to Installation & Commissioning of Meter
Confirm scope of changes required to Metering System
Provide Functional Design Specification (FDS) for changes - [1]
Provide theoretical measurement uncertainty calculations for the system post changes (e.g. using ISO5168 or other Guide in Measurement Uncertainty (GUM) method) – [2]
Provide copy of intended Factory Acceptance Testing (FAT) procedure for the changes and invite National Grid to attend (NG may or may not attend) – [3]
If meters are undergoing high pressure meter calibration provide notice of such calibration and invite National Grid to attend and witness such calibration (NG may or may not attend)
Provide copies of the results of FAT and also calibrations (including certificates) – [4]
Provide copy of Site Acceptance Testing (SAT) for the changes – [5]
Confirm proposed Operational Date for Meter
If a new Gas Chromatograph has been being installed provide a copy of the ISO10723 report with a pass.
Agree and sign draft of Supplemental Agreement Appendix D
Items post Commissioning of Meter
Results from SAT – [6]
Updated Measurement Uncertainty Calculations (As Built) where necessary – [7]
Agree and execute Supplemental Agreement amendments (including Appendix D)
Exchange Supplementals Agreements complete with revised Appendix D’s

## Slide 2: High Level Process
OAD Notice
On Site
Delivery
Confirm Outcome
Start
End
Meter Test
Design Part C Approval ¹
No Amendments ²
Pass
Fail
(Meter not live)
Amendments ³
SAT
Uncertainty Calcs
Revise SA Appdx D
Process SA
Pre Meter Commissioning data items to be provided at Design approval or prior to work on site commencing.
Results of Meter Test. If passed as expected this is to be confirmed as such along with No further amendments necessary. SA can be finalised and exchanged.
Results of Meter Test. If passed and amendments are required these are to be confirmed as such and advise on when revised data can be provided. The revised changes may or may not have an impact upon the SA.

## Slide 3: Indicative timeline for Metering Information Requirements
Timeline
G17 Part A
OAD Notice
Pre Design
Detailed Design
G17 Part C
Design
Post Testing
Planning & Delivery
NRO
Project Planning
Procurement & Pre Testing
Installation
Meter Test
Results, Reporting & Updares
1
2
Metering Information Requirements
Functional Design Scope
Uncertainty Calculations
Intended Factory Acceptance Testing (FAT)
FAT Results & Certificates
Intended Site Acceptance Testing (SAT)
Draft Supplemental Agreement (SA)
SAT Results
Chromat Results (where applicable)
Update Uncertainty Calculations (where necessary)
Update/Execute SA
3
4
5
6
7
8
9
10

## Slide 4: Provision of Metering Information for GDN Metering Upgrades
Requirements in Tabular Form
Item | Requirement | Timing
1 | Functional Design Specification | At G17 Part C
2 | Measurement Uncertainty Calculations | 
3 | Intended Factory Acceptance Test Procedure (FAT) | To be agreed with Project Plan
4 | FAT Results & Certificates | With NRO for Meter Installation & Testing
5 | Intended Site Acceptance Test Procedure (SAT) | 
6 | Draft Supplemental Agreement (Appendix D) | 
7 | SAT Results | 3 weeks after respective Meter Stream has gone operational or date as agreed between Cadent & NGG via OAD process
8 | Chromat/ISO 10723 Results | 
9 | Updated Measurement Uncertainty Calculations (where applicable) | 
10 | Revised Supplemental Agreement |