## Clarifications
Sprint | Groupings | Issue key | Comments | Summary
| No Read | DDP-163 | Clarification required from PAFA as the No Reads position is different to the position of MPRNs that have not met Read Performance targets | As PAFA I want to view the 12 months rolling trend of percentage of meter points with No Reads per Shipper so that I can compare shipper meter reading submission failure performance to the requirements as set out in the UNC
Remove? | CF | DDP-168 | Relevance given MOD0692? Timestamp required to understand how long an MPRN has been above threshold - how much development required (NRL?) | As PAFA I want 12 months rolling trend of count of MPRNs per Shipper with AQ> 732,000 where SCF is 1.02264 split by EUC bands (04-09) to monitor potentially incorrect correction factors for large consuming sites
| No Meter | DDP-185 | Date of flows to be added to current info? | As PAFA I want a per-Shipper view that will tell me for how long and how many sites are there in each portfolio which have no meter and are receiving data flows so that I can identify if the Shippers are taking action on such data
Remove? | Rejections | DDP-189 | Will be delivered as part of DDP-389 | As PAFA I want a 12 monthly rolling view of the number of rejected Transfer Reads so that I can understand what volume of opening reads sent by Shippers is being rejected

## Sprint3
Sprint | Groupings | Issue key | Comments | Summary
Sprint3 | PC1 | DDP-380 | PAC agreed 3/3/21 that measure against allocated volumes (estimated or actual) | XRN4876 - As PAFA I want a report that shows a trend line between allocated and settled volumes that includes the total amount of industry being settled on estimates for PC1 and PC2 so that I can monitor performance
Sprint3 | PC1 | DDP-382 | PAC agreed 3/3/21 - to incorporate DDP-177 | XRN4876 - As PAFA I want check read information for PC1 and PC2 to show the age of missed check reads. I want this split into 1,2,3,4+ years so that I can monitor performance
Sprint3 | Meter | DDP-392 |  | XRN4876 - As PAFA I want a report to show Meter Mechanism so that I can see what type of meter is fitted to differentiate between smart meters and credit meters.
Sprint3 | Rej | DDP-393 | PAC agreed 3/3/21 that measure will relate to all UMR exceptions that are related to the "No Read" proportion of Read Performance. MPRNs will have a 1-2-1 count for measuring the impact on performance but the details will relate the total number of exceptions | XRN4876 - As PAFA I want a report that shows all meter read rejection codes, shown as count of rejections with associated AQ of each unresolved rejection so that I better understand materiality associated with performance.
Sprint3 | No Meter | DDP-384 | Is this not covered by Activity/No Activity? Covered by DDP-385? | XRN4876 - As PAFA I want the report to be able to distinguish between sites that have had a meter removed and sites where no meter has ever been installed. Story relates to XRN4876 and was confirmed at the PAFA workshop 4/8/2020. No Meter Recorded Asset 2B.2
Sprint3 | No Meter | DDP-385 | Widens current scope. Linked to DDP-384 | XRN4876 - As PAFA I want the report that distinguishes between sites that have had a meter removed and sites where no meter has ever been installed. To include which dataflows have been received e.g. (RGMA / device removal / CDN - connection / disconnection / read). Story relates to XRN4876 and was confirmed at the PAFA workshop 4/8/2020 No Meter Recorded and Data Flow received 2B.3
Sprint3 | Unreg | DDP-386 |  | XRN4876 - As PAFA I want a report that shows the time lapsed between MPRN creation date and the current date to show an age profile of existing unregistered sites where a shipper has attempted (but failed) to register so that I understand
Sprint3 | CF | DDP-398 |  | XRN4876 - As PAFA I want to know what AQ volumes are associated with standard correction factors that are above the non-standard threshold (732,000 kwh) so that I understand the AQ at risk
Sprint3 | COS | DDP-388 |  | XRN4876 - As PAFA I want to see how many transfer reads are being submitted, accepted / rejected each month and as a rolling 12 month view so that I can assess shipper's intent
Sprint3 | COS | DDP-389 |  | XRN4876 - As PAFA I want to see how many estimated opening reads are being replaced via the Shipper Agreed Read (SAR) process so that I can assess shipper's intent
Sprint3 | COS | DDP-400 | 3/3/21 - Agreed with PAC to cover PC3&4 only. Requirement to monitor impact will be covered under DDP-400. Timing tbc and measure of impact (Rec or AQ) to be reviewed (KK action to provide examples for PAC to review). | XRN4876 - As PAFA I want to see the impact the replacement read is having on AQ and on KWh reconciliation
Sprint3 | ISO | DDP-401 | Requirement confirmed 3/3/21 as standalone report for Isolations to monitor activity in this area + info as part of Read Performance | XRN4876 - As PAFA I want to see the Isolation status on the detail view of the PAFA dashboard, so I can see if an MPRN is isolated.
Sprint3 | Bypass | DDP-402 | Requirement confirmed 3/3/21 that standalone dashboard required for this topic, detailing the trend of Bypass status, but including read activity/EUC/AQ/Market Sector/Meter Capacity | XRN4876 - As PAFA I want to see how many bypass flags are 'Open' and 'Closed' across the industry so that I can monitor how many sites are using the bypass and are not paying for gas so that I understand whether this is a risk

## 2021-2022
Sprint | Groupings | Issue key | Comments | Summary
| AQ | DDP-195 | Align to DDP-22 | As PAFA I want a view of AQ split by age bands for each Shipper so that I can get a view of how old the AQs are in their Portfolio
Remove-SU to confirm | AQ | DDP-198 | Provided in details (+Class, EUC, Shipper, MPRN) - REQUIRED? | As PAFA, for all Shippers, I want the AQ corrections dashlet to display the Reason codes for AQ correction so that I have a better understanding of the AQ correction information and the reason behind the corrections
| AQ | DDP-22 | Align to DDP-195 | As PAFA I want to view the Percentage of portfolio with AQ calculation split by 1 month, 4 months, 12 months, 24 months, 36 months plus as it is an important element in understanding the settlement risk
Remove? | CF | DDP-168 | Relevance given MOD0692? Timestamp required to understand how long an MPRN has been above threshold - how much development required (NRL?) | As PAFA I want 12 months rolling trend of count of MPRNs per Shipper with AQ> 732,000 where SCF is 1.02264 split by EUC bands (04-09) to monitor potentially incorrect correction factors for large consuming sites
| No Meter | DDP-164 | Link to DDP-165 | As PAFA I want to view the 12 months rolling trend of count of meter points with no meter for each Shipper split by class so that I can get a view of how many sites are there for each Shipper which have no meter
| No Meter | DDP-165 | Link to DDP-164 | As PAFA I need 12 months trend of no. of meter points with no meter with data flow implying presence of a meter. This view needs to be per Shipper split by class so that I can see sites for each Shipper where there is no meter but data suggests activity
| No Meter | DDP-178 |  | As PAFA I want the ability to split the data in No Meter Recorded report by EUC Bands for a better understanding of the industry data
| No Meter | DDP-185 | Date of flows to be added to current info? | As PAFA I want a per-Shipper view that will tell me for how long and how many sites are there in each portfolio which have no meter and are receiving data flows so that I can identify if the Shippers are taking action on such data
| No Read | DDP-163 | Clarification required from PAFA as the No Reads position is different to the position of MPRNs that have not met Read Performance targets | As PAFA I want to view the 12 months rolling trend of percentage of meter points with No Reads per Shipper so that I can compare shipper meter reading submission failure performance to the requirements as set out in the UNC
| PC1 | DDP-254 | Align to Release - Timing only question | PAFA - XRN5038 - Mod0691 - CDSP to convert Class 2, 3 or 4 sites to Class 1
| Performance | DDP-170 |  | As PAFA want to view the Read Performance for PC4 portfolio per Shipper split into separate views for Smart and AMR meters for a better understanding of PC4 read performance figures
Remove? | Rejections | DDP-189 | Will be delivered as part of DDP-389 | As PAFA I want a 12 monthly rolling view of the number of rejected Transfer Reads so that I can understand what volume of opening reads sent by Shippers is being rejected
Action - KK | Rejections | DDP-193 | Incorporate DDP-166 & DDP-192 (KK expand requirements) | As PAFA I need to view additional information in the Meter Read Validity Monitoring report along with counts so that I can monitor both the level of recurring failures and AQs involved
Action - KK to liaise with JW/SU re requirements | Read Perf | DDP-190 | Shipper filtering on dashboard - more detail required from PAFA Consistency required across dashboards e.g. record counts | As PAFA I want additional information per Shipper on my Read Performance dashboard for further insight.
| Read Perf | DDP-191 |  | As PAFA I want the additional information per Shipper on the dashboard showing Class 4 Read Performance so that I can manage PC4 read performance in a better manner
Action - KK to liaise with JW/SU re requirements | tbc | DDP-336 | Details required | As PAFA, I would like to see a data for each DDP topic, in a table view for all Shippers, per month, so that I don't have to navigate to multiple screens.