## Sheet1
ME2 schedule 2022
Site Name | Meter Type | Validation Due | Validation complete | Report received | Checked by | Sent to UKT | Comments Send to: meterassurance@nationalgrid.com
Aberdeen AGI (Offtake) | USM | 2022-03-15 | 2022-03-10 | y | ss | n
Hume AGI (Tracker) | Turbine | 2022-03-15 | 2022-03-29 | y | ss | Y | Sent 5/8/22
Mitcham Bio | USM | 2022-03-15 | 2022-04-06 | y | ss | y
Ipsden A AGI (Offtake) | OP | 2022-03-15 | 2022-03-18 | Y | SS | Y | sent 5/8/22
Soutra | OP | 2022-03-15 | 2022-04-05 | y | ss | Y | Sent 5/8/22
Kinknockie AGI (Offtake) | Turbine | 2022-04-15 | 2022-04-21 | y | ss | y | Sent 4/8/22
Nether Howcleugh AGI (Offtake) | Turbine | 2022-04-15 | 2022-04-11 | y | ss | y | Sent 4/8/22
Bathgate AGI (Offtake) | USM | 2022-05-15 | 2022-04-27 | y | ss | y | Sent 4/8/22
Winkfield AGI SO (Offtake) | OP | 2022-05-15 | 2022-05-09 | y | ss | y | Sent 4/8/22
Winkfield AGI SE (Offtake) | USM | 2022-05-15 | 2022-05-13 | y | ss | y | Sent 4/8/22
Ipsden B AGI (Offtake) | OP | 2022-05-15 | 2022-05-18 | y | ss | y | Sent 5/8/22
Mappowder AGI (Offtake) | OP | 2022-05-15 | 2022-05-30 | y | ss | y | Sent 4/8/22
Careston AGI (Offtake) | Turbine | 2022-05-15 | 2022-05-19 | y | ss | y | Sent 4/8/22
Armadale AGI (Offtake) | OP | 2022-05-15 | 2022-05-17 | y | ss | y | Sent 4/8/22
Braishfield A AGI (Offtake) | USM | 2022-06-15 | 2022-06-16 | y | ss | y | Sent 4/8/22
Braishfield B AGI (Offtake) | USM | 2022-06-15 | 2022-06-28 | y | ss | Y | Sent 5/8/22
Farningham AGI B (Offtake) | USM | 2022-06-15 | 2022-06-29 | y | ss | Y | Sent 25/11/22
Hardwick AGI (Offtake) | USM | 2022-06-15 | 2022-07-25 | y | ss | y | Sent 4/8/22
Farningham AGI A (Offtake) | USM | 2022-06-15 | 2022-07-29 | Y | ss | Y | Sent 25/11/22
Lockerbie AGI (Offtake) | OP | 2022-06-15 | 2022-06-17 | y | ss | y | Sent 4/8/22
Isle Of Grain MP (Offtake) | Turbine | 2022-07-15 |  |  |  |  | IOG contractor Pens Pen
Shorne AGI (Offtake) | OP | 2022-07-15 | 2022-07-07 | y | ss | y | Sent 4/8/22
Broxburn AGI USM (Offtake) | USM | 2022-07-15 | 2022-08-10 | Y | ss | Y | Sent 25/11/22
Drum AGI (Offtake) | USM | 2022-07-22 | 2022-07-27 | Y | SS | Y | Sent 25/11/22
Glenmavis (Offtake) | USM | 2022-08-15 | 2022-08-18 | Y | SS | Y | Sent 25/11/22
Tatsfield AGI (Offtake) | USM | 2022-08-21 | 2022-08-09 | Y | SS | Y | Sent 25/11/22
Pitcairngreen AGI (Offtake) | Turbine | 2022-09-15 | 2022-04-06 | Y | SS | Y | Sent 25/11/22
Portsdown Hill 1 | Turbine | 2022-09-15 | 2022-10-13 | Y | SS | N
Portsdown Hill 2 | Turbine | 2022-09-15 | 2022-11-04 | Y | SS | N
Portsdown Hill 3 | Turbine | 2022-09-15 |  |  |  |  | Offline, direction susppended
Portsdown Hill 4 | Turbine | 2022-09-15 |  |  |  |  | Offline, direction susppended
Portsdown Hill 5 | Turbine | 2022-09-15 | 2022-09-29 | y | ss | N
St Fergus AGI (Offtake) | Turbine | 2022-09-15 | 2022-09-16 | y | ss | Y | Sent 25/11/22
Isle Of Grain LP (Offtake) | Turbine | 2022-10-09 |  |  |  |  | IOG contractor Pens Pen
Balgray AGI (Offtake) | USM | 2022-10-15 | 2022-10-05 | y | ss | Y | Sent 25/11/22
Poundbury Bio | USM | 2022-10-15 | 2022-10-06 | Y | SS | N
Stranraer AGI (Tracker) | Turbine | 2022-10-15 | 2022-11-03 | Y | SS | Y | Sent 25/11/22
Apsley Farm Bio | USM | 2022-11-10
Langholm AGI (Tracker) | Turbine | 2022-11-15 | 2022-11-22 | Y | SS | Y | Sent 25/11/22
Burnhervie AGI (Offtake) | USM | 2022-11-15 | 2022-11-16 | Y | SS | Y | Sent 25/11/22
St. Nicholas Court Farm Bio | USM | 2022-12-15 | 2022-11-17 | Y | SS | N
Coupar Angus Bio | USM | 2022-12-15
Girvan Bio | USM | 2022-12-15