## ME2 Monitor
2018 Site | Due date | Date started | Date complete | Complete within tolerance | Duration (days) | Report received | Report delay (days) | Checked by | Sent to UKT | 2018-10-05
Wytch Farm (Feb) | 2012-02-15 | 2018-04-18 | 2018-04-23 | Y | 5 | 2018-04-27 | 4
Hume | 2012-03-15 | 2018-03-07 | 2018-03-16 | Y | 9 | 2018-04-04 | 19 | SS | 2018-04-04
Soutra | 2012-03-15 | 2018-03-19 | 2018-03-21 | Y | 2 | 2018-04-04 | 14 | SS | 2018-04-04
Mitcham | 2017-03-15 |  |  |  | 0 |  | 0
Oak Avenue (Inter LDZ) | 2012-03-15
Blackmore Cres (Inter LDZ) | 2012-03-15
Dryburgh Road (Inter LDZ) | 2012-03-15
Balgray | 2012-04-15 | 2018-04-23 | 2018-04-24 | Y | 1 | 2018-04-25 | 1
Glenmavis (Winter) | 2012-04-15 | 2018-03-29 | 2018-03-29 | Y | 0 | 2018-04-04 | 6 | SS | 2018-04-04
Drum | 2012-04-15 |  |  |  | 0 |  | 0
Tatsfield (OP removal) | 2012-04-15
Winkfield SE | 2012-05-15 | 2018-05-30 | 2018-06-08 | Y | 9 | 2018-06-19 | 11 | SS | 2018-06-19
Mappowder | 2012-05-15 | 2018-05-29 | 2018-05-31 | Y | 2 | 2018-06-06 | 6 | SS | 2018-06-11
Careston | 2012-05-15 | 2018-05-22 | 2018-05-23 | Y | 1 | 2018-05-25 | 2 | SS | 2018-06-11
Winkfield SO | 2012-05-15 | 2018-05-04 | 2018-05-15 | Y | 11 | 2018-06-19 | 35 | SS | 2018-06-19
Bathgate | 2012-05-15 | 2018-05-22 | 2018-05-23 | Y | 1 | 2018-05-25 | 2 | SS | 2018-06-11
Ipsden A | 2012-05-15 | 2018-03-23 | 2018-03-28 | N | 5 | 2018-07-17 | 111 | SS | 2018-07-19
Ipsden B | 2012-05-15 |  |  |  | 0 |  | 0
Kinknockie | 2012-05-15 | 2018-05-29 | 2018-05-30 | Y | 1 | 2018-05-31 | 1 | SS | 2018-06-11
Mitcham | 2016-05-15 | 2018-04-10 | 2018-04-12 | Y | 2 | 2018-04-13 | 1 | SS | N/A
Farningham A | 2012-06-15 | 2018-06-05 | 2018-06-11 | Y | 6 | 2018-06-18 | 7 | SS | 2018-06-19
Farningham B | 2012-06-15 | 2018-06-19 | 2018-06-25 | Y | 6 | 2018-07-19 | 24 | SS | 2018-07-19
Braishfield B | 2012-06-15 | 2018-06-27 | 2018-07-03 | Y | 6 | 2018-07-06 | 3 | SS | 2018-07-19
Lockerbie | 2012-06-15 | 2018-06-19 | 2018-06-20 | Y | 1 | 2018-06-21 | 1 | SS | 2017-06-26
Braishfield A | 2012-06-15 | 2018-06-19 | 2018-06-25 | Y | 6 | 2018-07-06 | 11 | SS | 2018-07-19
Pitcairngreen | 2012-04-15 | 2018-05-03 | 2018-05-04 | Y | 1 | 2018-05-17 | 13 | SS | 2018-06-11
Hardwick | 2012-06-15 | 2018-07-09 | 2018-07-13 | Y | 4 | 2018-07-23 | 10 | SS | 2018-07-27
Grain 2B | 2012-07-15
Armadale | 2012-07-15 | 2018-07-10 | 2018-07-13 | Y | 3 | 2018-07-15 | 2 | SS | 2018-07-19
Aberdeen | 2012-07-15 | 2018-07-25 | 2018-07-26 | Y | 1 | 2018-08-01 | 6 | SS | 2018-08-01
Shorne | 2012-07-15 | 2018-07-16 | 2018-07-26 | Y | 10 | 2018-08-01 | 6 | SS | 2018-08-01
Drum | 2012-07-15
Broxburn | 2012-08-15 | 2018-08-13 | 2018-08-15 | Y | 2 | 2018-08-20 | 5 | SS | 2018-08-21
Tatsfield (USM ME2) | 2012-08-15 | 2018-08-23 | 2018-08-31 | Y | 8 | 2018-09-11 | 11 | SS | 2018-09-11
Lamberton Toll (Inter LDZ) | 2016-08-15
Portsdown Hill Str 1 |  | 2018-07-25 | 2018-07-31 |  | 6 | 2018-08-06 | 6
Portsdown Hill Str 2
Portsdown Hill Str 3
St Fergus | 2012-09-15 |  |  |  | 0 |  | 0
Nether Howcleugh | 2012-09-15 |  |  |  | 0 |  | 0
Glenmavis (Summer) | 2012-09-15 |  |  |  | 0 |  | 0
Wytch Farm (Sep) | 2012-09-15 |  |  |  | 0 |  | 0
Grain 38B | 2012-09-15
Banbury | 2017-09-15
Newton Longville | 2017-09-15
Poundbury | 2013-10-15 |  |  |  | 0 |  | 0
Stranraer | 2012-10-15 |  |  |  | 0 |  | 0
Burnhervie | 2012-11-15 |  |  |  | 0 |  | 0
Didcot Bio | 2012-11-15
Langholm | 2012-11-15 |  |  |  | 0 |  | 0
Apsley (Bio) | 2015-11-15 |  |  |  | 0 |  | 0
Grants A &B | 2017-12-15 |  |  |  | 0 |  | 0
St Nicholas (Bio) | 2012-12-15 |  |  |  | 0 |  | 0
Ebbsfleet (Bio) | 2015-12-15 |  |  |  | 0 |  | 0
Coupar Angus (Bio) | 2015-12-15 |  |  |  | 0 |  | 0
2017 Site
Wytch Farm (Feb) | 2012-02-15 | 2017-04-04 | 2017-04-07 | Y | 3 | 2017-04-10 | 3
Hume | 2012-03-15 | 2017-03-06 | 2017-03-08 | Y | 2 | 2017-03-14 | 6 | SS | 2017-03-21
Soutra | 2012-03-15 | 2017-03-13 | 2017-03-15 | Y | 2 | 2017-03-16 | 1 | SS | 2017-03-21
Mitcham | 2017-03-15 | 2017-03-14 | 2017-03-22 | Y | 8 | 2017-03-23 | 1
Oak Avenue (Inter LDZ) | 2012-03-15
Blackmore Cres (Inter LDZ) | 2012-03-15
Dryburgh Road (Inter LDZ) | 2012-03-15
Balgray | 2012-04-15 | 2017-04-18 | 2017-04-20 | Y | 2 | 2017-05-03 | 13 | SS | 2017-05-05
Glenmavis (Winter) | 2012-04-15 | 2017-04-03 | 2017-04-05 | Y | 2 | 2017-04-07 | 2 | SS | 2017-03-13
Drum | 2017-07-15 | 2017-04-24 | 2017-04-25 | Y | 1 | 2017-05-05 | 10 | SS | 2017-05-05
Tatsfield (OP removal) | 2012-04-15 | 2017-04-24 | 2017-04-28 | Y | 4 | 2017-05-02 | 4 | SS | 2017-05-02
Winkfield SE | 2012-05-15 | 2017-05-16 | 2017-05-23 | Y | 7 | 2017-06-06 | 14 | SS | 2017-06-06
Mappowder | 2012-05-15 | 2017-05-16 | 2017-05-18 | Y | 2 | 2017-05-22 | 4 | SS | 2017-05-24
Careston | 2012-05-15 | 2017-05-22 | 2017-05-24 | Y | 2 | 2017-05-30 | 6 | SS | 2017-06-06
Winkfield SO | 2012-05-15 | 2017-05-03 | 2017-05-09 | Y | 6 | 2017-05-18 | 9 | SS | 2017-05-24
Bathgate | 2012-05-15 | 2017-05-02 | 2017-05-04 | Y | 2 | 2017-05-05 | 1 | SS | 2017-05-05
Ipsden C/D | 2012-05-15 | 2017-03-27 | 2017-05-29 |  | 63 | 2017-06-05 | 7 | SS | 2017-06-06
Ipsden A | 2012-05-15 | 2017-04-03 | 2017-04-07 | Y | 4 | 2017-06-05 | 59 | SS | 2017-06-06
Kinknockie | 2012-05-15 | 2017-05-30 | 2017-05-31 | Y | 1 | 2017-06-01 | 1 | SS | 2017-06-06
Mitcham | 2016-05-15 | 2017-03-14 | 2017-03-22 | Y | 8 | 2017-03-23 | 1
Farningham A | 2012-06-15 | 2017-06-05 | 2017-06-16 | Y | 11 | 2017-06-27 | 11 | SS | 2017-06-30
Farningham B | 2012-06-15 | 2017-06-27 | 2017-07-01 | Y | 4 | 2017-07-07 | 6 | SS | 2017-07-11
Braishfield B | 2012-06-15 | 2017-06-27 | 2017-06-29 | Y | 2 | 2017-07-05 | 6 | SS | 2017-07-11
Kinknockie | 2012-06-15 | 2017-06-19 | 2017-06-21 | Y | 2 | 2017-07-04 | 13 | SS | 2017-07-11
Braishfield A | 2012-06-15 | 2017-06-20 | 2017-06-26 | Y | 6 | 2017-07-05 | 9 | SS | 2017-07-11
Pitcairngreen | 2012-04-15 | 2017-04-11 | 2017-04-12 | Y | 1 | 2017-04-20 | 8 | SS | 2017-04-21
Hardwick | 2012-06-15 | 2017-06-19 | 2017-06-22 | Y | 3 | 2017-07-07 | 15 | SS | 2017-07-11
Grain 2B | 2012-07-15
Armadale | 2012-07-15 | 2017-07-10 | 2017-07-12 | Y | 2 | 2017-07-13 | 1 | SS | 2017-07-14
Aberdeen | 2012-07-15 | 2017-07-25 | 2017-10-25 | Y | 92 | 2017-10-27 | 2 | SS | 2017-10-30
Shorne | 2012-07-15 | 2017-07-10 | 2017-07-14 | Y | 4 | 2017-07-14 | 0 | SS | 2017-07-14
Drum | 2012-07-15 | SEE APRIL
Broxburn | 2012-08-15 | 2017-08-14 | 2017-08-15 | Y | 1 | 2017-08-16 | 1 | SS | 2017-08-18
Tatsfield (USM ME2) | 2012-08-15 | 2017-07-25 | 2017-08-03 | Y | 9 | 2017-08-09 | 6
Lamberton Toll (Inter LDZ) | 2016-08-15
Portsdown Hill Str 2 |  |  | Aug
Portsdown Hill Str 3 |  |  | Aug
St Fergus | 2012-09-15 | 2017-09-26 | 2017-09-27 | Y | 1 | 2017-10-03 | 6 | SS | 2017-10-03
Nether Howcleugh | 2012-09-15 | 2017-09-18 | 2017-09-20 | Y | 2 | 2017-10-11 | 21 | SS | 2017-10-30
Glenmavis (Summer) | 2012-09-15 | 2017-09-05 | 2017-09-06 | Y | 1 | 2017-09-11 | 5 | SS | 2017-09-15
Wytch Farm (Sep) | 2012-09-15 | 2017-11-13 | 2017-11-17 | Y | 4 | 2017-11-17 | 0
Grain 38B | 2012-09-15
Banbury | 2017-09-15 |  | 2017-09-28
Newton Longville | 2017-09-15 |  | 2017-09-20
Poundbury | 2013-10-15 | 2017-09-27 | 2017-09-27 | Y | 0 | 2017-10-02 | 5
Stranraer | 2012-10-15 | 2017-09-27 | 2017-10-30 | Y | 33 | 2017-11-02 | 3
Burnhervie | 2012-11-15 | 2017-11-06 | 2017-11-08 | Y | 2 | 2017-11-13 | 5
Didcot Bio | 2012-11-15
Langholm | 2012-11-15 | 2017-11-07 | 2017-11-08 | Y | 1 | 2017-11-09 | 1
Apsley (Bio) | 2015-11-15 | 2017-11-07 | 2017-11-07 | Y | 0 | 2017-11-13 | 6
Grants A &B | 2017-12-15 | 2017-12-18 | 2017-12-21 | Y | 3 | 2017-12-22 | 1
St Nicholas (Bio) | 2012-12-15 | 2017-11-10 | 2017-11-14 | Y | 4 | 2017-11-17 | 3
Ebbsfleet (Bio) | 2015-12-15 | 2017-11-06 | 2017-11-06 | Y | 0 | 2017-11-13 | 7
Coupar Angus (Bio) | 2015-12-15 | 2017-12-12 | 2017-12-14 | Y | 2 | 2017-12-22 | 8
2016 Site | Due date | Date started | Date complete | Complete within tolerance | Duration (days) | Report received | Report delay (days) | Checked by | Sent to UKT
Wytch Farm (Feb) | 2012-02-15 | 2016-05-09 | 2016-05-11 | OK | 2 | 2016-05-12 | 1 | SS | 2016-05-12
Hume | 2012-03-15 | 2016-03-07 | 2016-03-09 | OK | 2 | 2016-03-14 | 5 | SS | 2016-03-14
Soutra | 2012-03-15 | 2016-03-14 | 2016-03-15 | OK | 2 | 2016-03-16 | 1 | SS | 2016-03-24
Oak Avenue (Inter LDZ) | 2012-03-15
Blackmore Cres (Inter LDZ) | 2012-03-15
Dryburgh Road (Inter LDZ) | 2012-03-15
Balgray | 2012-04-15 | 2016-04-20 | 2016-04-22 | OK | 2 | 2016-04-25 | 3 | SS | 2016-04-26
Glenmavis (Winter) | 2012-04-15 | 2016-04-19 | 2016-04-22 | OK | 3 | 2016-04-29 | 7 | SS | 2016-05-04
Winkfield SE | 2012-05-15 | 2016-05-09 | 2016-05-12 | Ok | 3 | 2016-06-07 | 26 | SS | 2016-06-07
Mappowder | 2012-05-15 | 2016-05-16 | 2016-05-19 | OK | 3 | 2016-05-20 | 1 | SS | 2016-05-24
Careston | 2012-05-15 | 2016-05-17 | 2016-05-18 | OK | 1 | 2016-05-24 | 6 | SS | 2016-05-24
Winkfield SO | 2012-05-15 | 2016-05-17 | 2016-05-24 | OK | 7 | 2016-06-01 | 8 | SS | 2016-06-03
Bathgate | 2012-05-15 | 2016-05-04 | 2016-05-05 | OK | 1 | 2016-05-06 | 1 | SS | 2016-05-12
Ipsden C/D | 2012-05-15 | 2016-05-16 | 2016-05-27 | OK | 11 | 2016-06-06 | 8 | SS | 2016-06-07
Ipsden A | 2012-05-15 | 2016-05-09 | 2016-05-12 | OK | 3 | 2016-06-13 | 32 | SS | 2016-06-14
Kinknockie | 2012-05-15 | 2016-05-31 | 2016-06-02 | OK | 3 | 2016-06-03 | 1 | SS | 2016-06-03
Mitcham | 2016-05-15 | 2016-04-14 | 2016-04-26 | OK | 12 | 2016-05-24 | 28 | SS | 2016-05-24
Farningham A | 2012-06-15 | 2016-06-06 | 2016-06-13 | OK | 7 | 2016-06-20 | 7 | SS | 2016-06-24
Farningham B | 2012-06-15 | 2016-06-13 | 2016-06-20 | OK | 7 | 2016-06-24 | 4 | SS | 2016-06-29
Braishfield B | 2012-06-15 | 2016-06-27 | 2016-06-30 | OK | 3 | 2016-07-01 | 1 | SS | 2016-07-01
Lockerbie | 2012-06-15 | 2016-06-07 | 2016-06-09 | OK | 2 | 2016-06-10 | 1 | SS | 2016-06-14
Braishfield A | 2012-06-15 | 2016-06-21 | 2016-06-30 | OK | 9 | 2016-07-01 | 1 | SS | 2016-07-01
Pitcairngreen | 2012-04-15 | 2016-04-26 | 2016-04-27 | OK | 1 | 2016-05-03 | 6 | SS | 2016-05-04
Hardwick | 2012-06-15 | 2016-06-14 | 2016-06-21 | OK | 7 | 2016-06-27 | 6 | SS | 2016-06-29
Grain 2B | 2012-07-15 | 2017-12-11 | 2017-12-12
Armadale | 2012-07-15 | 2016-07-19 | 2016-07-21 | OK | 3 | 1900-01-21 | 2 | SS | 2016-07-25
Aberdeen | 2012-07-15 | 2016-07-18 | 2016-07-20 | OK | 2 | 2016-07-22 | 2 | SS | 2016-07-25
Shorne | 2012-07-15 | 2016-07-12 | 2016-07-18 | OK | 6 | 2016-07-20 | 2 | SS | 2016-07-20
Drum | 2012-07-15 | 2016-07-05 | 2016-07-07 | OK | 2 | 2016-07-12 | 5 | SS | 2016-07-20
Broxburn | 2012-08-15 | 2016-08-16 | 2016-08-17 | OK | 1 | 2016-08-18 | 1 | SS | 2016-08-22
Tatsfield | 2012-08-15 | 2016-08-09 | 2016-08-17 | OK | 8 | 2016-08-19 | 2 | SS | 2016-08-22
Lamberton Toll (Inter LDZ) | 2016-08-15
St Fergus | 2012-09-15 | 2016-09-13 | 2016-09-15 | OK | 2 | 2016-09-22 | 7 | SS | 2016-09-28
Nether Howcleugh | 2012-09-15 | 2016-09-19 | 2016-09-22 | OK | 3 | 2016-09-28 | 6 | SS | 2016-09-28
Glenmavis (Summer) | 2012-09-15 | 2016-09-06 | 2016-09-08 | OK | 2 | 2016-09-16 | 8 | SS | 2016-09-20
Wytch Farm (Sep) | 2012-09-15 | 2016-11-07 | 2016-11-09 | OK | 2 | 2016-11-16 | 7
Grain 38B | 2012-09-15
Poundbury | 2013-10-15 | 2016-09-28 | 2016-10-04 | OK | 6 | 2016-10-04 | 0 | SS | 2016-10-05
Stranraer | 2012-10-15 | 2016-09-27 | 2016-09-29 | OK | 2 | 2016-10-03 | 4 | SS | 2016-10-05
Burnhervie | 2012-11-15 | 2016-11-07 | 2016-11-11 | OK | 4 | 2016-11-15 | 4 | SS | 2016-11-16
Didcot Bio | 2012-11-15 | 2016-11-15 | 2016-11-17 | OK | 2 | 2016-12-05 | 18
Langholm | 2012-11-15 | 2016-11-07 | 2016-11-10 | OK | 3 | 2016-11-15 | 5 | SS | 2016-11-16
Apsley (Bio) | 2015-11-15 | 2016-10-13 | 2016-10-18 | OK | 5 | 2016-10-24 | 6
Grants A & B |  | 2017-12-19 | 2017-12-22 | OK | 3 | 2016-12-23 | 2
St Nicholas (Bio) | 2012-12-15 | 2016-12-14 | 2016-12-22 | OK | 1 | 2016-12-28 | 6
Ebbsfleet (Bio) | 2015-12-15
Coupar Angus (Bio) | 2015-12-15 | 2016-12-12 | 2016-12-15 | OK | 3 | 2016-12-20 | 5
2015 Site | Due date | Date started | Date complete | Complete within tolerance | Duration (days) | Report received | Report delay (days) | Checked by | Sent to UKT
Wytch Farm (Feb) | 2012-02-15 | 2015-03-24 | 2015-04-07 | OK | 13 | 2015-04-08 | 1 | SS
Hume | 2012-03-15 | 2015-03-17 | 2015-03-26 | OK | 9 | 2015-04-02 | 7 | SS | 2015-04-07
Soutra | 2012-03-15 | 2015-03-24 | 2015-03-25 | OK | 2 | 2015-04-02 | 8 | SS | 2015-04-07
Balgray | 2012-04-15 | 2015-04-21 | 2015-04-23 | OK | 2 | 2015-04-29 | 6 | SS | 2015-05-05
Glenmavis (Winter) | 2012-04-15 | 2015-04-20 | 2015-04-22 | OK | 2 | 2015-05-01 | 9 | SS | 2015-05-05
Winkfield SE | 2012-05-15 | 2015-05-14 | 2015-05-29 | OK | 15 | 2015-05-29 | 0 | SS | 2015-06-01
Mappowder | 2012-05-15 | 2015-05-19 | 2015-05-21 | OK | 2 | 2015-05-26 | 5 | SS | 2015-06-01
Careston | 2012-05-15 | 2015-05-19 | 2015-05-28 | OK | 9 | 2015-05-28 | 0 | SS | 2015-06-01
Winkfield SO | 2012-05-15 | 2015-05-05 | 2015-05-13 | OK | 8 | 2015-05-19 | 6 | SS | 2015-05-20
Bathgate | 2012-05-15 | 2015-05-06 | 2015-05-27 | OK | 21 | 2015-06-01 | 5 | SS | 2015-06-01
Ipsden C/D | 2012-05-15 | 2015-05-18 | 2015-05-22 | OK | 4 | 2015-05-29 | 7 | SS | 2015-06-01
Ipsden A | 2012-05-15 | 2015-05-11 | 2015-05-13 | OK | 2 | 2015-05-29 | 6 | SS | 2015-06-01
Kinknockie | 2012-05-15 | 2015-05-26 | 2015-05-28 | OK | 2 | 2015-05-29 | 1 | SS | 2015-06-01
Farningham A | 2012-06-15 | 2015-06-10 | 2015-06-19 | OK | 9 | 2015-06-26 | 7 | SS | 2015-07-02
Farningham B | 2012-06-15 | 2015-06-22 | 2015-07-02 | OK | 10 | 2015-07-03 | 1 | SS | 2015-07-08
Braishfield B | 2012-06-15 | 2015-06-25 | 2015-06-29 | OK | 4 | 2015-07-06 | 7 | SS | 2015-07-08
Lockerbie | 2012-06-15 | 2015-06-02 | 2015-06-04 | OK | 2 | 2015-06-10 | 6 | SS | 2015-06-15
Braishfield A | 2012-06-15 | 2015-06-23 | 2015-06-25 | OK | 2 | 2015-07-06 | 11 | SS | 2015-07-08
Pitcairngreen | 2012-04-15 | 2015-04-28 | 2015-04-30 | OK | 2 | 2015-05-01 | 1 | SS | 2015-05-05
Hardwick | 2012-06-15 | 2015-06-08 | 2015-06-12 | OK | 4 | 2015-06-17 | 5 | SS | 2015-06-17
Grain 2B | 2012-07-15
Armadale | 2012-07-15 | 2015-07-14 | 2015-07-16 | OK | 2 | 2015-07-16 | 0 | SS | 2015-07-20
Aberdeen | 2012-07-15 | 2015-07-21 | 2015-07-23 | OK | 2 | 2015-07-24 | 1 | SS | 2015-07-27
Shorne | 2012-07-15 | 2015-07-13 | 2015-07-16 | OK | 3 | 2015-07-17 | 1 | SS | 2015-07-20
Drum | 2012-07-15 | 2015-07-07 | 2015-07-09 | OK | 2 | 2015-07-16 | 7 | SS | 2015-07-20
Broxburn | 2012-08-15 | 2015-08-10 | 2015-08-11 | OK | 1 | 2015-08-13 | 2 | SS | 2015-08-24
Tatsfield | 2012-08-15 | 2015-08-04 | 2015-08-14 | OK | 10 | 2015-08-19 | 5 | SS | 2015-08-24
St Fergus | 2012-09-15 | 2015-09-22 | 2015-09-24 | OK | 2 | 2015-09-30 | 6 | SS | 2015-10-01
Nether Howcleugh | 2012-09-15 | 2015-09-29 | 2015-10-09 | OK | 11 | 2015-10-12 | 3 | SS | 2015-10-16
Glenmavis (Summer) | 2012-09-15 | 2015-09-14 | 2015-09-17 | OK | 3 | 2015-09-30 | 13 | SS | 2015-10-01
Wytch Farm (Sep) | 2012-09-15 | 2015-10-12 | 2015-10-15 | OK | 3 | 2015-10-15 | 0
Grain 38B | 2012-09-15
Poundbury | 2013-10-15 | 2015-09-29 | 2015-09-30 | OK | 1 | 2015-10-05 | 5 | SS | 2015-10-09
Stranraer | 2012-10-15 | 2015-10-26 | 2015-10-29 | OK | 3 | 2015-10-30 | 1 | SS | 2015-11-03
Burnhervie | 2012-11-15 | 2015-11-02 | 2015-11-04 | OK | 2 | 2015-11-09 | 5 | SS | 2015-11-13
Didcot Bio | 2012-11-15 | 2015-11-10 | 2015-11-12 | OK | 2 | 2015-11-23 | 11 | SS | 2015-11-23
Langholm | 2012-11-15 | 2015-11-23 | 2015-11-25 | OK | 2 | 2015-12-07 | 12 | SS | 2015-12-07
Apsley (Bio) | 2015-11-15 | 2015-11-25 | 2015-11-26 | OK | 1 | 2015-11-27 | 1 | SS | 2015-11-27
St Nicholas (Bio) | 2015-12-15 | 2015-12-01 | 2015-12-14 | OK | 14 | 2015-12-16 | 2
Ebbsfleet | 2015-12-15 | 2015-12-18 | 2015-12-19 | OK | 1 | 2015-12-21 | 2
Coupar Angus | 2015-12-15 | 2015-12-08 | 2015-12-10 | OK | 2 | 2015-12-22 | 12
2014 Site | Due date | Date started | Date complete | Complete within tolerance | Duration (days) | Report received | Report delay (days) | Checked by | Sent to UKT | Reason not sent yet
Wytch Farm (Feb) | 2012-02-15 | 2014-03-10 | 2014-03-21 | OK | 11 | 2014-03-26 | 5 | SS | 2014-03-28
Hume | 2012-03-15 | 2014-03-05 | 2014-03-18 | OK | 13 | 2014-03-19 | 1 | SS | 2014-03-24
Soutra | 2012-03-15 | 2014-03-20 | 2014-03-21 | OK | 2 | 2014-03-24 | 3 | SS | 2014-03-31
Balgray | 2012-04-15 | 2014-04-22 | 2014-04-24 | OK | 2 | 2014-04-28 | 4 | SS | 2014-05-01
Glenmavis (Winter) | 2012-04-15 | 2014-04-07 | 2014-04-14 | OK | 7 | 2014-04-16 | 2 | SS | 2014-04-23
Winkfield SE | 2012-05-15 | 2014-05-14 | 2014-07-17 | FAIL | 73 | 2014-07-25 | 8 | SS | 2014-08-04
Mappowder | 2012-05-15 | 2014-05-22 | 2014-05-29 | OK | 7 | 2014-05-29 | 0 | SS | 2014-06-05
Careston | 2012-05-15 | 2014-05-19 | 2014-05-21 | OK | 2 | 2014-05-29 | 8 | SS | 2014-06-05
Winkfield SO | 2012-05-15 | 2014-04-29 | 2014-05-09 | OK | 10 | 2014-05-09 | 0 | SS | 2014-05-12
Bathgate | 2012-05-15 | 2014-05-21 | 2014-05-26 | OK | 5 | 2014-05-29 | 3 | SS | 2014-06-05
Ipsden C/D | 2012-05-15 | 2014-05-19 | 2014-05-22 | OK | 3 | 2014-05-23 | 1 | SS | 2014-06-05
Ipsden A | 2012-05-15 | 2014-05-12 | 2014-05-14 | OK | 2 | 2014-05-15 | 1 | SS | 2014-05-19
Kinknockie | 2012-06-15 | 2014-06-10 | 2014-06-12 | OK | 2 | 2014-06-16 | 4 | SS | 2014-06-18
Farningham A | 2012-06-15 | 2014-06-25 | 2014-06-30 | OK | 5 | 2014-07-01 | 1 | SS | 2014-07-02
Farningham B | 2012-06-15 | 2014-07-02 | 2014-07-08 | OK | 6 | 2014-07-10 | 2 | SS | 2014-07-10
Braishfield B | 2012-06-15 | 2014-06-19 | 2014-06-20 | OK | 2 | 2014-06-24 | 4 | SS | 2014-06-30
Lockerbie | 2012-06-15 | 2014-06-02 | 2014-06-06 | OK | 4 | 2014-06-17 | 11 | SS | 2014-06-18
Braishfield A | 2012-06-15 | 2014-06-17 | 2014-06-20 | OK | 3 | 2014-06-24 | 4 | SS | 2014-06-30
Pitcairngreen | 2012-06-15 | 2014-06-24 | 2014-06-27 | OK | 3 | 2014-06-27 | 0 | SS | 2014-06-30
Hardwick | 2012-06-15 | 2014-06-10 | 2014-06-12 | OK | 2 | 2014-06-12 | 0 | SS | 2014-06-30
Grain 2B | 2012-07-15 | 2014-10-23
Armadale | 2012-07-15 | 2014-07-08 | 2014-07-09 | OK | 1 | 2014-07-15 | 6 | SS | 2014-07-16
Aberdeen | 2012-07-15 | 2014-07-16 | 2014-07-18 | OK | 2 | 2014-07-22 | 4 | SS | 2014-07-22
Shorne | 2012-07-15 | 2014-07-15 | 2014-07-18 | OK | 3 | 2014-07-23 | 5 | SS | 2014-08-04
Drum | 2012-07-15 | 2014-07-24 | 2014-07-25 | OK | 1 | 2014-07-30 | 5 | SS | 2014-08-04
Broxburn | 2012-08-15 | 2014-08-07 | 2014-08-07 | OK | 1 | 2014-08-07 | 0 | SS | 2014-08-12
Tatsfield | 2012-08-15 | 2014-08-05 | 2014-08-13 | OK | 8 | 2014-08-19 | 6 | SS | 2014-08-21
St Fergus | 2012-09-15 | 2014-09-17 | 2014-09-23 | OK | 6 | 2014-09-24 | 1 | SS | 2014-09-26
Nether Howcleugh | 2012-09-15 | 2014-09-22 | 2014-10-09 | OK | 4 | 2014-10-13 | 4 | SS | 2014-10-13
Glenmavis (Summer) | 2012-09-15 | 2014-09-01 | 2014-09-03 | OK | 2 | 2014-09-05 | 2 | SS | 2014-09-10
Wytch Farm (Sep) | 2012-09-15 | 2014-11-25 | 2014-12-02 | OK | 7 | 2014-12-08 | 6
Grain 38B | 2012-09-15 | 2015-03-10
Poundbury | 2013-10-15 | 2014-09-23 | 2014-09-25 | OK | 2 | 2014-10-02 | 7 | SS | 2014-10-06
Stranraer | 2012-10-15 | 2014-10-14 | 2014-10-27 | OK | 13 | 2014-10-29 | 2 | SS | 2014-11-03
Burnhervie | 2012-11-15 | 2014-11-18 | 2014-11-20 | OK | 2 | 2014-11-27 | 7 | SS | 2014-12-01
Didcot Bio | 2012-11-15 | 2014-11-17 | 2014-11-19 | OK | 2 | 2014-11-21 | 2 | SS | 2014-11-26
Langholm | 2012-11-15 | 2014-11-25 | 2014-11-26 | OK | 2 | 2014-12-03 | 7 | SS | 2014-12-05
2013
Site | Due date | Date started | Date complete | Complete within tolerance | Duration (days) | Report received | Report delay (days) | Checked by | Sent to UKT | Reason not sent yet
Wytch Farm (Feb) | 2012-02-15 | 2013-03-22 | 2013-04-16 | FAIL | 25 | 2013-04-22 | 6 | TR
Hume | 2012-03-15 | 2013-03-04 | 2013-03-13 | OK | 9 | 2013-03-18 | 5 | TR | 2013-03-26
Soutra | 2012-03-15 | 2013-03-14 | 2013-03-15 | OK | 1 | 2013-03-18 | 3 | TR | 2013-03-27
Balgray | 2012-04-15 | 2013-04-15 | 2013-04-24 | OK | 9 | 2013-04-30 | 6 | TR | 2013-05-21
Glenmavis (Winter) | 2012-04-15 | 2013-04-09 | 2013-04-11 | OK | 2 | 2013-04-22 | 11 | TR | 2013-04-24
Winkfield SE | 2012-05-15 | 2013-05-21 | 2013-05-30 | OK | 9 | 2013-06-03 | 4 | TR | 2013-06-05
Mappowder | 2012-05-15 | 2013-05-23 | 2013-05-30 | OK | 7 | 2013-06-07 | 7 | TR | 2013-07-03
Careston | 2012-05-15 | 2013-05-09 | 2013-05-14 | OK | 5 | 2013-05-17 | 3 | TR | 2013-05-21
Winkfield SO | 2012-05-15 | 2013-05-08 | 2013-05-16 | OK | 8 | 2013-06-03 | 18 | TR | 2013-06-05
Bathgate | 2012-05-15 | 2013-05-13 | 2013-05-22 | OK | 9 | 2013-05-28 | 6 | TR | 2013-05-30
Ipsden C/D | 2012-05-15 | 2013-05-21 | 2013-05-23 | OK | 2 | 2013-05-24 | 1 | TR | 2013-08-02
Ipsden A | 2012-05-15 | 2013-05-13 | 2013-05-16 | OK | 3 | 2013-05-24 | 8 | TR | 2013-05-31
Kinknockie | 2012-06-15 | 2013-07-02 | 2013-07-03 | OK | 2 | 2013-07-17 | 14 | TR | 2013-08-02
Farningham A | 2012-06-15 | 2013-06-07 | 2013-06-14 | OK | 7 | 2013-07-26 | 42 | TR | 2013-08-02
Farningham B | 2012-06-15 | 2013-06-18 | 2013-06-25 | OK | 7 | 2013-07-26 | 31 | TR | 2013-08-05
Braishfield B | 2012-06-15 | 2013-06-04 | 2013-06-10 | OK | 6 | 2013-11-26 | 168 | SS | 2013-12-02
Lockerbie | 2012-06-15 | 2013-06-17 | 2013-06-20 | OK | 3 | 2013-06-28 | 8 | TR | 2013-07-03
Braishfield A | 2012-06-15 | 2013-06-12 | 2013-06-19 | OK | 7 | 2013-11-25 | 159 | SS | 2013-12-02
Pitcairngreen | 2012-06-15 | 2013-06-17 | 2013-06-20 | OK | 4 | 2013-07-03 | 13 | TR | 2013-07-05
Hardwick | 2012-06-15 | 2013-06-04 | 2013-06-06 | OK | 3 | 2013-06-06 | 0 | TR | 2013-06-26
Grain 2B | 2012-07-15 | 2014-08-13 | 2014-09-03 | OK | 21 | 2014-01-21
Armadale | 2012-07-15 | 2013-07-09 | 2013-07-10 | OK | 2 | 2013-08-30 | 50 | SS | 2013-08-30
Aberdeen | 2012-07-15 | 2013-07-16 | 2013-07-17 | OK | 2 | 2013-08-07 | 20 | TR | 2013-08-07
Shorne | 2012-07-15 | 2013-07-16 | 2013-07-26 | OK | 10 | 2013-08-12 | 17 | SS | 2013-08-30
Drum | 2012-07-15 | 2013-07-05 | 2013-07-06 | OK | 2 | 2013-07-17 | 11 | TR | 2013-08-02
Broxburn | 2012-08-15 | 2013-08-05 | 2013-08-06 | OK | 2 | 2013-08-30 | 24 | SS | 2013-08-30
Tatsfield | 2012-08-15 | 2013-08-20 | 2013-08-23 | OK | 3 | 2013-09-09 | 26 | SS | 2013-09-10
St Fergus | 2012-09-15 | 2013-09-24 | 2013-09-27 | OK | 3 | 2013-10-11 | 14 | SS | 2013-10-18
Nether Howcleugh | 2012-09-15 | 2013-09-02 | 2013-09-06 | OK | 4 | 2013-09-23 | 19 | SS | 2013-09-26
Glenmavis (Summer) | 2012-09-15 | 2013-08-23 | 2013-08-30 | OK | 7 | 2013-09-17 | 18 | SS | 2013-09-26
Wytch Farm (Sep) | 2012-09-15 | 2013-11-12 | 2013-11-21 | OK | 9 | 2013-11-28 | 7 | SS | 2013-12-06
Grain 38B | 2012-09-15 | 2014-01-14 | 2014-01-14 |  | 1 | LNG
Poundbury | 2013-10-15 | 2013-10-07 | 2013-10-09 | OK | 3 | 2013-11-25 | 139 | SS | 2014-02-27
Stranraer | 2012-10-15 | 2013-10-22 | 2013-10-24 | OK | 3 | 2013-11-13 | 20 | SS | 2013-11-13
Burnhervie | 2012-11-15 | 2013-11-27 | 2013-11-28 | OK | 2 | 2013-12-03 |  | SS | 2014-01-24
Didcot Bio | 2012-11-15 | 2013-11-18 | 2013-11-19 | OK | 2 | 2013-11-28 | 9 | SS | 2013-12-02
Langholm | 2012-11-15 | 2013-11-04 | 2013-11-06 | OK | 6 | 2013-11-29 | 23 | SS | 2013-12-02
2012
Site | Due date | Date started | Date complete | Complete within tolerance | Duration (days) | Report received | Report delay (days) | Checked by | Sent to UKT | Reason not sent yet
Wytch Farm (Feb) | 2012-02-15 | 2012-02-14 | 2012-04-10 | FAIL | 56 | 2012-04-13 | 3 | TR | N/A
Hume | 2012-03-15 | 2012-03-08 | 2012-03-21 | OK | 13 | 2012-04-05 | 15 | TR | 2012-04-11
Soutra | 2012-03-15 | 2012-03-20 | 2012-03-22 | OK | 2 | 2012-03-29 | 7 | TR | 2012-04-05
Balgray | 2012-04-15 | 2012-04-30 | 2012-05-03 | FAIL | 3 | 2012-05-17 | 14 | TR | 2012-06-07
Glenmavis (Winter) | 2012-04-15 | 2012-04-02 | 2012-04-05 | OK | 3 | 2012-04-27 | 22 | TR | 2012-05-14
Winkfield SE | 2012-05-15 | 2012-05-01 | 2012-05-08 | OK | 7 | 2012-05-14 | 6 | TR | 2012-05-14
Mappowder | 2012-05-15 | 2012-05-21 | 2012-05-25 | OK | 4 | 2012-05-29 | 4 | TR | 2012-06-25
Careston | 2012-05-15 | 2012-05-08 | 2012-05-10 | OK | 2 | 2012-05-16 | 6 | TR | 2012-05-22
Winkfield SO | 2012-05-15 | 2012-05-08 | 2012-05-17 | OK | 9 | 2012-05-18 | 1 | TR | 2012-05-22
Bathgate | 2012-05-15 | 2012-05-09 | 2012-05-18 | OK | 9 | 2012-05-25 | 7 | TR | 2012-05-30
Ipsden C/D | 2012-05-15 | 2012-05-15 | 2012-05-21 | OK | 6 | 2012-05-22 | 1 | TR | 2012-06-18
Ipsden A | 2012-05-15 | 2012-05-22 | 2012-05-25 | OK | 3 | 2012-05-28 | 3 | TR | 2012-06-18
Farningham A | 2012-06-15 | 2012-06-12 | 2012-06-18 | OK | 6 | 2012-06-27 | 9 | TR | 2012-06-29
Farningham B | 2012-06-15 | 2012-06-19 | 2012-06-28 | 2012-07-11 | 9 | 2012-07-11 | 13 | TR | 2012-07-16
Braishfield B | 2012-06-15
Lockerbie | 2012-06-15 | 2012-06-11 | 2012-06-13 | OK | 2 | 2012-06-19 | 6 | TR | 2012-06-20
Kinknockie | 2012-06-15 | 2012-06-20 | 2012-06-21 | OK | 2 | 2012-06-28 | 7 | TR | 2012-06-29
Braishfield A | 2012-06-15 | 2012-06-19 | 2012-06-22 | OK | 3 | 2012-06-29 | 7 | TR | 2012-07-02
Pitcairngreen | 2012-06-15 | 2012-06-13 | 2012-06-15 | OK | 2 | 2012-06-21 | 6 | TR | 2012-06-21
Hardwick | 2012-06-15 | 2012-06-12 | 2012-06-15 | OK | 3 | 2012-06-18 | 3 | TR | 2012-06-20
Grain 2B | 2012-07-15 | 2012-07-24 | 2012-07-25 | OK | 2 | 2012-09-17
Armadale | 2012-07-15 | 2012-07-11 | 2012-07-12 | OK | 2 | 2012-07-17 | 5 | TR | 2012-07-27
Aberdeen | 2012-07-15 | 2012-07-10 | 2012-07-12 | OK | 2 | 2012-07-17 | 5 | TR | 2012-07-25
Shorne | 2012-07-15 | 2012-07-20 | 2012-07-25 | OK | 5 | 2012-07-26 | 1 | TR | 2012-07-27
Drum | 2012-07-15 | 2012-07-16 | 2012-07-18 | OK | 2 | 2012-07-30 | 12 | TR | 2012-07-31
Broxburn | 2012-08-15 | 2012-08-01 | 2012-08-02 | OK | 2 | 2012-08-03 | 1 | TR | 2012-08-13
Tatsfield | 2012-08-15 | 2012-08-13 | 2012-08-22 | OK | 9 | 2012-08-23 | 1 | TR | 2012-08-28
St Fergus | 2012-09-15 | 2012-09-26 | 2012-10-01 | OK | 5 | 2012-10-18 | 17 | TR | 2012-10-25
Nether Howcleugh | 2012-09-15 | 2012-08-27 | 2012-09-04 | OK | 7 | 2012-09-13 | 9 | TR | 2012-10-08
Wytch Farm (Sep) | 2012-09-15 | 2013-11-19 | 2013-12-20 |  |  | 2012-12-24 | 4
Glenmavis (Summer) | 2012-09-15 | 2012-09-26 | 2012-09-28 | OK | 2 | 2012-10-09 | 11 | TR | 2012-10-10
Grain 38B | 2012-09-15 | 2012-10-30 |  |  |  | 2012-12-10
Stranraer | 2012-10-15 | 2012-10-23 | 2012-10-26 | OK | 3 | 2012-11-02 | 7 | TR | 2013-11-05
Burnhervie | 2012-11-15 | 2013-11-19 | 2013-11-23 | OK | 4 | 2012-12-18 | 25 | TR | 2013-12-19
Didcot Bio | 2012-11-15 | 2012-11-19 | 2012-11-20 | OK | 1 | 2012-11-22 | 2 | TR
Langholm | 2012-11-15 | 2012-11-12 | 2012-11-15 | OK | 3 | 2012-11-23 | 8 | TR | 2013-11-29
2011
Site | Due date | Date started | Date complete | duration (days) | Report received | Report delay (days) | Plate pics received | Sent to UKT | Reason not sent yet
Grain 38B | 2010-10-04 | 2011-03-21 | 2011-03-22 | 2 | 2011-04-14 | 23 | N/A | Awaiting check / approval
Wytch Farm (Feb) | 2010-02-15 | 2011-03-14 | 2011-03-31 | 17 | 2011-04-13 | 13 | N |  | CP8a ??
Hume | 2010-03-15 | 2011-03-15 | 2011-03-29 | 14 | 2011-04-05 | 7 |  | 2011-04-08
Balgray | 2009-04-15 | 2011-04-05 | 2011-04-19 | 14 | 2011-05-10 | 21 | 2011-05-10 | 2011-05-17
Winkfield SE | 2009-05-15 | 2011-05-04 | 2011-05-26 | 22 | 2011-05-31 | 5 | 2011-05-09 | 2011-06-01
Mappowder | 2009-05-15 | 2011-05-18 | 2011-05-26 | 8 | 2011-06-02 | 7 |  | 2011-09-01
Careston | 2009-05-15 | 2011-05-04 | 2011-05-18 | 14 | 2011-06-03 | 16 | N/A | 2011-06-06
Winkfield SO | 2009-05-15 | 2011-05-05 | 2011-05-24 | 19 | 2011-05-31 | 7 | 2011-05-09 | 2011-05-31
Bathgate | 2009-05-15 | 2011-05-16 | 2011-05-18 | 2 | 2011-06-07 | 20 |  | 2011-06-08
Ipsden C/D | 2009-05-15 | 2011-05-16 | 2011-05-20 | 4 | 2011-06-28 | 39 | 2011-06-28 | 2011-07-06
Ipsden A | 2009-05-15 | 2011-05-23 | 2011-05-26 | 3 | 2011-06-28 | 33 | 2011-06-28 | 2011-09-01
Soutra | 2009-06-15 | 2011-05-31 | 2011-06-02 | 2 | 2011-06-16 | 14 | 2011-06-16 | 2011-06-21
Farningham | 2009-06-15 | 2011-06-06 | 2011-06-10 | 4 | 2011-06-16 | 6 | 2011-06-07 | 2011-06-16
Braishfield B | 2009-06-15 | 2011-07-06 | 2011-07-08 | 2 | 2011-07-11 | 3 | 2011-07-11 | 2011-07-12
Lockerbie | 2009-06-15 | 2011-06-13 | 2011-06-16 | 3 | 2011-06-20 | 4 | 2011-06-20 | 2011-07-01
Kinknockie | 2009-06-15 | 2011-06-01 | 2011-06-03 | 2 | 2011-06-17 | 14 |  | 2011-06-17
Braishfield A | 2009-06-15 | 2011-06-29 | 2011-07-01 | 2 | 2011-07-04 | 3 | 2011-07-04 | 2011-07-05
Pitcairngreen | 2009-06-15 | 2011-06-09 | 2011-06-14 | 5 | 2011-06-17 | 3 |  | 2011-06-17
Hardwick | 2009-06-15 | 2011-06-07 | 2011-06-09 | 2 | 2011-06-30 | 21 | 2011-06-30 | 2011-10-18
Grain 2B | 2009-07-15 | 2011-06-29 | 2011-06-30 |  | Read me
Armadale | 2009-07-15 | 2011-07-04 | 2011-07-06 | 2 | 2011-07-20 | 14 | 2011-07-20 | 2011-07-20
Aberdeen | 2009-07-15 | 2011-07-27 | 2011-07-29 | 2 | 2011-08-02 | 4 | 2011-08-02 | 2011-08-03
Shorne | 2009-07-15 | 2011-07-18 | 2011-07-22 | 4 | 2011-07-25 | 3 | 2011-07-25 | 2011-07-26
Drum | 2009-07-15 | 2011-07-14 | 2011-07-22 | 8 | 2011-08-02 | 11 |  | 2011-09-15
Broxburn | 2009-08-15 | 2011-08-01 | 2011-08-03 | 2 | 2011-08-12 | 9 | 2011-08-12 | 2011-08-18
Tatsfield | 2009-08-15 | 2011-08-22 | 2011-08-30 | 8 | 2011-08-31 | 1 | 2011-08-31 | 2011-09-02
St Fergus | 2009-09-15 | 2011-09-28 | 2011-09-30 | 2 | 2011-10-13 | 13 |  | 2011-10-17
Nether Howcleugh | 2009-09-15 | 2011-09-27 | 2011-09-30 | 3 | 2011-10-13 | 13 |  | 2011-10-17
Wytch Farm (Sep) | 2009-09-15
Glenmavis | 2009-09-15 | 2011-08-29 | 2011-09-01 | 3 | 2011-09-08 | 7 | 2011-09-08 | 2011-09-13
Stranraer | 2009-10-15 | 2011-10-24 | 2011-10-27 | 3 | 2011-11-10 | 14 |  | 2011-11-11
Grain 38B | 2009-10-15 | 2011-08-22 | 2011-08-29 | 7 | Read me
Didcot Bio | 2011-11-15 |  |  |  | Read me
Langholm | 2009-11-15 | 2011-11-07 | 2011-11-09 | 2 | 2011-11-14 | 5 |  | 2011-11-16
2010
Site | Due date | Date started | Date complete | Report received | Plate pics received | Master config used? | OMNI battery change complete?
Wytch Farm (Mar) | 2009-03-01 | 2010-04-13 | 2010-05-12 | 2010-05-20 | NO | NO
Hume | 2009-03-08 | 2010-03-15 | 2010-03-16 | 2010-03-22
Balgray | 2009-04-19 | 2010-04-01 | 2010-04-08 | 2010-05-21 | Y | Y
Winkfield SE | 2009-05-04 | 2010-05-20 | 2010-06-09 | 2010-06-10 | 2010-06-10 | Y | Y
Mappowder | 2009-05-10 | 2010-06-01 | 2010-07-05 | 2010-08-10 | 2010-06-07 | NO | Y
Careston | 2009-05-10 | 2010-05-11 | 2010-05-12 | 2010-05-27 |  | Y
Winkfield SO | 2009-05-10 | 2010-05-12 | 2010-05-24 | 2010-06-10 | 2010-06-10 | Y | N/A
Bathgate | 2009-05-17 | 2010-05-13 | 2010-05-26 | 2010-09-02
Ipsden C/D | 2010-05-17 | 2010-05-17 | 2010-06-23 | 2010-07-12 | 2010-07-12 | NO | Y
Ipsden A | 2010-05-24 | 2010-05-20 | 2010-05-27 | 2010-07-12 | 2010-07-12 | NO | Y
Soutra | 2009-06-01 | 2010-06-29 | 2010-06-30 | 2010-07-30 | 2010-07-30 | Y | Y
Farningham | #REF! | 2010-06-28 | 2010-07-13 | 2010-07-14 | N | Y | Y
Braishfield B | 2009-06-07 | 2010-06-07 | 2010-06-23 | 2010-07-19 | Y | NO | NO
Lockerbie | 2009-06-07 | 2010-06-23 | 2010-07-12 | 2010-09-13 | 2010-09-13 | Y | Y
Kinknockie | 2009-06-14 | 2010-06-22 | 2010-06-28 | 2010-08-19
Braishfield A | 2009-06-21 | 2010-09-23 | 2010-09-30 | 2010-10-19 | Y | NO | NO
Pitcairngreen | 2009-06-21 | 2010-06-03 | 2010-06-11 | 2010-08-19
Hardwick | 2009-06-28 | 2010-07-05 | 2010-07-08 | 2010-11-29 |  | NO | Y
Grain 2B | 2009-07-05 |  | 2010-07-01 | 2010-07-08
Armadale | 2009-07-05 | 2010-07-08 | 2010-07-13 | 2010-09-13 | Y | Y | Y
Aberdeen | 2009-07-19 | 2010-07-21 | 2010-07-27 | 2010-08-19 |  | Y | Y
Shorne | 2009-07-19 | 2010-07-20 | 2010-09-09 | 2010-09-13 | Y | Y | Y
Drum | 2009-08-09 | 2010-08-03 | 2010-08-04 | 2010-11-17 | Y | Y | Y
Broxburn | 2009-08-09 | 2010-09-28 | 2010-09-30 | 2010-11-15
Tatsfield | 2009-08-31 | 2010-09-14 | 2010-10-12 | 2010-11-01 | 2010-11-01 | Y | Y
St Fergus | 2009-09-06 | 2011-02-07 | 2011-02-09 | 2011-02-11
Nether Howcleugh | 2009-09-06 | 2011-01-10 | 2011-01-25 | 2011-01-31
Wytch Farm (Sep) | 2009-09-13
Glenmavis | 2009-09-13 | 2010-09-13 | 2010-09-20 | 2010-11-17 | 2010-11-17 | Y | Y
Stranraer | 2009-10-04 | 2011-02-04 | 2011-02-08 | 2011-02-10
Grain 38B | 2009-10-04 | Postponed
Langholm | 2009-11-01 | 2011-01-31 | 2011-02-02 | 2011-02-09
Didcot Bio |  |  | 2011-11-04
Note on A11: SGN: ME2 brought forward from July to April as per C.Moffatt
Note on A12: SGN: Due to USM project, ME2 brought forward from August to April
Note on B19: SGN: Moved to Aug 18 Due to lack of resoucres and site work
Note on B20: am55611: Was due 15/06/15…. Change requested by BR to 15/05/15
Note on B27: am55611: Was due 15/06/15…. Change requested by BR to 15/04/15
Note on A33: SGN: ME2 brought forward to April as per C.Moffatt
Note on A35: SGN: Due to USM project.. ME2 brought forward to April
Note on A68: SGN: ME2 brought forward from July to April as per C.Moffatt
Note on A69: SGN: Due to USM project, ME2 brought forward from August to April
Note on B77: am55611: Was due 15/06/15…. Change requested by BR to 15/05/15
Note on B84: am55611: Was due 15/06/15…. Change requested by BR to 15/04/15
Note on A90: SGN: ME2 brought forward to April as per C.Moffatt
Note on A92: SGN: Due to USM project.. ME2 brought forward to April
Note on D111: SGN: Confirmed with Shaun on 4/12/17. Due to pass /date for CP reading 17/12/2015
Note on B130: am55611: Was due 15/06/15…. Change requested by BR to 15/05/15
Note on B137: am55611: Was due 15/06/15…. Change requested by BR to 15/04/15
Note on B176: am55611: Was due 15/06/15…. Change requested by BR to 15/05/15
Note on B182: am55611: Was due 15/06/15…. Change requested by BR to 15/04/15
Note on C207: am55611: 13/02/14 Asked GD for start date: ME2 has been delayed 2/3 weeks due to NRO & Perenco…….Due to start 10.03.14
Note on C212: am55611: Extended by one month due to OP problems. Extended a further 3 weeks.
Note on D212: am55611: Problems with damaged Orifice Plate & delayed NRO also waiting on other Network to finish their works.
Note on D227: am55611: Witness report requested but not received yet...
Note on C237: am55611: W/o extended till 31/10/14 as per Asset Management. Further extension to 05/12.. ..ME2 planned to start 24/11 as per GD……(am 23/10)
Note on C238: am55611: W/o extended till 31/10/14 as per SJ. ME2 started 11/03/15 with SS witnessing.
Note on J256: am55611: 31/05 queries to BD
Note on C261: am55611: Str 2 June. Str 1 Aug 5th to 14th
Note on C263: am55611: Str 2 June. Str 1 22/7 to 2/8
Note on C267: am55611: Report not received yet .Dates taken from Site Log. Report rec'd 29.08. They apologised for the delay as they thought it had been sent.
Note on C271: am55611: Report not received yet .Dates taken from Site Log. Report rec'd 29.08
Note on C272: am55611: Report not received yet .Dates taken from Site Log.
Note on C276: am55611: Taken from site logs…14.11.13
Note on G276: am55611: Queries…..
Note on B278: am55611: KH requested delay from 15th Sep to 15th Oct.
Note on G278: am55611: Queries sent to RK 06.12.13. 25/02/14 Amended ME2 (CP3a/CP3b/CP10) received from RK. SS sent to UKT 26/02/14
Note on G280: am55611: Failed ME2. Amended, Approved ME2 received 20/01/14
Note on C281: am55611: Taken from site logs…
Note on C307: am55611: Dates taken from HPMIS Site Log.
Note on G307: am55611: Witness Report received 03.08.12 Unchecked report received from MG 17 Sep.
Note on G318: am55611: ME2 on 30.10.12. Witness Report received 05.11.12 ME2 Report received 10.12.12 not sure if Checked / Approved..???
Note on I327: am55611: MG sent to RK for checking 16.05.11
Note on F333: AM55611: Outstanding issues
Note on I338: AM55611: Queries on report - Queries resolved 8 Aug
Note on I346: am55611: Queries resolved 18.10.11
Note on F347: AM55611: Unchecked Report received 02.08.11 MB sent to RK for checking 02.08.11 SGN Witness Report received 02.08.11
Note on I351: AM55611: Queries on report. Resolved and sent 15.09
Note on F359: AM55611: MG awaiting report from GLNG as at 17.10.11. SGN Witness Report received 17.10.11 Unchecked / Unapproved ME2 results received 24.10.11 from MG. Returned to MG for checking / Approval.
Note on F360: am55611: ME2 complete but report with R Keat for checking as per B Dunn e.mail 11.01.12
Note on D397: am55611: Commissioning validation.