## Sheet1
Action Reference | Decision /Issue /Risk /Action | Description of Action | Meeting Target Date | Owner | Update | Status
01-0511 |  | 0789 Process: Model volumes that shippers would need to buy under 0789 if a med size and large size shipper were to fail, including application of trigger points | 2021-11-09 | NGG |  | Pending
02-0511 |  | 0789 Scenarios: Model cashflow impact on neutrality account for next meeting | 2021-11-09 | NGG |  | Pending
03-0511 |  | 0789 Scenarios: NGG to produce a timeline of when trades occur and the impacts on neutrality as it happens further down the line with and without any bad debt | 2021-11-09 | NGG |  | Pending
04-0511 |  | If National Grid were to buy the additional volumes, how can trading costs be recovered more quickly than under neutrality for the Residual Balancer role. | 2021-11-09 | NGG |  | Pending
05-0511 |  | NGG to check compliance with National Grid procurement activity with the EU Balancing Code | 2021-11-09 | NGG |  | Pending
06-0511 |  | Review of any Licence restrictions to NGG undertaking the procurement role | 2021-11-09 | NGG |  | Pending
07-0511 |  | 0789 Alternative: Proposer to review the solution and work with NGG in terms of the Residual Balancing role and the new ring fenced role | 2021-11-09 | N Wye |  | Pending
08-0511 |  | Consider the interaction with the GDE; what is being proposed and the worsening of the market situation. Demand Side interruption, if the volume has been given to shippers to procure and then NG interrupts supply. | 2021-11-09 | NGG |  | Pending

## Lookups
Action
Decision
Issue
Risk