## Sheet1
Item | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01
Shrinkage Forum Meetings | 2015-08-01: 19 Aug Tel Con; 2015-10-01: 27 Oct Face; 2016-02-01: 3 Feb Face; 2016-03-01: Telecon TBC; 2016-06-01: Telecon TBC; 2016-08-01: Telecon TBC; 2016-10-01: Telecon TBC; 2016-12-01: Telecon TBC; 2017-02-01: Telecon TBC
2016/17 Shrinkage Proposals | 2015-12-01: 31 Dec Initial Shrinkage Proposals Issued; 2016-01-01: Industry Consultation Period; 2016-02-01: Issue Resolution Period; 2016-03-01: 1 Mar Final Shrinkage Proposals Issued
2017/18 Shrinkage Proposals | 2016-12-01: 31 Dec Initial Shrinkage Proposals Issued; 2017-01-01: Industry Consultation Period; 2017-02-01: Issue Resolution Period; 2017-03-01: 1 Mar Final Shrinkage Proposals Issued
2014/15 Shrinkage Assessment and Adjustment | 2015-08-01: 31 August Neutrality Invoice issued to Xoserve; 2015-09-01: Neutrality Invoice processed by Xoserve
2015/16 Shrinkage Assessment and Adjustment | 2016-07-01: 31 July Publication; 2016-08-01: 31 August Neutrality Invoice issued to Xoserve; 2016-09-01: Neutrality Invoice processed by Xoserve
Annual Shrinkage and Leakage Model Review | 2015-08-01: Development; 2015-10-01: Industry Consultation Period; 2015-11-01: Consultation Review; 2015-12-01: 31 Dec Submission to Ofgem & Industry; 2016-08-01: Development; 2016-10-01: Industry Consultation Period; 2016-11-01: Consultation Review; 2016-12-01: 31 Dec Submission to Ofgem & Industry
Bi Annual Shrinkage and Leakage Smart Metering Report | 2015-09-01: Development; 2016-07-01: 31 July Submission to Ofgem & Industry
Special Condition 1F Part H:Revision in respect to Shrinkage Costs | 2016-03-01: DN Review/Development; 2016-07-01: 31 July Submission to Ofgem
Interference Damage Modification | 2015-08-01: Industry Discussion; 2015-09-01: Submission to Ofgem & Industry
AGI Venting Modification | 2015-08-01: DN Inventory Review; 2016-01-01: Development