## ME2's 2023
ME2 schedule 2023
Site Name | Meter Type | Validation Due | Validation complete | Report received | Checked by | Sent to NG | Comments Send to: meterassurance@nationalgrid.com
Aberdeen AGI (Offtake) | USM | 2023-03-15 | 2023-03-09 | y | ss | 2023-07-25
Hume AGI (Tracker) | Turbine | 2023-03-15 | 2023-03-07 | y | ss | 2023-07-25
Mitcham Bio | USM | 2023-03-15 |  |  |  | n/a
Ipsden A AGI (Offtake) | OP | 2023-03-15 | 2023-03-16 | Y | SS | 2023-04-26
Soutra | OP | 2023-03-15 | 2023-03-14 | y | ss | 2023-07-25
Kinknockie AGI (Offtake) | Turbine | 2023-04-15 | 2023-04-06 | Y | SS | 2023-07-25
Nether Howcleugh AGI (Offtake) | Turbine | 2023-04-15 | 2023-04-13 | Y | SS | 2023-07-25
Bathgate AGI (Offtake) | USM | 2023-05-15 | 2023-04-12 | Y | SS | 2023-07-25
Winkfield AGI SO (Offtake) | OP | 2023-05-15 | 2023-05-18 | Y | SS | 2023-07-25
Winkfield AGI SE (Offtake) | USM | 2023-05-15 | 2023-05-26 | Y | SS | 2023-07-25
Ipsden B AGI (Offtake) | OP | 2023-05-15 | 2023-06-09 | Y | SS | 2023-07-25
Mappowder AGI (Offtake) | OP | 2023-05-15 | 2023-06-29 | Y | SS | 2023-07-25
Careston AGI (Offtake) | Turbine | 2023-05-15 | 2023-05-24 | Y | SS | 2023-07-25
Armadale AGI (Offtake) | OP | 2023-05-15 | 2023-05-24 | Y | SS | 2023-07-25
Braishfield A AGI (Offtake) | USM | 2023-06-15 | 2023-08-08 | y | ss | 2023-10-12
Braishfield B AGI (Offtake) | USM | 2023-06-15 | 2023-07-28 | y | ss | 2023-10-12
Farningham AGI B (Offtake) | USM | 2023-06-15 | 2023-06-29 | Y | SS | 2023-10-12
Hardwick AGI (Offtake) | USM | 2023-06-15 | 2023-07-25 | Y | SS | 2023-10-31
Farningham AGI A (Offtake) | USM | 2023-06-15 | 2023-07-20 | Y | SS | 2023-07-25
Lockerbie AGI (Offtake) | OP | 2023-06-15 | 2023-06-21 | y | SS | 2023-10-12
Isle Of Grain MP (Offtake) | Turbine | 2023-07-15 |  |  |  | n/a
Shorne AGI (Offtake) | OP | 2023-07-15 | 2023-08-07 | Y | ss | 2023-10-12
Broxburn AGI USM (Offtake) | USM | 2023-07-15 | 2023-08-20 | Y | SS | 2023-10-31
Drum AGI (Offtake) | USM | 2023-07-22 | 2023-04-27 | y | ss | 2023-10-12
Glenmavis (Offtake) | USM | 2023-08-15 | 2023-05-30 | Y | SS | 2023-10-12
Tatsfield AGI (Offtake) | USM | 2023-08-21 | 2023-10-02 | Y | SS | 2023-10-12
Pitcairngreen AGI (Offtake) | Turbine | 2023-09-15 | 2023-04-12 | y | ss | 2023-10-12
Portsdown Hill 1 | Turbine | 2023-09-15
Portsdown Hill 2 | Turbine | 2023-09-15
Portsdown Hill 3 | Turbine | 2023-09-15
Portsdown Hill 4 | Turbine | 2023-09-15
Portsdown Hill 5 | Turbine | 2023-09-15 | 2023-10-17 | Y | SS | n/a
St Fergus AGI (Offtake) | Turbine | 2023-09-15 | 2023-09-19 | Y | SS | 2023-10-31
Isle Of Grain LP (Offtake) | Turbine | 2023-10-09 |  |  |  | n/a
Balgray AGI (Offtake) | USM | 2023-10-15
Poundbury | USM | 2023-10-15
Stranraer AGI (Tracker) | Turbine | 2023-10-15
Apsley Farm | USM | 2023-11-10
Langholm AGI (Tracker) | Turbine | 2023-11-15
Burnhervie AGI (Offtake) | USM | 2023-11-15
St. Nicholas Court Farm | USM | 2023-12-15
Coupar Angus | USM | 2023-12-15
Girvan Biomethane | USM | 2023-12-15
Comments
Suspended