## Sheet1
Action/Issue Reference | Decision/Issue/Risk/Action | Description of Action | Target Date | Owner | Update | Status
2901-01 | Issue | Section 3.26.1 of Mod 0678 and the impact of top-up charges on existing contracts and compliance with the TAR NC Article 35. |  | SSE (JCh) |  | Pending
2901-01 | Action | National Grid to consider the impact of top-up charges on existing contracts and compliance with the TAR NC. |  | National Grid Colin Williams (CW) |  | Pending
2901-02 | Action | Article 35: Joint Office to consider the topic list and confirm whether Article 35 fits into the timetable. Suggested for 31 January meeting under Revenue Recovery. |  | Joint Office |  | Pending
2901-03 | Action | Workgroup to consider existing contracts and any potential discriminatory aspects relating to storage capacity (reference rules being developed under Modification 0662). |  | Workgroup |  | Pending
2901-04 | Action | National Grid to consider the consistent presentation of charges to enable comparative analysis of Alternatives. |  | National Grid Colin Williams (CW) |  | Pending
2901-05 | Issue | Regulatory Impact Assessment – impact on customers.
2901-05 | Action | Workgroup to consider the requirement to provide a regulatory impact assessment. |  | Workgroup |  | Pending
2901-06 | Action | National Grid to consider traded capacity contracts and exposure to the capacity uplift charge and when it would attract the revenue recovery charge and if this was intended for this modification |  | National Grid Colin Williams (CW) |  | Pending
2901-07 | Action | Ofgem to provide a formal View on the feasibility of achieving 01 October 2019 implementation date and the impact of not achieving this date and being compliant as soon as possible. (JO to action this) |  | Ofgem David O'Neil (DON) |  | Pending
2901-08 | Action | Workgroup to review the draft Workgroup Report at the end of each session and provide any updates ahead of the start of the next session/meeting. |  | Workgroup |  | Pending

## Lookups
Action
Decision
Issue
Risk