## Sheet1
Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 | Step 7 | Step 8 | Step 9
MDD Market Participant ID Application Verification Initiation (exclusing Shipper UA steps which are described in the verification guidelines) | MP ID Application Verification Conclusion by CDSP (-5 WD from step 3) | Collated MP Id Request Document Published (-10 Working Days from step 4) | Representation / Comments Deadline (-5 WDs from step 5) | DSC MP ID Sub Committee | DSC MP Id Sub Committee Outcome Published (+2 WD from Step 5) | DSC Contract Management Committee – (Opportunity to challenge DSC MP Id Sub Committee Outcome) | Appeal Expiry Date (+10 WDs from Step 7) | MDD Release Go-Live date (+5 WD from Step 8) | Comments
2019-12-03 | 2019-12-10 | 2019-12-17 | 2019-12-31 | 2020-01-07 | 2020-01-09 | 2020-01-15 | 2020-01-29 | 2020-02-05
2020-01-07 | 2020-01-14 | 2020-01-21 | 2020-02-04 | 2020-02-11 | 2020-02-13 | 2020-02-19 | 2020-03-04 | 2020-03-11
2020-02-04 | 2020-02-11 | 2020-02-18 | 2020-03-03 | 2020-03-10 | 2020-03-12 | 2020-03-18 | 2020-04-01 | 2020-04-08
04/03/2020* | 13/03/2020* | 20/03/2020* | 03/04/2020* | 2020-04-14 | 2020-04-16 | 2020-04-15 | 2020-04-29 | 07/05/2020* | Proposing to publish outcomes of sub-committee on same day rather than +2 days - as CoMC falls before the publish date for Step 6
2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-05-05 | 2020-05-12 | 2020-05-14 | 2020-05-20 | 04/06/2020* | 11/06/2020*
01/05/2020* | 11/05/2020* | 18/05/2020* | 2020-06-02 | 2020-06-09 | 2020-06-11 | 2020-06-17 | 2020-07-01 | 2020-07-08
2020-06-09 | 2020-06-16 | 2020-06-23 | 2020-07-07 | 2020-07-14 | 2020-07-16 | 2020-07-15 | 2020-07-29 | 2020-08-05 | Proposing to publish outcomes of sub-committee on same day rather than +2 days - as CoMC falls before the publish date for Step 6
2020-07-07 | 2020-07-14 | 2020-07-21 | 2020-08-04 | 2020-08-11 | 2020-08-13 | 2020-08-19 | 03/09/2020* | 10/09/2020*
2020-08-04 | 2020-08-11 | 17/08/2020* | 2020-09-01 | 2020-09-08 | 2020-09-10 | 2020-09-16 | 2020-09-30 | 2020-10-07
2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-10-06 | 2020-10-13 | 2020-10-15 | 2020-10-14 | 2020-10-28 | 2020-11-04 | Proposing to publish outcomes of sub-committee on same day rather than +2 days - as CoMC falls before the publish date for Step 6
2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-11-03 | 2020-11-10 | 2020-11-12 | 2020-11-18 | 2020-12-02 | 2020-12-09
2020-11-03 | 2020-11-10 | 2020-11-17 | 2020-12-01 | 2020-12-08 | 2020-12-10 | 2020-12-16 | 04/01/2021* | 11/01/2021*