## Slide 1: Xoserve IX Refresh
Customer Update
November 2020

## Slide 2: IX Refresh Customer Update
The project has not seen any impact so far following the recent announcement of a second COVID-19 lockdown
The project end date is February 2021. Our current run rate is tracking a January 2021 completion
The project is targeting to complete all physical installations by 30th November. Currently there are 8 sites (5%) that are at risk of missing this date
Project team have engaged with our legacy service to secure extension terms, if needed.
  Agreement in place to extend support past February 2021
  Minimum 3-month extension
  A decision will be made mid-December
  Project needs customer support to ensure all remaining sites are migrated by February
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com