## Slide 1: Amendment Invoice Update

## Slide 2: Summary
Merged ASP & AML files issued to customers for the first time for the November 2019 Billing Period.
A rare Primes & Sub deduct meter scenario was not captured as part of the ASP file merge activity and this resulted in an ASP mismatch for 12 MPRNs affecting 6 customers.
All 6 customers affected had an ASP mismatch file issued 3 business days prior to the invoice Payment Due Date.
Cataloguing of Exception resolution process steps significantly behind schedule. Plan was originally to be completed by end of Dec-19. Revised plan has a completion date of end of Feb-20.
Defect resolution and deployment has been affected by re-prioritisation and focus on AQ issues and code object locks for November 19 release plus a larger than normal volume all with the same SLA date of 6th Dec causing a few bottle necks through-out the process. RTG forecast to be mid January.

## Slide 3: Summary Resolution Plan
Apr
May
Jun
Jul
Aug
Sept
Mobilise
Oct
Nov onwards
ASP / AML Mismatches
Exclusions
Defects
MI / Reporting
Backlog Clearance
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
RCA activities
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
Backlog Clearance
Operating within SLA
Deploy MI solution
Operating within SLA
Exceptions (LSPs)
Exceptions (SSPs)

## Slide 4: Supporting Information Mismatches
SLA
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Green
RAG Justification
110 MPRNs out of the 235,402 LSPs (0.05%) that were billed incurred an ASP mismatch. File merge activities reduced the mismatch to 12 MPRNs affecting 6 customers. December 2019 files will be updated to include the Primes & Subs scenario.
100 % of ASP offline correction files issued 3 days prior to PDD.
Merged ASP & AML files issued to customers for 1st time. 6 customers still required an ASP correction file.
Merged ASP file to be updated to include the Primes & Subs scenario for the December 2019 billing period.

## Slide 5: Exceptions
SLA
Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
RED
RAG Justification
Exception backlog clearance continues to trend downwards. Despite reductions in backlog exceptions, the number of LSP and SSP reconciliations held off the AMS as a result of an exception remains high. Exceptions MI now shared with customers and analysis underway as to how best utilise this data for improved exception resolution.
What is an exception?
Business or Technical processing errors generated within our system, that cause reconciliations at individual sites, to be held back off the Amendment Invoice until resolved.
124,1552 distinct MPRNs currently have unresolved exceptions within our systems (as of 31st Dec).
(Aug-19 = 442,074, Sep-19 =147,489, Oct-19 = 179,165)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers.

## Slide 6: Exclusions
SLA
Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection.
Target Date to operate within SLA
July 2019
Current SLA RAG Status
AMBER
RAG Justification
c.20,000 distinct sites released from bill blocks over the last three months. Cataloguing of all scenario resolution steps to ensure accuracy remains a key focus
What is an exclusion?
Until permanent system fixes are deployed to address charge calculation errors, monthly profiling of new reconciliations received that relate to the scenario of the open defect is performed, with “bill blocks” applied to that MPRN to safeguard the accuracy of the amendment charge calculations by exclusion from the AMS.
247 distinct MPRNs for the October billing period currently have bill blocks placed upon them (as at 30/11/19)
(Aug-19 = 2,696, Sep-19 = 8,503, Oct-19 = 1,245)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers

## Slide 7: Defects
SLA
Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
RED
RAG Justification
9 Amendment invoice impacting defects open as of 2nd Jan-20. 3 Defects did not meet the December SLA: 1458 – Defect put on hold due to November release. Due to be deployed 04/01/2020 1429 – had additional scenarios added at a late stage of the defect process due to MOD700, then failed assurance on 2 occasions – currently awaiting clarification with potential deployment 17/01/2020 1449 – Defect put on hold due to November Release – currently in UAT execution with potential deployment 31/01/2020
9 open ASP/AML related defects as of 2nd Jan-20
(8 defects open at last month’s update)
54 defects (all process areas) awaiting fix deployment
Defect ID | Defect Title | Date Detected | Target Fix Date | SLA Resolution Date
1333 | DM REC financial mismatches in Amendment supporting file | 27/03/2019 | TBC | 31/08/2019
1429 | RGMA activity has performed both class 3 normal rec and Check to Check reconciliation. This should have ideally triggered only Check to Check rec since DRE or AMR are registered. | 24/07/2019 | 17/01/2020 | 04/10/2019
1449 | RGMA activity received in a class 4 period post class change from class 2 to class 4 calculates incorrect volume. | 03/09/2019 | 31/01/2020 | 08/11/2019
1458 | Issue with class 3 read upload process - Non-opening read is inserted between two reads through UBR process and next read has a TTZ of 1, volume is calculated incorrectly through UBR process | 13/09/2019 | 04/01/2020 | 06/12/2019
1477 | Incorrect variance Energy created after NDM prime reconciliation and net off volume and energy getting populated with 0 | 11/10/2019 | 10/01/2020 | 10/01/2020
1495 | Class 3 - Incorrect volume calculation when class change read is estimated with TTZ1 | 15/11/2019 | 24/01/2020 | 07/02/2020
1501 | Incorrect TTZ getting calculated on next read when last read and next read is estimated | 29/11/2019 | 07/02/2020 | 07/02/2020
1503 | Incorrect Class 4 Rec | 29/11/2019 | 07/02/2020 | 07/02/2020
1513 | MR15 exception not created when the variance volume was negative but total volumes was positive and vice versa | 17/12/19 | 21/02/2020 | 06/03/2020

## Slide 8: MI / Reporting
SLA
All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Green
RAG Justification
Reports shared with all customers and general and individual WebEx’s are ongoing
MI reports continue to be shared with our customers 2 business days after Amendment invoice issue date.
Ongoing WebEx’s are being held to discuss general questions our customers have with the reports.
Ongoing individual customer WebEx's to discuss what the MI means specifically to them.

## Slide 9: Summary Resolution One Pager
Mismatches | Exceptions | Exclusions | Defects | MI / Reporting
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age. | Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old. | Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection. | Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised. | All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA |  |  |  | 
September 2019 | August 2019 | July 2019 | August 2019 | August 2019
Current SLA RAG Status |  |  |  | 
GREEN | RED | GREEN | RED | GREEN
RAG Justification |  |  |  | 
Merged ASP & AML files issued for the 1st time for November 2019 Billing Period. Primes & Subs scenarios resulted in 12 MPRNs with ASP mismatch affecting 6 customers. All 6 customers had ASP corrections delivered 3 days prior to Payment Due Date Merged files to be updated to capture the Primes & Subs scenario for December 2019 Billing Period. | Despite reductions in backlog exceptions, the number of LSP and SSP reconciliations held off the AMS as a result of an exception remains high. Glidepath for clearance of backlog and transition exceptions on track for Feb-20 (SSP Glidepath attached as an appendix) Cataloguing all scenario resolution steps to ensure accuracy | c.25,000 distinct sites released from bill blocks over the last six months. | 9 Amendment invoice impacting defects open as of 2nd Jan-20. 3 Defects have not meet their SLA dates. Affected by re-prioritisation focus on AQ issues and code object locks for November 19 release Return to Green (RTG) forecast is for mid Jan 2020 for all defect types | Reports shared with all customers 2 business days after Amendment invoice issue date. Ongoing WebEx’s are being held to discuss general questions our customers have with the reports Ongoing individual customer WebEx's to discuss what the MI means specifically to them

## Slide 10: Wipro SSP Exceptions Backlog & Transitions - SLA FEB 2020 – as at 1st January
Overall Delivery Status |  | Current Workstream Health Metrics |  |  |  | 
Overall Status | Trend | Performance VS plan | Risk Profile | Resourcing | Readiness BAU | Benefits SLA contribution
On track; no slippage or concerns
Monitor closely, some slippage
Urgent and decisive action required
Key:
Static
Declining
Improving