## Sheet1
Methodology Issues
Issue Ref. | Issue Title | Issue Originator | Date Created | Status | Priority for Discussion (H/M/L) | Status Date | Status Summary
M001 | Methodology document needs to include aggregate or sum of in every section for clarity, else divide by number of days makes no sense | Energy UK | 2019-06-04 | Live
M002 | It is not clear if future annual bookings are considered? | Energy UK | 2019-06-04 | Live
M003 | Justification of selection of parameters as per TAR NC article 26 1 (a) i, is absent | Energy UK | 2019-06-04 | Live
M004 | There is no justification provided for a different approach for GDN offtakes Y-1 vs Y -2 at all other offtakes, this allows adjustments up/down to be reflected more rapidly in GDN values than for other sites | Energy UK | 2019-06-04 | Live
M005 | Why are PARCA reservations / bookings are not incorporated into the GDN FCC values | Energy UK | 2019-06-04 | Live
M006 | The use of Y-1 seems to implicitly assume no short-term bookings by GDNs – can this be demonstrated / guaranteed, Does UNC prevent DN Users from making short term bookings? | Energy UK | 2019-06-04 | Live
M007 | Updated Forecast – appears to be a defined term, is it defined in the new legal text, it is not in the current UNC defined terms listings? | Energy UK | 2019-06-04 | Live
M008 | Does the Updated Forecast relate to a particular scenario? | Energy UK | 2019-06-04 | Live
M009 | Is it a peak day forecast? | Energy UK | 2019-06-04 | Live
M010 | The GTYS charts and data SS does not contain data at the granularity required for FCC | Energy UK | 2019-06-04 | Live
M011 | How are site specific values determined? | Energy UK | 2019-06-04 | Live
M012 | What values are used for new sites, without a PARCA reservation? | Energy UK | 2019-06-04 | Live
M013 | Exceptions in Chapter 4: a means to deal with difficult issues but does not seem to have been applied to FCC in ss NG specifically says it is not using exceptions, but will do later for actual charges – presumably in some unpredictable random way | Energy UK | 2019-06-04 | Live
M014 | No assurance process to ensure accuracy, consider adding one(within year?) review for RRC purposes | NTSCMF RWE | 2019-06-04 | Live
M015 | Consider adding (within year?) review for RRC purposes | NTSCMF Eni | 2019-06-04 | Live
Values Issues
V001 | Storage sites am interconnectors still have no forecast values – which leads to a query of the forecast used | Energy UK | 2019-06-04 | Live
V002 | Avonmouth refill,, Deeside (www.tritonpower.co.uk/deeside), Rough injection, Glenmavis injection, Gowkhall ( Longannet), Dynevor refill, Rough refill, have FCC values for all 6 years from flows or bookings in 2017/18, but are closed – surely this should be covered by exception rule? | Energy UK | 2019-06-04 | Live
V003 | Bacton GDN – it is not clear if the FCC includes the PARCA capacity from 1/3/21 , FCC falls then is flat | Energy UK | 2019-06-04 | Live
V004 | Ipsden and Ipsden 2 have PARCA bookings from 1/2/19 but the FCC values are below these | Energy UK | 2019-06-04 | Live
V005 | Keadby blackstart has 0 forecast values until 2022 then sizeble values appear? | Energy UK | 2019-06-04 | Live
V006 | Mappowder 19/20 FCC is below PARCA quantity | Energy UK | 2019-06-04 | Live
V007 | Peterborough EYE (TEE) and Silk Willoughby not clear that PARCA bookings from 1/3/21 are included in FCC values which are flat at the booked level of 17/18 | Energy UK | 2019-06-04 | Live
V008 | Peterhead has no forecast from 2022, so is assumed to close ? | Energy UK | 2019-06-04 | Live
V009 | Knottingley PS has forecast values from 2022 ,but no PARCA | Energy UK | 2019-06-04 | Live
V010 | Hirwuan PARCA reservation should start on 1/10/20 |  |  | Closed
V011 | Drax PARCA reservation values are missing |  |  | Closed
V012 | Tilbury Marshes is missing but has PARCA reservation from 1/12/20 |  |  | Closed
V013 | Treatment of Theddlethorpe and Caythorpe needs considering | Energy UK | 2019-06-04 | Live