## Issue Tracking List
ISSUE TRACKING LIST
WORKGROUP | 0849R
PROJECT NAME | Commercial Framework Review to Enable Hydrogen Blending
Issue Tracker Owner | Megan Bray - megan.bray@nationalgas.co.uk
ISSUE NO. / TITLE | DATE CREATED | DESCRIPTION | ASSOCIATED ACTION | STATUS | WITHIN 0849R SCOPE? | COMPLETION DATE | RAISED BY | COMMENTS | OUTCOME | CLOSE
1a- Deblending | 2023-06-19 | Do we need to consider de-blending commercial framework as part of this workgroup? If not who will be looking at this and when? | Action 11 | Created | ? |  |  | Issue's list for commercial framework changes to support deblending created. Agree if these issues should be included in 0849R scope or kept separate.
1b- CCGT compatibility with H2 blend | 2023-06-19 | CCGT’s Operation can only burn up to 2-5% H2 blend. Beyond this they are not covered by OEM warranties. | Action 1 | Created | depends on above? |  |  | As above.
1c- Blend variability | 2023-07-20 | If blending used for reserve offtake role, blend % variability will be likely. How will this impact Industrial end users. | Action 1 | Under Review | HSE |  |  | Progressive Energy blend acceptability study is reviewing this.
3- CCUS | 2023-06-19 | DESNZ want CCUS networks to be fully utilised, with possibility of penalties if they are not. |  | Created | No? |  |  | Change to comment- DESNZ commented blending to be used as reserve offtaker or interim solution before 100% H2 demand is ready.
4a- Interconnectors | 2023-06-19 | EU blending strategy likely to differ from UK, therefore, require solution for H2 blend volumes across IP’s in order to continue trading |  | Monitor | Yes for Transmission only |  |  | NG are scoping EU-UK Strategy paper to review the certainties and unknowns for EU strategy and where alignments and interjurisdictional coordination with UK strategy is required.
4b- European Interconnector Document | 2023-07-18 | Any changes made to UNC may impact EID, or may require changes in EID. | Action 6 | Created | Yes
5- Reverse Compression | 2023-06-19 | Reverse compression MOD 808 , concerns over impacts to a blended gas being transported. |  | Monitor | Potentially |  |  | MOD currently in discussion looking at Reverse compression between Tx and Dx networks which could impact blend cap management. This will need to be monitored and considered if MOD is raised.
6- Connection Agreements | 2023-06-19 | Industrial users that have connection agreements in place have to warrant that site is safe for offtake of gas, this is specifically around Methane, therefore adaptation will be required, this will need to be reviewed by HSE? |  | Resolved | No (HSE) |  |  | NExA point to standard offtake requirements in code | This will sit under the HSE Safety case remit and therefore does not require further review under 0849R
7- Control of Major Accidents Hazard (COMAH) | 2023-06-19 | Timeline for HSE to review Control of major accident hazards (COMAH) safety approvals would need to be considered within roll out plan |  | Resolved | Consideration for Implementation timeline. Within HSE safety case scope. |  |  | This point impacts timescales the roll out of blending but does not need to be considered within the scope for 849R | This will sit under the HSE Safety case remit and therefore does not require further review under 0849R
8- GCOTER | 2023-06-19 | Other aspects of GCOTER include gas temperature, pressure correction and compressibility factor. Has this been covered adequately within Hydeploy programme, does it need to be further considered within 849R? | Action 2 | Under Review | Hydeploy report. HSE safety case scope. |  |  | This will be considered within the HSE safety case review, report covering this has been covered within Hydeploy project, Cadent to share once complete. Also work completed by Dave Lander looks at this, Dave has offered to present this data to the group in September.
9- Limitation to blend volume percentages | 2023-06-19 | Consideration as to how lower limits of blend volume percentage for initial injections coud be outlined? Through code or agreed within Connection Agreements? |  | Created | HSE |  |  | This will be considered within the HSE safety case review and a steer provided as to whether this sits within code or elsewhere.
10- Changes to Existing NEA's to enable blending | 2023-06-19 | More transparency required on changes to existing NEA’s for Distribution Networks as current framework requires no MOD or industry consultation for this. Information such as agreed maximum blend volume to be shared with those impacted further downstream. |  | Created | Yes |  |  | Whats important to end users here, what information do they want? Review work currently being completed on Gas Quality. Blend points likely to be new NEA's. Refer to actions 9 an 10.
11- New NEA's for blending | 2023-06-19 | Currently no MOD or industry consultation required for new NEA's (Tx & Dx). More transparency required to include agreed maximum blend percentages and impacts on parties downstream. |  | Created | Yes |  |  | Considerations for this have been explored in Future Billing Methodology. Also review any considerations within RIIO3 team. Refer to Actions 9 and 10.
12- Blend Cap Management | 2023-06-19 | Existing constraint management tools are mainly for turning down flows, do we require additional tools for when flows need to be increased to manage H2 blending? | Action 7a & 7b | Created | Yes |  |  | Is this more for maximised blending rather than initial connections? (phase 2 consideration)
13- Command and Control | 2023-06-19 | Technical solution required within NEA to ensure maximum H2 blend rates are not exceeded. Require a tool to guarantee a change in flow before emergency phase is reached. Could onsite storage be solution for this? |  | Created | Yes |  |  | Agree, this needs to be called out in NEA.
14- Delivery Facility Operators | 2023-06-19 | Review who DFO’s would be for injecting H2 blend, particularly for entry points with multiple connections. |  | Under Review | Yes |  |  | F.Specs report outlines this, to be reviewed in August review group.
15- Buffer Service | 2023-06-19 | Buffer service (i.e storage, linepack) provided by TSO’s, could this be outlined in code/ agreed within connection agreement as a service to support maximisation of H2 production? |  | Resolved | Yes |  |  | This would impact blend cap, and would be restricted making it difficult to offer as a service.
16- NExA Safety Case/ Data Sheets | 2023-07-18 | Safety case/ data sheets for NExA's may refer to Methane, therefore these will need to be reviewed to include a blended gas. |  | Created | HSE?

## Actions Tracking List
ACTIONS TRACKING LIST
WORKGROUP | 0849R
PROJECT NAME | Commercial Framework Review to Enable Hydrogen Blending
Actions Tracker Owner | Megan Bray - megan.bray@nationalgas.co.uk
ACTION NO. / TITLE | DATE CREATED | DESCRIPTION | ASSIGNEE | STATUS | PRIORITY | RAISED BY | COMMENTS | OUTCOME (so what) | CLOSE
1- CCGT's | 2023-06-19 | Check CCGT’s are included in Progressive Energy study looking at Hydrogen Acceptability. | Megan Bray | In-progress |  |  | All gas handling technology archetypes will be considered within the PE Accessibility Study, these have been agregated from a list of direct connected sites to the NTS and will cover CCGT equipment. Interviews will then be conducted with relevant industrial customers regarding each archetype and their compatibility with a Hydrogen blend of up to 20% including variability. | Megan and Julie Cox to discuss archetype and survey methodology for H2 acceptability study offline. The outputs of this work to be shared with industry upon completion and any issues identified to be considered for framework changes. | Yes
2- GCOTER | 2023-06-19 | GCOTER includes gas temperature, pressure correction and compressibility factor. Check this is adequately covered within Hydeploy (DN's). Confirm when report will be completed and share with group. | DN'S | In-progress |  |  | Report covering additional specifications such as gas temperature, pressure correction and compressibility factor is being completed within the Hydeploy programme and will be submitted to HSE as part of the safety case evidence. Report is still being developed, Cadent to share once complete. - Dave Lander has offered to present on findings from previous consumer billing report on this and update group. - Eric Fowler also raised enquiry with IGEM gas measurement committee- it was suggested for 5% blend in pressures upto 2bar effects would be immaterial, however this may need to be considered in higher pressures as well as effects of variability. |  | Yes
3a- Existing NExA gas specifications | 2023-06-19 | Check there are no direct gas specifications included in existing exit agreements. If 0.1% Hydrogen content is specifically referenced, this will need to be changed through appropriate method developed and agreed within this review group. | DN's Megan Bray | In-progress |  |  | DN's and Transmssion currently checking NExA's for specific Hydrogen content reference. | SGN and Cadent completed check and identified no direct H2 content reference.
3b- Existing NExA (reference to GS(M)R) | 2023-06-19 | Alternatively existing NExA's may point to GS(M)R (likely to change to 20% H2 content) check if this is the case where specific H2 contents is not referenced. | DN's Megan Bray | Created |  |  | If yes, this leads into deblending issues list and the requirement for an application process for customers to request specific gas quality from network operators and the relevant evidence to justify this requirement.
3c- Safety case/ data sheets | 2023-07-18 | Check whether NExA safety case and data sheets reference Methane specifically. | DN's Megan Bray | Created |  |  | If these include specific reference to Methane they would need to be updated to cover a blended gas. Would this sit with HSE Safety case review instead? | Does this issue sit within HSE Safety Case Review?
5a- GT License exemption for Hydrogen DFO (NTS) | 2023-06-19 | Check if DFO injecting Hydrogen into NTS as a pre-blend would require a GT License exemption. Liase with Ofgem for clarification and refer to consultation (Gas Transporter Licence Exemption for Onshore Production of Gas) | Megan Bray | Created |  |  | Review referenced consulation and liase with Ofgem as to whether H2 producers could utilise the exemption. The exemption proposes a class exemption to remove the requirement to hold a transporter licence for a person who conveys gas that is produced or extracted onshore (e.g. biomethane, unconventional and conventional) to the gas grid (pipe-line system operated by a licenced gas transporter).
5b-GT License exemption for Hydrogen DFO (DN) | 2023-06-19 | Check if DFO injecting Hydrogen into Distribution Network as a pre blend, would require a GT License exemption. (refer to arrangements for Bio Methane plants) | DN's | Created |  |  | (As above) The current arrangements for biomethane sites are managed through the Network Entry Agreements (copy attached for reference ), which form part of the License. The License doesn’t outline a process for modifying NEAs, NGN make revisions as and when needed. The NEAs and the obligations within ensure that any gas entering the system complies with GS(M)R in terms of gas quality. The blending limit may also be managed through an NEA for each hydrogen production site, this could potentially be different for each site, dependent on where they are connected to the network and if there’s another facility nearby. Biomethane sites have to be Ofgem Directed CV measurement sites with a CV measurement point of the embedded connection. If the billing methodology remains as it is then the same would need to be in place for hydrogen blends.
6- European Interconnection Document | 2023-06-19 | Review EID to check if/where there may be cross over and requirement for amendments. | Megan Bray | Created
7a- Managing the H2 blend cap (decrease in H2 availability) | 2023-07-18 | If H2 blend percentage needs to remain consistent, how could a loss in H2 supply be managed? | Networks | Created |  |  | Do we agree H2 producers will need to supply a constant blend or are we accepting it will be variable but with mitigating mechanisms in place for sensitive users? (i.e de-blending).
7b- Managing the H2 blend cap (when limited NG to blend) | 2023-07-18 | Review potential mechanism to manage blend cap where constraint on the network limits natural gas flow to blend. | Networks | Created |  |  | In terms of gas quality safety a Terminal Flow Advisory can be submitted to stop injection, however where a network constraint reduces availability of N.gas to blend, is there a mechanism that could guarantee an increase in flow of N.gas before capacity buy-back is utilised..
8- Clarification on the role of H2 Blending into networks (reserve offtaker or maximised production) | 2023-06-19 | Clarify with DESNZ whether H2 blending producers will be incentivised to maximise H2 production for blending or whether it will only be used as a reserve offtaker. If only reserve offtaker, does that H2 producer have the right to inject all of H2 reserve into networks, or is it down to network discretion/ capability? | DN's | Continue to review following DESNZ consultation. |  |  | Likely initial blending connections will be those with a HBM. DESNZ plan to run case by case assessment for HBM funding and forsee that blending will be utilised as reserve offtaker where Hydrogen Producers main demand is 100% H2 consumer, or blending may be utilised as an interim solution where production goes live before the demand is connected and ready. HBM's are still being considered in terms of roll out and assessment criteria.
9- Gas Quality changes in existing and new NTS NEA's | 2023-06-19 | Review previous ‘Implementing the Proposed Gas Quality Standards’ work programme and assess if outputs from this work can give guidance on how a gas quality change within existing and new NEA’s could be manged for a blended gas. | Megan Bray | Created
10- Gas Quality changes in existing and new DN NEA's | 2023-06-19 | Review GGG work looking at Gas Quality Data Provision and the recommendations from this to assess how we can enhance gas quality changes within existing and new Distribution NEA’s for blending. | DN's | Created
11- De-blending | 2023-07-18 | Frontier Economics paper outlines high-level commercial framework changes to enable de-blending. Liase with Ofgem/DESNZ/HSE whether this should considered alongside blending. If so who would be responsible for ownership of the de-blending facilities. | Megan Bray | Created
12- Assumptions | 2023-07-18 | Review updated assumptions during each session | Megan Bray | Created