## Issue Tracking List
ISSUE TRACKING LIST
WORKGROUP | 0849R
PROJECT NAME | Commercial Framework Review to Enable Hydrogen Blending
Issue Tracker Owner | Megan Bray - megan.bray@nationalgas.co.uk
ISSUE NO. / TITLE | DATE CREATED | DESCRIPTION | ASSOCIATED ACTION | STATUS | WITHIN 0849R SCOPE? | COMPLETION DATE | RAISED BY | COMMENTS | OUTCOME | CLOSE
1a- Deblending | 2023-06-19 | Do we need to consider de-blending commercial framework as part of this workgroup? If not who will be looking at this and when? | Action 11 | Created | ? |  |  | Issue's list for commercial framework changes to support deblending created. Agree if these issues should be included in 0849R scope or kept separate.
1b- CCGT compatibility with H2 blend | 2023-06-19 | CCGT’s Operation can only burn up to 2-5% H2 blend. Beyond this they are not covered by OEM warranties. | Action 1 | Created | depends on above? |  |  | As above.
1c- Blend variability | 2023-07-20 | If blending used for reserve offtake role, blend % variability will be likely. How will this impact Industrial end users and what mitigation techniques will be required? | Action 1 | Under Review | HSE/ DESNZ |  |  | Progressive Energy blend acceptability study is reviewing this for Transmission direct connects, Hydeploy project for Distribution. However overarching approach for blending as reserve offtaker- requires clarification from Government as to whether a variable or fixed blended gas quality based approach will be implemented, this has been enquired within consultation. | Action Legislative question - Liase with DESNZ as to whether reserve offtaker role will support a variable blend of H2 and therefore mitigating solutions required to manage this will require consideration or whether a fixed H2 volume approach is preferred requiring altermative mitigating solutions to manage (i.e. storage). (This may be addressed in H2 blend consultation).
3- CCUS | 2023-06-19 | DESNZ want CCUS networks to be fully utilised, with possibility of penalties if they are not. |  | Resolved | No? |  |  | Change to comment- DESNZ commented CCS H2 blending will only be supported as reserve offtaker or interim solution before 100% H2 demand is ready.
4a- Interconnectors | 2023-06-19 | EU blending strategy likely to differ from UK, therefore, require solution for H2 blend volumes across IP’s in order to continue trading |  | Monitor | Yes for Transmission only |  |  | NG are scoping EU-UK Strategy paper to review the certainties and unknowns for EU strategy and where alignments and interjurisdictional coordination with UK strategy is required.
4b- European Interconnector Document | 2023-07-18 | Any changes made to UNC may impact EID, or may require changes in EID. | Action 6 | Created | Yes
5- Reverse Compression | 2023-06-19 | Reverse compression MOD 808 , concerns over impacts to a blended gas being transported. |  | Monitor | Potentially |  |  | MOD currently in discussion looking at Reverse compression between Tx and Dx networks which could impact blend cap management. This will need to be monitored and considered if MOD is raised.
6- Connection Agreements | 2023-06-19 | Industrial users that have connection agreements in place have to warrant that site is safe for offtake of gas, this is specifically around Methane, therefore adaptation will be required, this will need to be reviewed by HSE? |  | Resolved | No (HSE) |  |  | NExA point to standard offtake requirements in code | This will sit under the HSE Safety case remit and therefore does not require further review under 0849R
7- Control of Major Accidents Hazard (COMAH) | 2023-06-19 | Timeline for HSE to review Control of major accident hazards (COMAH) safety approvals would need to be considered within roll out plan |  | Resolved | Consideration for Implementation timeline. Within HSE safety case scope. |  |  | This point impacts timescales the roll out of blending but does not need to be considered within the scope for 849R | This will sit under the HSE Safety case remit and therefore does not require further review under 0849R
8- GCOTER | 2023-06-19 | Other aspects of GCOTER include gas temperature, pressure correction and compressibility factor. Has this been covered adequately within Hydeploy programme, does it need to be further considered within 849R? | Action 2 | Under Review | Hydeploy report. HSE safety case scope. |  |  | This will be considered within the HSE safety case review, report covering this has been covered within Hydeploy project, Cadent to share once complete. Also work completed by Dave Lander looks at this, Dave has offered to present this data to the group in September.
9- Limitation to blend volume percentages | 2023-06-19 | Consideration as to how lower limits of blend volume percentage for initial injections coud be outlined? Through code or agreed within Connection Agreements? |  | Created | HSE |  |  | This will be considered within the HSE safety case review and a steer provided as to whether this sits within code or elsewhere.
10- Changes to Existing NEA's to enable blending | 2023-06-19 | More transparency required on changes to existing NEA’s for Distribution Networks as current framework requires no MOD or industry consultation for this. Information such as agreed maximum blend volume to be shared with those impacted further downstream. | Action 10 | Created | Yes |  |  | Whats important to end users here, what information do they want? Review work currently being completed on Gas Quality. Blend points likely to be new NEA's. Refer to actions 9 an 10.
11- New NEA's for blending | 2023-06-19 | Currently no MOD or industry consultation required for new NEA's (Tx & Dx). More transparency required to include agreed maximum blend percentages and impacts on parties downstream. | Action 9 & 10 | Created | Yes |  |  | Considerations for this have been explored in Future Billing Methodology. Also review any considerations within RIIO3 team. Refer to Actions 9 and 10.
12- Blend Cap Management | 2023-06-19 | Existing constraint management tools are mainly for turning down flows, do we require additional tools for when flows need to be increased to manage H2 blending? | Action 7a & 7b | Created | Yes |  |  | Is this more for maximised blending rather than initial connections? (phase 2 consideration)
13- Command and Control | 2023-06-19 | Technical solution required within NEA to ensure maximum H2 blend rates are not exceeded. Require a tool to guarantee a change in flow before emergency phase is reached. Could onsite storage be solution for this? | Action 7b | Created | Yes |  |  | Agree, this needs to be called out in NEA. Transportation Flow Advice (TFA) can be issued to reduce or stop flows.
14- Delivery Facility Operators | 2023-06-19 | Review who DFO’s would be for injecting H2 blend, particularly for entry points with multiple connections. |  | Resolved | Outlined in Functional Specifications Project. |  |  | F.Specs report outlines this, to be reviewed in August review group.
15- Buffer Service | 2023-06-19 | Buffer service ( linepack) provided by TSO’s, could this be outlined in code/ agreed within connection agreement as a service to support maximisation of H2 production? |  | Resolved | Yes |  |  | This would impact blend cap, and would be restricted making it difficult to offer as a service.
16- NExA Safety Case/ Data Sheets | 2023-07-18 | Safety case/ data sheets for NExA's may refer to Methane, therefore these will need to be reviewed to include a blended gas. | Action 4 | Created | HSE?
17- H2 energy to volume difference | 2023-08-02 | Hydrogen has a lower energy to volume ratio than natural gas. |  | Monitor | Future Consideration- to be monitored |  |  | For initial H2 blend injections this difference will not be materialistic, therefore a H2 blend can be traded as energy at the NBP, however if H2 blend injections are to increase in the future this difference in energy vs volume will need to be considered and reviewed.

## Actions Tracking List
ACTIONS TRACKING LIST
WORKGROUP | 0849R
PROJECT NAME | Commercial Framework Review to Enable Hydrogen Blending
Actions Tracker Owner | Megan Bray - megan.bray@nationalgas.co.uk
ACTION NO. / TITLE | DATE CREATED | DESCRIPTION | ASSIGNEE | STATUS | PRIORITY | RAISED BY | COMMENTS | OUTCOME (so what) | CLOSE
1- CCGT's | 2023-06-19 | Check CCGT’s are included in Progressive Energy study looking at Hydrogen Acceptability. | Megan Bray | In-progress |  |  | All gas handling technology archetypes will be considered within the PE Accessibility Study, these have been agregated from a list of direct connected sites to the NTS and will cover CCGT equipment. Interviews will then be conducted with relevant industrial customers regarding each archetype and their compatibility with a Hydrogen blend of up to 20% including variability. | Megan and Julie Cox to discuss archetype and survey methodology for H2 acceptability study offline. The outputs of this work to be shared with industry upon completion and any issues identified to be considered for framework changes. | Yes
2- GCOTER | 2023-06-19 | GCOTER includes gas temperature, pressure correction and compressibility factor. Check this is adequately covered within Hydeploy (DN's). Confirm when report will be completed and share with group. | DN'S | In-progress |  |  | Report covering additional specifications such as gas temperature, pressure correction and compressibility factor is being completed within the Hydeploy programme and will be submitted to HSE as part of the safety case evidence. Report is still being developed, Cadent to share once complete. - Dave Lander has offered to present on findings from previous consumer billing report on this and update group. - Eric Fowler also raised enquiry with IGEM gas measurement committee- it was suggested for 5% blend in pressures upto 2bar effects would be immaterial, however this may need to be considered in higher pressures as well as effects of variability. |  | Yes
3a- Existing NExA gas specifications | 2023-06-19 | Check there are no direct gas specifications included in existing exit agreements. If 0.1% Hydrogen content is specifically referenced, this will need to be changed through appropriate method developed and agreed within this review group. | DN's Megan Bray | Completed |  |  | DN's and Transmssion currently checking NExA's for specific Hydrogen content reference. | National Gas, SGN and Cadent completed check and identified no direct H2 content reference.
3b- Existing NExA (reference to GS(M)R) | 2023-06-19 | Alternatively existing NExA's may point to GS(M)R (likely to change to 20% H2 content) check if this is the case where specific H2 contents is not referenced. | DN's Megan Bray | Completed |  |  | If yes, this leads into deblending issues list and the requirement for an application process for customers to request specific gas quality from network operators and the relevant evidence to justify this requirement.
3c- Hydrogen content in combined entry/exit agreements (IEA/CSEP) | 2023-08-02 | Check whether specific H2 content is referenced within IEA's/ CSEP and consider aspects / interactions with the Offtake Arrangements Document (OAD) and Independent Gas Transporter Arrangements Document (IGTAD). | Megan Bray | Completed |  |  | NTS standard storage connection agreement includes reference to 0.1% H2 content within Annex C - GAS ENTRY & QUALITY PROVISIONS. Interconnector Agreements are more bespoke bi-lateral agreements, however likely also include specific H2 content with entry provisions which will need to be changed to implement blending. | All exisiting combined connection agreements will need to be reviewed and will most likely require an ammendment within the Gas entry provisions section for H2 content. This will need to be reviewed on a case by case basis as and when a blend is to be recieved/ injected.
4- Safety case/ data sheets | 2023-07-18 | Check whether NExA safety case and data sheets reference Methane specifically. | DN's Megan Bray | Completed |  |  | If these include specific reference to Methane they would need to be updated to cover a blended gas. Would this sit with HSE Safety case review instead? | the HSE would need to consult on GS(M)R changes which would provide end consumers with an opportunity to comment / feedback on the H2 20% aspects. HSE would then need to make a decision on how to best manage the safety risk. Although the UNC has a valuable role in educating industry parties, the earlier any issues are highlighted the better (i.e. not awaiting HSE Safety Case related decisions). Therefore earlier industry enagaement on this matter is crucial.
5a- GT License exemption for Hydrogen DFO (NTS) | 2023-06-19 | Check if DFO injecting Hydrogen into NTS as a pre-blend would require a GT License exemption. Liase with Ofgem for clarification and refer to consultation (Gas Transporter Licence Exemption for Onshore Production of Gas) Exemption appies for pipeline up to 16.093km. | Megan Bray | Completed |  |  | https://www.legislation.gov.uk/uksi/2013/1726/made | Ofgem suggested exemption would need to be reviewed on a case by case basis considering the exemption conditions.
5b-GT License exemption for Hydrogen DFO (DN) | 2023-06-19 | Check if DFO injecting Hydrogen into Distribution Network as a pre blend, would require a GT License exemption. (refer to arrangements for Bio Methane plants) | DN's | Completed |  |  | Conditions on Exemption: a) "A does not convey the gas mentioned in article 3 to any premises; and b) the length of pipeline through which the gas mentioned in article 3 is conveyed does not exceed 16.043km between- i) the onshore gas processing facility at which gas processing operations are first carried out on that gas, and ii)the place at which the gas in introduced into a pipeline system operated by a gas transporter." | Ofgem suggested exemption would need to be reviewed on a case by case basis considering the expemtion conditions.
6- European Interconnection Document | 2023-06-19 | Review EID to check if/where there may be cross over and requirement for amendments. | Megan Bray | Created |  |  |  | Interconnection Nomination, if blended gas is imported across the interconnector, could that then sterilise connectioms from blending dwnstream of the IP, who would have the right to blend?
7a- Managing the H2 blend cap (decrease in H2 availability) | 2023-07-18 | If H2 blend percentage needs to remain consistent, how could a loss in H2 supply be managed? | Networks | Created |  |  | This issue would only arise if a fixed H2 blend model is implemented whereby injections would need to remain conistsent (fixed volumes). Storage could be a viable technical solution however may not be economical..
7b- Managing the H2 blend cap (when limited NG to blend) | 2023-07-18 | Review potential mechanism to manage blend cap where constraint on the network limits natural gas flow to blend. | Networks | In-progress |  |  | In terms of gas quality safety a Terminal Flow Advisory can be submitted to stop injection, however where a network constraint reduces availability of N.gas to blend, is there a mechanism that could guarantee an increase in flow of N.gas before capacity buy-back is utilised.. | Review with capacity team and any lessons learnt from Lupton blend connection.
8- Clarification on the role of H2 Blending into networks (reserve offtaker or maximised production) | 2023-06-19 | Clarify with DESNZ whether H2 blending producers will be incentivised to maximise H2 production for blending or whether it will only be used as a reserve offtaker. If only reserve offtaker, does that H2 producer have the right to inject all of H2 reserve into networks, or is it down to network discretion/ capability? | DN's | Continue to review following DESNZ consultation. |  |  | Likely initial blending connections will be those with a HBM. DESNZ plan to run case by case assessment for HBM funding and forsee that blending will be utilised as reserve offtaker where Hydrogen Producers main demand is 100% H2 consumer, or blending may be utilised as an interim solution where production goes live before the demand is connected and ready. HBM's are still being considered in terms of roll out and assessment criteria. (Links with Action 13). H2 blending consultation due to be published in Sept, this may also give steer on the govt's perceived role for blending. | Reserve offtaker for electorlytic and CCUS projects to manage 'volume risk'. Blending may also have value in strategically enabling electrolytic hydrogen producers to support the wider energy system, beneficial for electrolytic hydrogen producers located behind electricity network constraints using excess renewable electricity that would otherwise have been curtailed.
9- Gas Quality changes in existing and new NTS NEA's | 2023-06-19 | Review previous ‘Implementing the Proposed Gas Quality Standards’ work programme and assess if outputs from this work can give guidance on how a gas quality change within existing and new NEA’s could be manged for a blended gas. | Megan Bray | In- Progress
10- Gas Quality changes in existing and new DN NEA's | 2023-06-19 | Review GGG work looking at Gas Quality Data Provision and the recommendations from this to assess how we can enhance gas quality changes within existing and new Distribution NEA’s for blending. | DN's | In- Progress
11- De-blending | 2023-07-18 | Frontier Economics paper outlines high-level commercial framework changes to enable de-blending. Liase with Ofgem/DESNZ/HSE whether this should be considered alongside blending. If so who would be responsible for ownership of the de-blending facilities. | Megan Bray | Created
12- Assumptions | 2023-07-18 | Review updated assumptions during each session | Megan Bray | In-progress
13- Blend variability | 2023-08-02 | Enquire whether Govt's legislative position on blending as a reserve offtaker role includes a fixed or variable blend gas quality approach. So that the necessary mitigating solutions required can then be considered and developed accordingly. | Networks | In- Progress |  |  | Blending consultation request's feedback from end consumers on H2 acceptability and specifically calls out variability.
14- H2 blend purchased on OCM | 2023-08-02 | Would SO need to know when they are purchasing H2 on OCM? Check with NCC. | Megan Bray | In-progress |  |  | Gas traded on OCM in energy therefore are updates to Gemini required so that Network operator was aware when they were purchasing H2 for shrinkage/ own use gas.