## Sheet1
Date Requested | Reason for Request | Data Type/Information required | Data Provider | Due Date | Status | Priority | Key
2019-07-12 | Calculation of Total UG | Allocations Final allocations including CSEPS from 01/10/2017 to 30/09/2018, new data only | Xoserve | 2019-08-08 | Received |  | Data received
2019-07-12 | Calculation of Total UG | Throughput/UIG Required from point of Nexus go-live. Includes throughput, DM consumption, shrinkage and UIG | Xoserve | 2019-08-01 | Received |  | Data delayed but no impact on analysis envisaged
2019-07-12 | Calculation of Consumption | AQ History Updated AQ history files to be provided containing any new AQ records since previous data drop. | Xoserve | By LDZ as available. Data provision to start by 1 Sep and complete by 1 Nov | Received 1 LDZ 18 Sep, 2 further LDZs 27 Sep | M | Data delayed and will impact analysis
2019-07-12 | Calculation of Consumption | CSEP Invoicing Data at 1 Oct 2018 - Supply point counts and AQs - AQ recalculation success rates | Xoserve | 2019-08-08 | Received |  | Data not yet due and no known issues with delivery
2019-07-12 | Calculation of Consumption | Factors (Profiling Algorithm Parameters) An update containing the most recent factors (gas year 2017/18) is required | Xoserve | 2019-09-01 | Received
2019-07-12 | Calculation of Consumption | Meter Errors (LDZ, CSEP, DM & Unique) All meter error adjustments (offline adjustments) from 1/04/2008 onwards, "closed" meter errors only | Xoserve | 2019-10-15 |  | L
2019-07-12 | Calculation of Consumption | Meter Asset Information Update of Meter Info files containing all updates since the previous data drop | Xoserve | By LDZ as available. Data provision to start by 1 Sep and complete by 1 Nov | Received 1 LDZ 18 Sep, 2 further LDZs 27 Sep | H
2019-07-12 | Calculation of Consumption | Meter reads & volumes Updated meter reads from 01/04/2008. To include those with NULL LDZ field and all opening and final reads | Xoserve | By LDZ as available. Data provision to start by 1 Sep and complete by 1 Nov | Received WN SSP Reads 6 Sep, EM & SE 18 Sep, SC 27 Sep. No LSP reads yet | H
2019-07-12 | Calculation of Consumption | Prime/Sub Meters | Xoserve | 2019-09-06 | Not Received | L
2019-07-12 | Calculation of Consumption | New/Lost Meters | Xoserve | 2019-09-13 | Not Received | M
2019-07-12 | Calculation of Consumption | Mod0429 Claims | Xoserve | 2019-09-06 | Not Received | L
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Unregistered/Shipperless detailed files | Xoserve | Monthly, data provision to begin by 1 Sep | Received Sep-Dec 2018 on 17 Sep | M
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Snapshot Query Response Responses to any queries regarding suspicious AQ values | Xoserve | When requested, response within 3 weeks of request |  | L
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Connection Details for Orphaned Sites Asset and Shipper meter read details for sites that were Orphaned but now confirmed. | Xoserve | 2019-09-30 | Not Received | L
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Gas Safety Regulations Visit Data (GSR) Gas Safety Regulations visit data used to estimate the number of sites that have no Shipper but have not yet reached the threshold for inclusion in the snapshots | Xoserve | 2019-09-30 | Not Received | L
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Mod410A Supporting Data | Xoserve | When requested, response within 3 weeks of request |  | L
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Shipperless Sites Supporting Data | Xoserve | When requested, response within 3 weeks of request |  | L
2019-07-12 | Calculation of UG from iGT CSEPS | iGT CSEP data for known CSEPs Provides the composition of known CSEPs by EUC | Xoserve | 2019-09-30 | Not Received | L
2019-07-12 | Calculation of UG from iGT CSEPS | iGT CSEP data unknown projects snapshots | Xoserve | Monthly, data provision to begin by 1 Sep | Not Received
2019-07-12 | Calculation of UG from Meter Errors | Meter capacity report | Xoserve | 2019-09-30 | Not Received | L
2019-07-12 | Theft Assesment | Theft of Gas (Shipper) Data for all detected thefts from April 2016 | Xoserve | 2019-08-08 | Received
2019-07-12 | Theft Assesment | Theft of Gas (TRAS) - Outcome Files - Leads and qualified outliers | TRAS via Xoserve | 2019-10-31 |  | H
2019-07-12 | Theft Assesment | Theft of Gas (SPAA) - Anonymised Schedule 33 Report - Supplier Response Rates | TRAS | 2019-10-31 |  | H
2019-07-12 | Calculation of Factors to Split UG by Product Class | Product Class Mapping - Initial data drop | Xoserve | 2019-08-15 | Received
2019-07-31 | Calculation of Factors to Split UG by Product Class | Product Class Mapping - Update for table calculation | Xoserve | 2019-11-29 |  | M
2019-07-12 | Reconciliation analysis to assess permanent UG | Reconciliation Values (Post-Nexus) Monthly Energy by LDZ | Xoserve | 2019-09-13 | Received (Download from CDSP website)
2019-07-12 | Assessment of effect of using static temperature correction factor in energy conversion | Converter Details Pressure/Temperature Conversion Devices by MPRN | Xoserve | 2019-08-30 | Received 5 Sep
2019-07-12 | Assessment of effect of using static temperature correction factor in energy conversion | Non-Standard Sites List of all non-standard sites e.g. LPG, telemetered | Xoserve | 2019-08-15 | Received
2019-07-12 | Assessment of meter gas temperature | Meter Location Code & Description | Xoserve | 2019-09-18 | Received 27 Sep | M
2019-07-31 | Assessment of effect of using static temperature correction factor in energy conversion | Actual Temperature Bi-Hourly by LDZ | Xoserve | 2019-08-15 | Received
2019-07-31 | Assessment of effect of using static temperature correction factor in energy conversion | Meter reads & volumes Sample of all corrected and uncorrected meter reads/volumes for 1 LDZ | Xoserve | 2019-08-15 | Received 21 Aug 2019
2019-07-31 | Assessment of poor address information | Address update information | Xoserve | 2019-08-30 | Not Received | M
2019-08-31 | Assessment of effect of using static temperature correction factor in energy conversion | New EUC Mappings | Xoserve | 2019-10-15 |  | L
2019-07-31 | Reconciliation analysis to assess permanent UG | Expected Product Class Uptake | Xoserve | 2019-10-15 | Received Initial Data. Refresh required later | H
2019-09-13 | UIG from use of std CF | Number of updates from Standard to Site Specific CF | Xoserve | TBA |  | M
| Allow better understanding of AMR populations | Additional AMR Details Details of AMR devices fitted by I&C suppliers but not reported to BEIS | ICoSS | 2019-11-29 | Not yet requested