## Sheet1
Date Requested | Reason for Request | Data Type/Information required | Data Provider | Due Date | Status | Priority
2018-07-13 | Calculation of Total UG | Allocations Final allocations including CSEPS from 01/10/2016 to 30/09/2017, new data only | Xoserve | 2018-08-10 | Provided
2018-07-13 | Calculation of Total UG | Throughput Required from point of Nexus go-live. Includes throughput, DM consumption, shrinkage and UIG | Xoserve | 2018-08-10 | Provided
2018-07-13 | Calculation of Consumption | AQ History Updated AQ history files to be provided containing any new AQ records since previous data drop. | Xoserve | By LDZ as available. Data provision to start by 3 Sep and complete by 16 Nov | Provided
2018-07-13 | Calculation of Consumption | CSEP Invoicing Data at 1 Oct 2017 - Supply point counts and AQs - AQ recalculation success rates | Xoserve | 2018-08-10 | Provided but issue with historic data identified | 1
2018-07-13 | Calculation of Consumption | Factors (Profiling Algorithm Parameters) An update containing the most recent factors (gas year 2016/17) is required | Xoserve | 2018-09-07 | Provided
2018-07-13 | Calculation of Consumption | Meter Errors (LDZ, CSEP, DM & Unique) All meter error adjustments (offline adjustments) from 1/04/2008 onwards, "closed" meter errors only | Xoserve | 2018-11-16 | Provided but issues still exist | 2
2018-07-13 | Calculation of Consumption | Meter Asset Information Update of Meter Info files containing all updates since the previous data drop | Xoserve | By LDZ as available. Data provision to start by 3 Sep and complete by 16 Nov | Provided
2018-07-13 | Calculation of Consumption | Meter reads & volumes Updated meter reads from 01/04/2008 | Xoserve | By LDZ as available. Data provision to start by 3 Sep and complete by 16 Nov | Provided
2018-07-13 | Calculation of Consumption | Prime/Sub Meters | Xoserve | 2018-09-07 | Provided
2018-07-13 | Calculation of Consumption | New/Lost Meters | Xoserve | 2018-09-14 | Provided
2018-07-13 | Calculation of Consumption | Mod0429 Claims | Xoserve | 2018-09-07 | Provided
2018-07-13 | Calculation of UG from Shipperless/Unregistered Sites | Unregistered/Shipperless detailed files | Xoserve | Monthly, data provision to begin by 30 Sep | Provided
2018-07-13 | Calculation of UG from Shipperless/Unregistered Sites | Snapshot Query Response Responses to any queries regarding suspicious AQ values | Xoserve | When requested, response within 3 weeks of request | Not Provided
2018-07-13 | Calculation of UG from Shipperless/Unregistered Sites | Connection Details for Orphaned Sites Asset and Shipper meter read details for sites that were Orphaned but now confirmed. | Xoserve | 2018-09-30 | Provided
2018-07-13 | Calculation of UG from Shipperless/Unregistered Sites | Gas Safety Regulations Visit Data (GSR) Gas Safety Regulations visit data used to estimate the number of sites that have no Shipper but have not yet reached the threshold for inclusion in the snapshots | Xoserve | 2018-09-30 | Provided
2018-07-13 | Calculation of UG from Shipperless/Unregistered Sites | Mod410A Supporting Data | Xoserve | When requested, response within 3 weeks of request | Not Provided | 3
2018-07-13 | Calculation of UG from Shipperless/Unregistered Sites | Shipperless Sites Supporting Data | Xoserve | When requested, response within 3 weeks of request | Not Provided | 3
2018-07-13 | Calculation of UG from iGT CSEPS | iGT CSEP data for known CSEPs Provides the composition of known CSEPs by EUC | Xoserve | 2018-09-30 | Not Provided - Received registered sites | 2
2018-07-13 | Calculation of UG from iGT CSEPS | iGT CSEP data unknown projects snapshots | Xoserve | Monthly, data provision to begin by 30 Sep | Not Provided | 1
2018-07-13 | Calculation of UG from Meter Errors | Meter capacity report | Xoserve | 2018-09-30 | Provided
2018-07-13 | Theft Assesment | Theft of Gas (Shipper) Data for all detected thefts from April 2016 | Xoserve | 2018-08-10 | Provided
2018-06-20 | Theft Assesment | Theft of Gas (TRAS) - Outcome Files - Leads and qualified outliers | TRAS | 2018-10-31 | Received TRAS outcome data but not ETTOS and TRAS qualified outliers | 1
2018-06-20 | Theft Assesment | Theft of Gas (SPAA) - Anonymised Schedule 33 Report - Supplier Response Rates | TRAS | 2018-10-31 | Provided
2018-07-13 | Calculation of Factors to Split UG by Product Class | Product Class Mapping | Xoserve | 2018-08-10 | Provided
2018-07-13 | Analysis of effect of altitude on energy conversion | Elevation by MPRN | OS/Xoserve | 2018-08-10 | Provided
2018-08-15 | Reconciliation analysis to assess permanent UG | Reconciliation Values (Post-Nexus) Monthly Energy by LDZ | Xoserve | 2018-09-14 | Provided
2018-08-15 | Reconciliation analysis to assess permanent UG | Reconciliation Values (Pre-Nexus) Monthly Energy by LDZ | Xoserve | 2018-09-14 | Provided
2018-08-15 | Reconciliation analysis to assess permanent UG | Daily UIG Values (Post-Nexus) | Xoserve | 2018-09-14 | Provided
2018-08-15 | Reconciliation analysis to assess permanent UG | Daily UIG Values (Pre-Nexus Estimates) | Xoserve | 2018-09-14 | Provided
2018-08-08 | Assessment of effect of using static temperature correction factor in energy conversion | Actual Temperature Bi-Hourly by LDZ | Xoserve | 2018-08-31 | Provided
2018-08-15 | Assessment of effect of using static temperature correction factor in energy conversion | Seasonal Normal Temperature Daily SNT by LDZ | Xoserve | 2018-08-31 | Provided
2018-10-12 | Assessment of effect of using static temperature correction factor in energy conversion | Atmospheric Pressure Historic Actual Pressure data for weather stations used by CDSP | Xoserve | 2018-11-01 | Provided
2018-08-15 | Assessment of effect of using static temperature correction factor in energy conversion | Converter Details Pressure/Temperature Conversion Devices by MPRN | Xoserve | 2018-08-31 | Provided
2018-08-30 | Theft analysis to support calculation of Factors to Split UG by Product Class | Meter Type Derived from meter serial number based on rules provided by DNV GL | Xoserve | 2018-09-21 | Provided
2018-08-31 | Assessment of meter gas temperature | Meter Location Code & Description | Xoserve | 2018-09-18 | Provided
2018-11-09 | Assessment of UIG from meter exchange | Opening & Closing Meter Reads All opening and closing meter reads for one LDZ and one gas year | Xoserve | 2018-11-30 | Provided
2018-11-19 | Allow better understanding of AMR populations | Additional AMR Details Details of AMR devices fitted by I&C suppliers but not reported to BEIS | ICoSS | 2018-12-07 | Provided