## Summary
Date Requested | Reason for Request | Data Type/Information required | Data Provider | Due Date | Status | Priority | Key
2019-07-12 | Calculation of Total UG | Allocations Final allocations including CSEPS from 01/10/2017 to 30/09/2018, new data only | Xoserve | 2019-08-08 | Received |  | Data received
2019-07-12 | Calculation of Total UG | Throughput/UIG Required from point of Nexus go-live. Includes throughput, DM consumption, shrinkage and UIG | Xoserve | 2019-08-01 | Received |  | Data delayed but no impact on analysis envisaged
2019-07-12 | Calculation of Consumption | AQ History Updated AQ history files to be provided containing any new AQ records since previous data drop. | Xoserve | By LDZ as available. Data provision to start by 1 Sep and complete by 1 Nov | Received | M | Data delayed and will impact analysis
2019-07-12 | Calculation of Consumption | CSEP Invoicing Data at 1 Oct 2018 - Supply point counts and AQs - AQ recalculation success rates | Xoserve | 2019-08-08 | Received |  | Data not yet due and no known issues with delivery
2019-07-12 | Calculation of Consumption | Factors (Profiling Algorithm Parameters) An update containing the most recent factors (gas year 2017/18) is required | Xoserve | 2019-09-01 | Received
2019-07-12 | Calculation of Consumption | Meter Errors (LDZ, CSEP, DM & Unique) All meter error adjustments (offline adjustments) from 1/04/2008 onwards, "closed" meter errors only | Xoserve | 2019-10-15 | Received 25 Nov but split by billing month not month for which correction applies
2019-07-12 | Calculation of Consumption | Meter Asset Information Update of Meter Info files containing all updates since the previous data drop | Xoserve | By LDZ as available. Data provision to start by 1 Sep and complete by 1 Nov | Received | H
2019-07-12 | Calculation of Consumption | Meter reads & volumes Updated meter reads from 01/04/2008. To include those with NULL LDZ field and all opening and final reads | Xoserve | By LDZ as available. Data provision to start by 1 Sep and complete by 1 Nov | Received | H
2019-07-12 | Calculation of Consumption | Prime/Sub Meters | Xoserve | 2019-09-06 | Received 25 Nov | L
2019-07-12 | Calculation of Consumption | New/Lost Meters | Xoserve | 2019-09-13 | Received 25 Nov | M
2019-07-12 | Calculation of Consumption | Mod0429 Claims | Xoserve | 2019-09-06 | Not Received | L
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Unregistered/Shipperless detailed files | Xoserve | Monthly, data provision to begin by 1 Sep | Received Sep-Jun 2019 on 17 Sep. Received Jul,Aug,Sep 2019 on 7 Nov | M
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Snapshot Query Response Responses to any queries regarding suspicious AQ values | Xoserve | When requested, response within 3 weeks of request |  | L
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Connection Details for Orphaned Sites Asset and Shipper meter read details for sites that were Orphaned but now confirmed. | Xoserve | 2019-09-30 | Received 31 Oct | H
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Gas Safety Regulations Visit Data (GSR) Gas Safety Regulations visit data used to estimate the number of sites that have no Shipper but have not yet reached the threshold for inclusion in the snapshots | Xoserve | 2019-09-30 | Received 7 Nov | H
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Mod410A Supporting Data | Xoserve | When requested, response within 3 weeks of request |  | L
2019-07-12 | Calculation of UG from Shipperless/Unregistered Sites | Shipperless Sites Supporting Data | Xoserve | When requested, response within 3 weeks of request |  | L
2019-07-12 | Calculation of UG from iGT CSEPS | iGT CSEP data for known CSEPs Provides the composition of known CSEPs by EUC (Registered & Unregistered Sites) | Xoserve | 2019-09-30 | Received Registered Sites, Unregistered received 20 Nov but data suspect | H
2019-07-12 | Calculation of UG from iGT CSEPS | iGT CSEP data unknown projects snapshots | Xoserve | Monthly, data provision to begin by 1 Sep | Not Available post-Nexus
2019-07-12 | Calculation of UG from Meter Errors | Meter capacity report | Xoserve | 2019-09-30 | Received 11 Oct
2019-07-12 | Theft Assesment | Theft of Gas (Shipper) Data for all detected thefts from April 2016 | Xoserve | 2019-08-08 | Received
2019-07-12 | Theft Assesment | Theft of Gas (TRAS) - Outcome Files - Leads and qualified outliers | TRAS via Xoserve | 2019-10-31 | Not Received | H
2019-07-12 | Theft Assesment | Theft of Gas (SPAA) - Anonymised Schedule 33 Report - Supplier Response Rates | TRAS | 2019-10-31 | Not Received | H
2019-07-12 | Calculation of Factors to Split UG by Product Class | Product Class Mapping - Initial data drop | Xoserve | 2019-08-15 | Received
2019-07-31 | Calculation of Factors to Split UG by Product Class | Product Class Mapping - Update for table calculation | Xoserve | 2019-11-29 | Received 25 Nov
2019-07-12 | Reconciliation analysis to assess permanent UG | Reconciliation Values (Post-Nexus) Monthly Energy by LDZ | Xoserve | 2019-09-13 | Received (Download from CDSP website)
2019-07-12 | Assessment of effect of using static temperature correction factor in energy conversion | Converter Details Pressure/Temperature Conversion Devices by MPRN | Xoserve | 2019-08-30 | Received 5 Sep
2019-07-12 | Assessment of effect of using static temperature correction factor in energy conversion | Non-Standard Sites List of all non-standard sites e.g. LPG, telemetered | Xoserve | 2019-08-15 | Received
2019-07-12 | Assessment of meter gas temperature | Meter Location Code & Description | Xoserve | 2019-09-18 | Received 27 Sep | M
2019-07-31 | Assessment of effect of using static temperature correction factor in energy conversion | Actual Temperature Bi-Hourly by LDZ | Xoserve | 2019-08-15 | Received
2019-07-31 | Assessment of effect of using static temperature correction factor in energy conversion | Meter reads & volumes Sample of all corrected and uncorrected meter reads/volumes for 1 LDZ | Xoserve | 2019-08-15 | Received 21 Aug 2019
2019-07-31 | Assessment of poor address information | Address update information | Xoserve | 2019-08-30 | No Longer Required
2019-08-31 | Assessment of effect of using static temperature correction factor in energy conversion | New EUC Mappings | Xoserve | 2019-10-15 | Not Received | L
2019-07-31 | Reconciliation analysis to assess permanent UG | Expected Product Class Uptake | Xoserve | 2019-10-15 | Received Initial Data. Refresh required later | H
2019-09-13 | UIG from use of std CF | Updates from Standard to Site Specific CF Number of updates since 1 June 2018 | Xoserve | 2019-11-13 | Received 13 Nov | M
2019-10-16 | Temperature Analysis | Actual Temperature Bi-Hourly by LDZ for calendar years 1996, 1997, 1998, 1999 & 2000 | Xoserve | 2019-11-05 | Received 5 Nov | H
2019-10-17 | Temperature Analysis | Seasonal Normal Temperature Latest daily SNT by LDZ | Xoserve | TBA | Not avaialble from CDSP | H
2019-10-17 | Temperature Analysis | Allocations Final allocations (including CSEPS) for gas years 1996, 1997, 1998 and 1999 (1 Oct 1996 to 30 Sep 2000) - same format as for allocations used in Consumption calculation | Xoserve | 2019-11-14 | Received 14 Nov | H
2019-10-17 | Consumption Calculation | Revised Data Based on New CWV Definition All relevant data updated for complete history (from 1/4/2008). CWV, SNCWV, WCF, WAALP | Xoserve | TBA | Not yet available. WAALPs not expected to be available until Sep 2020 | L
21/20/2019 | Meter Errors | Details of Meter Maintenance & Z-Conversion | Industry | 2019-11-15 | No Information Received
2019-10-30 | Allow better understanding of AMR populations | Additional AMR Details Details of AMR devices fitted by I&C suppliers but not reported to BEIS | ICoSS | 2019-11-29 | Received 26 Nov
2019-10-31 | Temperature Analysis | Internal Building Temperatures Average internal temperature by LDZ/EUC | Industry | 2019-11-22 | No Information Received
2019-11-13 | Assessment of effect of using static temperature correction factor in energy conversion | Meter reads & volumes Sample of all corrected and uncorrected meter reads/volumes for 2 LDZs, NO and SW | Xoserve | 2019-11-22 | Received 22 Nov for SC & SW
2019-11-22 | Consumption Calculation | Meter reads & volumes All corrected and uncorrected meter reads/volumes for all LDZs going back as far as possible | Xoserve | 2019-11-29 |  | H
2019-11-20 | Temperature Analysis | Actual Temperature Bi-Hourly by LDZ for calendar years 2001 onwards | Xoserve | 2019-11-21 | Received 21 Nov | H

## ByFile
Data Type | Expected Files | Received Files | % Received |  | Data Category | Expected Files | Received Files | % Data Received
Allocations | 2 | 2 | 100% |  | Consumption Calculation | 71 | 68 | 95.77%
Throughput | 1 | 1 | 100% |  | Shipperless/Unregistered | 15 | 14 | 93.33%
AQ | 14 | 14 | 100% |  | Theft of Gas | 5 | 1 | 20%
Meter Asset Info | 15 | 15 | 100% |  | CF Analysis (incl P&T) | 10 | 10 | 100%
SSP Meter Reads | 16 | 16 | 100% |  | Other | 9 | 6 | 66.67%
LSP Meter Reads | 15 | 15 | 100%
CSEP Invoicing Data | 1 | 1 | 100% |  | Total | 110 | 99 | 90%
NDM Algorithm Factors | 1 | 1 | 100%
Meter Errors | 1 | 0 | 0%
Primes/Subs | 1 | 1 | 100%
New/Lost Meters | 1 | 1 | 100%
Mod429 Claims | 1 | 0 | 0%
Shipperless/Unregistered Sites | 15 | 14 | 93.33% | *includes CSEP unreg sites
Meter Capacity Report | 1 | 1 | 100%
Theft of Gas (Shipper) | 1 | 1 | 100%
Theft of Gas (TRAS) | 2 | 0 | 0%
Theft of Gas (SPAA) | 2 | 0 | 0%
Product Class Mapping | 1 | 1 | 100%
Reconciliation Data | 1 | 1 | 100%
Converter Details | 1 | 1 | 100%
Non-Standard Sites | 1 | 1 | 100%
Meter Location | 1 | 1 | 100%
LDZ Temperatures | 1 | 1 | 100%
Sample of Converted Reads | 3 | 3 | 100%
Address Update Info | 0 | 0 | 100%
New EUC Mappings | 1 | 0 | 0%
Expected Product Class Update | 2 | 2 | 100%
CF Updates | 1 | 1 | 100%
Actual Historic LDZ Temperatures | 2 | 2 | 100%
LDZ Seasonal Normal Temperatures | 0 | 0 | 100%
Actual Historic Allocations | 1 | 1 | 100%
CWV Update data (new defn) | 2 | 0 | 0% | **TBC
Additional AMR Details | 1 | 1 | 100%
Converted Reads for all LDZs | 1 | 0 | 0%
Total | 110 | 99 | 90%