## Sheet1
Data Request ID | Contributor | Data Item | Data Item Description | Priority Rating | Source | Request Date | Expected Date | Status | Received | Validated
1 | Theft | Shipper Theft Data | Details of theft provided to Xoserve within CMS | H | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y
2 | Theft | TRAS Outcome File Data | The data outcome from TRAS | H | Xoserve (TRAS) | 2020-06-30 | 2020-07-27 | Valid | Y | Y
3 | Theft | TRAS Suspected Thefts | ETTOS Data | H | Xoserve (TRAS) | 2020-06-30 | 2020-07-27 | In Query | Y
4 | Unregistered Shipperless | Snapshot files (including MPR details) | Monthly Snapshot files | M | Xoserve | 2020-06-30 | 2020-07-27 | In Query | Y | N
5 | Unregistered Shipperless | Gas Safety Regulations visit data | Details of Gas Safety Regulation Visits | M | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y
6 | Unregistered Shipperless | Mod 0410A supporting data | Supporting data from the UNC Mod 0410A: Responsibility for gas off-taken at Unregistered Sites following New Network Connections. | L | Xoserve | 2020-06-30 | 2020-08-17 | Awaiting file
7 | Unregistered Shipperless | Connection details for orphaned sites | Details of connections for Orphaned sites | M | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y
8 | IGT Unknown Projects | Not currently planned for investigation
9 | Consumption Meter Errors | Meter Capacity report | A report providing the capacity of meter | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y
10 | Meter Errors at LDZ input | Meter Errors | This file provides details of the meter errors that have taken place and their associated energy | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y
11 | Meter Errors at LDZ input | Measurement Error Register | The register of the Measurement Errors held on the Joint Office Website | M | Joint Office website | n/a | n/a |  | Y | Y
12 | IGT Shrinkage | Main Length | Details of the length of main and the total number of end users | H | IGTs | 2020-08-25 | 2020-10-01 | Awaiting info
13 | IGT Shrinkage | Leakage Rates | Leakage rates from the NLT | H | Public Domain | n/a | n/a
14 | IGT Shrinkage | IGT Sites | Number and associated AQ of sites on IGTs | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y
15 | Atmospheric Pressure Assumption | Historical Pressure Information | Historical Pressure information by Weather Station | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y
16 | Atmospheric Pressure Assumption | Sites with volume conversion equipment fitted | A report providing information for sites that have volume conversion equipment fitted | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y
17 | Average Temperature Assumption | Meter Location | Snapshot of the meter location split by EUC band | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y
18 | Average Temperature Assumption | Gas Temperature Data | Gas Temperature Data From DMTS & ICTS | M | DNV | 2020-06-15 | 2020-06-15 | Valid | Y | Y
19 | No meter read at line in the sand | Sites with no reads after April 2018 | Details of the sites with no actual read after April 2018 | H | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y
20 | No meter read at line in the sand | Change in AQ since June 2017 | A report by class and EUC of the change in rolling AQ | H | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y
21 | Large sites with incorrect correction factors | Site details | Correction factors for all sites in EUC04 and above | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y
22 | Large sites with incorrect correction factors | Correction Factor Changes | Changes to correction factor within year | L | Xoserve | TBC
23 | CV Shrinkage | Not currently planned for investigation
24 | Meter Exchanges | Not currently planned for investigation
25 | General Industry Information | Market summary report | A snapshot report of the number of Live sites and associated AQ | M | Xoserve | 2020-06-30 | 2020-08-03 | No Longer required | n/a
26 | General Industry Information | Future class change | A report of any known future class changes indicated by Shippers | M | Xoserve | 2020-06-30 | 2020-08-03 | No report exists | n/a
27 | General Industry Information | Consumption | Allocation by LDZ | M | Xoserve | 2020-06-30 | 2020-08-03 | In Query | Y
28 | General Industry Information | Throughput | Daily Total throughput, DM allocation and UIG by EUC | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y
29 | General Industry Information | Daily Allocation Factor | The daily Allocation factors applied to NDM sites | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y
30 | General Industry Information | Reconciliation | Monthly report of the reconciliations since Nexus go live | M | Xoserve | n/a |  |  | Y | Y
31 | General Industry Information | Additional reconciliation information | Percentage of DM energy reconciled to actual read or better estimate based on actual read | M | Xoserve | 2020-06-30 | 2020-08-03 | Awaiting info
32 | Other | AMR Date |  | L | ICOSS | TBC |  | Investigating if data is necessary
33 | Other | Smart Meter Data |  | M | Public domain | n/a | n/a