## Cover
Shipperless / Unregistered Sites
1.25M ACs
750K
3M
3M
3M
3M
3M
y.0M
y.0M + Tail = 2.7M

## USNANA Graphs
Unregistered Sites No Activity No Assets
Overview (xoserve) 4,891 MPRNs have been processes during August. 2,373 were cleared and the number requiring further investigation has increased by 2,518. 64% of the cleared MPRNs are erroneous and will be set to EX, 31% are now registered and 3% of the sites are legitimately unregistered. 22,346 MPRNs have been or are going through the End User process and to date 2,000 (figure to be confirmed) of these sites have passed the agreed timescales without a response. Distribution Networks have agreed to site visit the MPRNs that have not had a response from the end user letters and the template to facilitate this is currently being tested ready for use during September.

## Shipperless Graphs
Shipper activity unregistered sites
General Comments (Suzanne Powell and Julia Sherwen) (SP) We received 4,215 invoices this week and sent 3,956. The remaining 259 were not sent due to the PP fault. The main bulk of issues remain in the workflow and exception categories. We currently have 11,235 accounts within work management that are faulted. 11, 012 are mis-directed Technical errors (Idoc). The working group have now prioritised over 80% of the faults for release (Rj312.2) and the other 20% will be actioned in tomorrow's workshop. (JS) This week we have included data (CLO 13 & 14) from Meter to Cash analysis showing invoicing performance relating to two specific dates. This will be developed in coming weeks.
Comments (Gillian Taylor) The reconciliation levels have remained constant week on week (now at 79%). The rate of raising issues on financial reconciliation has slowed, but the rate of resolution of outstanding HPOVs has also been slow. The focus this week in Finance will be to test the new functionality and fixes which were implemented for Finance as part of RJ312. There is a weekly teleconference on unbilled revenue to track issues. Key outstanding issues relate to the volume of exceptions where unbilled is unable to produce an estimate; the run times of unbilled revenue; the processing of multiple gas meter reads on the same day, and the development of an exclusion / substitution process.
Comments - Acquisitions Acquisitions slowly continue to creep up. There are a number of faults/issues surrounding Acquisitions and these are being actioned by the top 20. We expect to see an increase within Acquisitions next week due to the 5,985 new sales going through on Monday as a result of RJ312. The working group are continuing to meet daily and assess the impacts.
Comments - Withdrawals Volume outstanding again has slightly increased due to the "Discuss Objection"(243) and "Objection Received" items, Further investigations are being carried out, but the exceptions have been closed within Siebel but are showing as open in SAP. There is no customer impact.
Comments - Home Move Slight increase from 92 to 102 (109) exceptions this week. 51 of the 102are WIP and 27are faults due to cancel re-bill (909515 due in RJ312.2), 24 in progress and were cleared Monday.
Overview (xoserve) Unregistered sites where Shipper Activity has been identified has decreased. Shipper responses to the report have reduced and these issues will be addressed through operational meetings.
1.25M ACs
750K
3M
3M
3M
3M
3M
y.0M
y.0M + Tail = 2.7M

## USNANA Data
Unregistered Data
USNANA Age Analysis | Pre 1996 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | Total
Original age analysis | 79 | 1790 | 835 | 1793 | 2269 | 4380 | 3635 | 15957 | 23439 | 11831 | 9328 | 15950 | 22838 | 114124
Current age analysis | 0 | 0 | 17 | 127 | 522 | 1382 | 972 | 3700 | 13828 | 6095 | 5071 | 6896 | 7891 | 46501
Resolved to date | 79 | 1790 | 818 | 1666 | 1747 | 2998 | 2663 | 12257 | 9611 | 5736 | 4257 | 9054 | 14947 | 67623
USNANA Overall status - cumulative | Pre 1996: 2007; 1997: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Outstanding target | 49470 | 42470 | 37470 | 33470 | 29470 | 24220 | 18970 | 13720 | 8470 | 4220 | 1150 | 0
Outstanding | 49470 | 48105 | 44361 | 37967 | 32543 | 26273 | 20202 | 15461 | 10899 | 6369 | 1478
Variance from target | 0 | 5635 | 6891 | 4497 | 3073 | 2053 | 1232 | 1741 | 2429 | 2149
Under investigation | 52826 | 33017 | 33448 | 34626 | 35190 | 36926 | 37670 | 39313 | 40948 | 42505 | 45023
Total Registered |  |  |  | 12803 | 14558 | 15866 | 17377 | 18503 | 19137 | 20024 | 20966
Total Set to Extinct (EX) |  |  |  | 24287 | 27532 | 30872 | 34953 | 37230 | 39562 | 41776 | 43457
Total Legitimately Unregistered |  |  |  | 2384 | 2338 | 2238 | 2175 | 2094 | 2050 | 1997 | 1963
Desktop Moved to Shipper Activity Pot | 3165 | 4109 | 2139 | 2057 | 1963 | 1949 | 1747 | 1523 | 1528 | 1453 | 1237
Cleared | 11828 | 33002 | 36315 | 41531 | 46391 | 50925 | 56252 | 59350 | 62277 | 65250 | 67623
Check Cell - Total Project Amount |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -114124
Check cell - Cleared Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Desktop actions - cumulative | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Desktop Registered | 5397 | 7164 | 10894 | 12655 | 14401 | 15651 | 16935 | 17431 | 17883 | 18451 | 18999 | 0
Desktop Set to EX | 541 | 19138 | 20833 | 23731 | 26788 | 29794 | 33767 | 35921 | 37994 | 39590 | 40661 | 0
Desktop Legitimately Unregistered | 2725 | 2591 | 2449 | 2309 | 2263 | 2163 | 2100 | 2022 | 1978 | 1926 | 1893 | 0
Desktop Moved to Shipper Activity Pot | 3165 | 4109 | 2139 | 2057 | 1963 | 1949 | 1747 | 1523 | 1528 | 1453 | 1237 | 0
Desktop End user |  | 1369 | 2377 | 5034 | 7372 | 9673 | 11948 | 15067 | 17484 | 20530 | 24346 | 0
Total | 11828 | 34371 | 38692 | 45786 | 52787 | 47608 | 52802 | 55374 | 57855 | 59967 | 61553 | 0
End User Actions | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Letter pending | 0 | 36 | 45 | 181 | 1724 | 928 | 755 | 3632 | 4325 | 1764 | 693
Letter 1 Sent | 0 | 1005 | 1721 | 2578 | 2209 | 4118 | 4915 | 4419 | 5232 | 6303 | 5411
Letter 2 Sent | 0 | 0 | 0 | 588 | 1219 | 1266 | 1617 | 1489 | 1998 | 4279 | 5972
Site Visit | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 211 | 211 | 320 | 2000
Query | 0 | 43 | 39 | 179 | 279 | 430 | 573 | 510 | 337 | 556 | 920
PSA | 0 | 132 | 160 | 215 | 252 | 310 | 404 | 335 | 340 | 354 | 412
No Gas | 0 | 101 | 171 | 553 | 712 | 1196 | 1779 | 1883 | 2014 | 2955 | 3865
Vacant | 0 | 47 | 67 | 111 | 151 | 207 | 274 | 285 | 283 | 319 | 390
To be set to extinct | 0 | 4 | 144 | 487 | 675 | 1009 | 1117 | 1240 | 1499 | 2117 | 2727
Registered | 0 | 1 | 30 | 142 | 151 | 209 | 436 | 1063 | 1245 | 1563 | 1956
Total | 0 | 1369 | 2377 | 5034 | 7372 | 9673 | 11948 | 15067 | 17484 | 20530 | 24346 | 0
Check cell - end user totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Site visits | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
For Network Attention | 2008 May: 78; 2008 Jun: 211; 2008 Jul: 211; 2008 Aug: 320; 2008 Sep: 2000
Sent | 350 | 494 | 494 | 494 | 494 | 494 | 494 | 494 | 494 | 494 | 494
Undertaken | 150 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163
Resolved | 0 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 0
Response outstanding | 200 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 331 | 0
Check cell - site visit total | 350 | 494 | 494 | 494 | 494 | 494 | 416 | 283 | 283 | 174 | -1506 | 0
National Grid Plc |  | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220 | 220
Northern Gas Networks Ltd |  | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31 | 31
Scotland Gas Networks Ltd |  | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39
Southern Gas Networks Ltd |  | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Wales & the West Utilities |  | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
Check cell outstanding split | -200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Site Visit Resolution breakdown | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Registered |  | 6 | 6 | 6 | 6 | 6 | 6 | 9 | 9 | 10 | 11
Set to EX |  | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69
Legitimately Unregistered |  | 75 | 75 | 75 | 75 | 75 | 75 | 72 | 72 | 71 | 70
Eu has contract with supplier | bar: 2007 Dec to 2008 Sep
Live supply and burning Gas |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
No Access |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Total | 0 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 163 | 0
Check cell resolved breakdown |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A31: Adam Turbitt (AT097): Blank cells, Letter 1 Printed, Restart
Note on A32: Adam Turbitt (AT097): Letter 1 Sent, Letter 2 Printed
Note on A33: Adam Turbitt (AT097): Letter 2 Sent
Note on A36: Adam Turbitt (AT097): PSA, Actpend
Note on A34: Adam Turbitt (AT097): Site Visit
Note on A37: Adam Turbitt (AT097): No Gas
Note on A35: Adam Turbitt (AT097): Address, Query
Note on A38: Adam Turbitt (AT097): Vacant
Note on A40: Adam Turbitt (AT097): Conf
Note on A39: Adam Turbitt (AT097): DN Link, DE, EX

## Shipperless Data
Shipper Activity Data | 2007 |  | 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
No response from Shipper | 10546 | 8269 | 5601 | 5408 | 5444 | 5728 | 5517 | 6072 | 6232 | 6263 | 5844
Orphaned | 1514 | 2053 | 2083 | 2011 | 1946 | 2042 | 2023 | 1951 | 1957 | 1947 | 1944
Shipper intends to confirm | 1253 | 1193 | 1089 | 896 | 850 | 822 | 816 | 849 | 751 | 655 | 550
Total Shipper Activity MPRN's Including Orphaned | 13313 | 11515 | 8773 | 8315 | 8240 | 8592 | 8356 | 8872 | 8940 | 8865 | 8338
Target Level | 7000 | 6250 | 5500 | 4750 | 4500 | 4500 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
Cumulative - Shipper Activity Unregistered Sites Shipper Response | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
No response from Shipper | 10546 | 8269 | 5601 | 5408 | 5444 | 5728 | 5517 | 6072 | 6232 | 6263 | 5844 | 0
Orphaned | 1514 | 2053 | 2083 | 2011 | 1946 | 2042 | 2023 | 1951 | 1957 | 1947 | 1944 | 0
Shipper intends to confirm | 1253 | 1193 | 1089 | 896 | 850 | 822 | 816 | 849 | 751 | 655 | 550 | 0
Target | 6500 | 6000 | 5500 | 5000 | 4500 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
Total | 13313 | 11515 | 8773 | 8315 | 8240 | 8592 | 8356 | 8872 | 8940 | 8865 | 8338 | 0
Check Cell - Shipper Intent | bar: 2007 Nov to 2008 Oct
Cumulative - Shipper activity unregistered sites Age Analysis | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1 to 6 months old | 6610 | 5241 | 2758 | 2501 | 2171 | 2259 | 1956 | 2078 | 2141 | 2363 | 2115
7 to 12 months old | 3026 | 2113 | 1743 | 1671 | 1840 | 1867 | 1817 | 1974 | 1974 | 1696 | 1445
Over 12 months old | 1099 | 1056 | 1128 | 1104 | 1220 | 1337 | 1470 | 1712 | 1677 | 1628 | 1565
Over 24 months old | 1064 | 1052 | 1061 | 1028 | 1063 | 1087 | 1090 | 1157 | 1191 | 1231 | 1269
Total | 11799 | 9462 | 6690 | 6304 | 6294 | 6550 | 6333 | 6921 | 6983 | 6918 | 6394 | 0
Check Cell | bar: 2007 Nov to 2008 Oct
Cumulative - Unregistered 'Yes' responses age analysis | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1 to 6 months old | 3 | 9 | 37 | 28 | 16 | 7 | 44 | 28 | 29 | 26 | 19
7 to 12 months old | 546 | 490 | 281 | 159 | 28 | 33 | 31 | 53 | 51 | 46 | 39
Over 12 months old | 535 | 525 | 701 | 539 | 631 | 594 | 558 | 557 | 451 | 349 | 242
Over 24 months old | 169 | 169 | 70 | 170 | 175 | 188 | 183 | 211 | 220 | 234 | 250
Total | 1253 | 1193 | 1089 | 896 | 850 | 822 | 816 | 849 | 751 | 655 | 550 | 0
Check Cell | bar: 2007 Nov to 2008 Oct
Cumulative Orphaned End User Age Analysis | 2007 Nov: 2007; 2008 Jan: 2008
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1 to 6 months old | 0 | 348 | 179 | 31 | 9 | 69 | 39 | 19 | 31 | 24 | 32
7 to 12 months old | 76 | 278 | 404 | 463 | 420 | 388 | 369 | 303 | 222 | 124 | 105
Over 12 months old | 539 | 545 | 531 | 498 | 440 | 433 | 423 | 409 | 435 | 483 | 489
Over 24 months old | 899 | 891 | 969 | 1019 | 1077 | 1152 | 1192 | 1220 | 1269 | 1316 | 1318
Total | 1514 | 2062 | 2083 | 2011 | 1946 | 2042 | 2023 | 1951 | 1957 | 1947 | 1944 | 0
Check Cell | bar: 2007 Nov to 2008 Oct