## Slide 1: Entry Capacity Assignment Modification Discussion
UNC0779
  29th November 2021

## Slide 2: Timelines - Updates
Six Workgroups proposed:
  This is to give time to discuss options and fully explore any proposed alternates
  Return to Panel scheduled for February 2022
Analysis - presented at TxWG 4th November
  Storage Sites – Potential impact of EC Rate vs Discounted Reserve Price?
  UNC0728B interaction – Potential impact of EC Rate vs Discounted Reserve Price?
  In either case interaction with RRC cannot be modelled
ROM & Legal Text
  ROM to be raised following update of the single Modification for discussion in November Published 19/11/2021
  Legal text to be requested for December (earlier if possible) To be published prior to workgroup, however we may need to consider the text at TxWG on 02/12/2021 if time is needed to digest.
Implementation:
  Workgroups proposed to Feb-2022 - Workgroup report to be finalised in December TxWG and report to Panel that month
  Consultation to Apr-2022 – Should be completed by January 2022
  Ofgem Decision – Indication of potential decision timescale?
  Project Stand Up – 3 months - Confirmed by ROM
  System Development – 26 – 30 weeks - Confirmed by ROM
  A non-October start should be weighed against a potential Revenue Recovery Charge to compensate for any impacts.
Notes: Impact on User Commitment duration

## Slide 3: Timelines
Expected timeline
Fixed points i.e. workgroup and Panels are bordered.
The consultation period could be flexed but would still fall between two fixed Panel dates unless an extraordinary meeting was called.
A period of 3 months is assumed for an Ofgem decision, there is no firm basis for this assumption, guidance from Ofgem would be welcomed.
These timelines adhere to the details provided in the ROM
Implementation could potentially be achieved in week commencing 13th February 2023 dependant on other projects and system impacts.

## Slide 4: Timelines
Reduced timeline with no allowance for Ofgem decision
Fixed points i.e. workgroup and Panels are bordered.
The consultation period could be flexed but would still fall between two fixed Panel dates unless an extraordinary meeting was called.
This version does not include any time allowance for an Ofgem decision (i.e. Self Governance)
The shortest timelines proposed in the ROM is used here
Implementation could be achieved around the week commencing 17th October 2022 dependant on other projects and system impacts.