## DSC CHMC Issue Register
DSC Change Management Committee Issue Register
Issue Ref. | Issue | Background | Issue Originator | Date Created | Status | Priority for Discussion (H/M/L) | Status Date | Status Summary/Action taken | Next Review
DSC ChM 001 | Sustainable/equitable governance solutions | If a change has an indicated funding split that would lead to a voting imbalance, it is difficult for the consitutency represented by smaller numbers of votes to have an equitable voice. E.G. XRN5615 13/3/24 initial funding split suggested 50:50 Shipper: DN, Voting: 6:2 Shipper: DN. | DSC Change | 2024-03-13 | Live | Medium | 2024-05-08 | Options offered on 10 April, Customers must indicate that they wish to take one of these options forward. None have done this so far. Action 0301 closed. | June 2024 DSC Change
DSC ChM 002 | DDP Governance Data Accuracy | TBC | OC Centrica | 2024-03-13 | Live | Medium | 2024-05-08 | To be discussed at June 2024 DSC Change Management Meeting | June 2024 DSC Change
DSC ChM 003

## LookUps
Look Ups
Issue Originator | DSC Committee | Priority | Status
BG | DSC Change | High | Closed
BP | DSC Contract | Low | Hold
British Gas | DSC Credit | Medium | Live
Centrica
Centrica Storage Ltd
ConocoPhillips
Corona Energy
DSC Change
DSC Contract
DSC Credit
E.ON UK
EDF Energy
Electricity Supply Board
Energy 24
energywatch
Exxon Mobil
first:utility
GasTerra
Gaz de France
Gazprom
Joint Office
Macquarie Bank
National Grid Distribution
National Gas Transmission
Northern Gas Networks
RWE Npower
RWE Trading GmbH
Scotia Gas Networks
Scottish Power
Shell
Shippers
SSE
Statoil UK
Total Gas and Power
Transporters
Wales & West Utilities
Waters Wye